## model29-treatment-info
Model | Ecoregion | Treatment | LO_notes | Trt_ID | Prj_ID | Plan_Imp | Success | Dates_Confirmed | Init_Date | Comp_Date | Units | Num_Units | Trt_Type_Major | Trt_Type_Sub | Treatment_Type | Treatment_Seeded | Seed_List | Seed_Mix_Name | Seeds_or_Seedlings | Seed_List_Confirmed | Control_Areas | Seed_Application_Rate | Seed_Notes | Objectives | Planned_Implementation | Actual_Implementation | Treatment_Effect_and_Results | Trt_Feature_Type | Feature_Status | How_Feature_Created | Feature_Creation_Date | Total_Acres | BLM_Acres | GIS_Notes | Initiated_By | Trt_Concerns | Trt_Concerns_Desc | Problems_Apply_Trt | Problems_Apply_Trt_Desc | Conditions_At_Trt | Conditions_At_Trt_Desc | Trt_Notes | User_Updated
Model 29 | Central Basin and Range | Post-burn herbicide | Targeted noxious weeds | 13611 | 4902 | Implemented | Fully Successful | 1 | 00/00/2007 | 00/00/2008 | Acres | 3813 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | [7 empty] | Inventory, identify, and control the spread of noxious weeds within the treatment area. | Areas of noxious weed were inventoried and sprayed with herbicide or manually removed under contract. | The entire wildfire was inventoried for the presence of noxious weeds and subsequently treated to minimize the spread and establishment. | PI's assured that contract specifications were met for all contracts. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 5091.0737 | 3714.0695 |  |  | Erosion, Loss of Perennials, Habitat for sage grouse, Loss of cultural sites, Invasion by Cheatgrass | * The fire burned rapidly and with great intensity when wind driven, consuming virtually everything in its path. The fire burned range facilities, such as fences and one wildlife guzzler. Primary activities in the fire area include livestock grazing, off road vehicles, camping and hunting. Safety will be considered during seeding and mechanical treatment operations. There are homes (Greenville, UT) and private property (alfalfa and rangeland fields) below the location of the wildfire. These areas have already received impacts from flooding (mud flows) following recent precipitation events. * Throughout the burned area, soils are inherently prone to wind erosion and runoff generation. Because the fire consumed soil organic matter and coarse debris in most parts of the burn, the potential for runoff generation from a given precipitation event has increased. Areas of greatest potential impact are the community of Greenville, adjacent agricultural fields and Minersville Reservoir (which is on the State of Utah&$s 303 (d) list of impacted waters). Decreases in vegetation debris litter cover, increases in runoff generation, and decreases in soil structure and cohesion (due to loss of organic matter) have also increased the susceptibility of soils to erosion from sheet flow. On steeper slopes, there is also increased risk of rill erosion. * Greater sage-grouse (Centrocercus urophasianus), a Utah Division of Wildlife Resources and BLM sensitive species are found within the treatment area * Covering seed using mechanical methods may negatively impact cultural sites. There are potentially some cultural sites (recorded and unrecorded) within the Greenville Bench Fire Area. The potential for erosion damage and artifact looting is of concern. * Noxious weeds are present (Scotch thistle) within the surrounding area of the Greenville Bench Fire. | None |  | None |  | Since noxious weeds are growing in the area adjacent to the fire, the Plan states that the burned area would be inventoried and treated as needed. | 40:36
Model 29 | Central Basin and Range | Post-burn herbicide | Targeted knapweed (2,4-D) | 28746 | 10599 | Implemented | Unknown | 1 | 1999-05-01 | 1999-05-18 | Acres | 974 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | [7 empty] | - - - - - EFRP - - - - - Aerial spray 974 acres with Grazon... | - - - - - EFRP - - - - - Aerial spray...with Grazon in April, 1999... | The Simpson Springs fire was not revegetated; it was sprayed with Grazon herbicide to control Squarrose knapweed infestations. Herbicide application treatment and monitoring information have been submitted to the BLM Salt Lake District Office in another report (Duncan 1998). | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1288.6989 | 1250.4001 |  | Contractor | Noxious Weeds | #NAME? | None |  | None |  |  | 40:51
Model 29 | Central Basin and Range | Post-burn herbicide |  | 30876 | 11383 | Implemented | Partially Successful | 1 | 2007-05-31 | 2009-07-17 | Acres | 2136 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | [7 empty] | Control of noxious weeds is consistent with the management plans for the resource and will help protect the ecological integrity, biodiversity, and site productivity of this shrub-steppe plant community. Treatment of noxious weeds is necessary to comply with Nevada State Laws, to implement the Integrated Weed Management Program of the Elko Field Office, and to be responsible neighbors to the adjacent private landowners. Working cooperatively with local weed management groups and private landowners will achieve better weed management. | During the implementation of the emergency stabilization plan, treatments and evaluations will be conducted on approximately 2,400 acres (1,200 acres treatments and 1,200 acres evaluations) for noxious weed infestations. During the implementation of the rehabilitation plan, treatments and evaluations will be conducted on approximately 1,930 acres (965 acres of treatments and 965 acres of evaluations) for 2 years. Noxious weeds known to exist within the burned area are hoary cress, Russian knapweed, and Scotch thistle. More infestations may be detected as plants recover from the fire or establish from spread seeds. Integrated weed treatments will be used including, but may not be limited to, manual and chemical weed control measures. Manual treatments will be done by grubbing with shovels or hand pulling or chopping off of fruiting structures. Chemical treatments will be done following all label requirements and conform to the BLM Chemical Pest Control Handbook H-9011-1. Herbicides, Surfactants, and Dyes used will be approved for use on BLM administered lands and applied following standard safety and operating procedures. Herbicide application to rangeland sites will be by low pressure backpack sprayer or hand gun from an ATV. Herbicide application to road right-of-ways will be by vehicle mounted unit or ATV. No aerial application is planned. | Treatments were completed by the BLM Weeds Team, documented and reviewed by the Weeds Coordinator. Chemical treatments were done following label requirements and conform to the BLM Chemical Pest Control Handbook H-9011-1. Treated areas were mapped with GIS for size and species of infestation. ESR 2007 Weed treatments were conducted on noxious weeds infestations found within the burned area. In addition to treatment of weed species, this activity also includes inventory of the entire burn (39,734 acres) for weed presence and evaluation of treatments. Approximately 50 acres of weeds were treated and each of these 50 acres was evaluated for treatment success. Integrated weed treatments were used including manual and chemical weed control measures such as grubbing with shovels, hand pulling or chopping off fruiting structures and herbicide spraying. Fifty acres of noxious weeds (including 47 of Scotch Thistle and 3 of Russian Knapweed) were treated by BLM weeds crews. Most weed infestations on the Susie burn were contracted out. Post-treatment evaluations were not conducted. 2008 Control noxious weeds within the burn using integrated weed management techniques of manual and chemical weed control measures including grubbing with shovels, hand pulling, chopping fruiting structures, and herbicide spraying. Treatments were conducted on 67 acres of infestations within the burn, and each of these 67 acres was evaluated for treatment success. Sixty-seven acres of noxious weeds were treated under ES funding. Most treatments occurring in Dry Gulch and on the Susie Riparian Drill Seeding. Both chemical and mechanical treatments were employed by BLM weeds crews. A portion of Dry Gulch was also contracted out. Post treatment evaluations determined impact on target weed species and non-target vegetation. BAR 2008 Control noxious weeds within the burn using integrated weed management techniques of manual and chemical weed control measures including grubbing with shovels, hand pulling, chopping fruiting structures, and herbicide spraying. Treatments were conducted on 810 acres of infestations within the burn, and each of these 810 acres was evaluated for treatment success. Eight-hundred and ten acres were treated under BAR funding. Most of the treatments occurred in Dry Gulch and on the Susie Riparian Drill Seeding. Both chemical and mechanical treatments were employed by BLM weeds crews. Part of Dry Gulch was also contracted out. Post treatment evaluations determined impact on target weed species and non-target vegetation. 2009 Control noxious weeds within the burn using integrated weed management techniques of manual and chemical weed control measures including grubbing with shovels, hand pulling, chopping fruiting structures, and herbicide spraying. Treatments were conducted on 1209 acres of infestations within the burn, and each of these 1209 acres was evaluated for treatment success. One-thousand two-hundred and nine acres of Scotch Thistle were treated during 2009. Most treatments were implemented in Dry Gulch and on the Susie riparian Drill seeding. Both mechanical and chemical treatments were utilized by BLM weeds crews. A portion of Dry Gulch was also contracted out. Post-treatment evaluations were not conducted. | Effectiveness of weed treatments is evaluated by the BLM Weeds Team and the Weeds Coordinator and results of inventory and treatment are kept on file at the BLM office. Weed treatments are considered effective if >80% of the targeted weed species are affected by the treatment(s) during that year. ESR 2007 \u2013 No post-treatment evaluations were completed. 2008 \u2013 Treatment evaluation demonstrated that 95% of Scotch Thistle plants were either killed or visibly stunted with diminished seed production. The Scotch Thistle that was treated bolted and produced minimal seed, but seed appeared non-viable. BAR 2008 \u2013 Treatment evaluations demonstrated that 95% of Scotch Thistle plants were either killed or visibly stunted with diminished seed production. The Scotch Thistle that was treated bolted and produced minimal seed, which appeared to be non-viable. 2009 \u2013 No post-treatment evaluations were completed. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1650.2215 | 1084.8407 | Includes 2008 and 2009 treatments. No GIS for 2007 treatments, unless it covered the same area. |  | Erosion, Habitat for sage grouse, Livestock in treated area, Loss of Perenials, Noxious Weeds, Habitat for antelope, Habitat for mule deer, Habitat for wildlife, Invasion by non-native annuals, Special Status Species, Watershed degradation | The purpose of the proposed action described in the emergency stabilization and rehabilitation plans and this EA is to: protect the burned area from livestock grazing&* stabilize watersheds and upland soils to prevent further degradation to affected resources on lands within the fire perimeter or downstream drainages that may result from short duration, high intensity precipitation events&* reduce the potential for establishment of annual, invasive nonnative plant and noxious weed species&* allow the undamaged plant species time to reestablish&* treat the invasive nonnative plant and noxious weed species to prevent spreading&* and help provide forage, cover, and habitat for wildlife, including but not limited to, BLM designated special status species, migratory birds, fish, mule deer, pronghorn antelope, and sage grouse. The need for the proposed action is to: stabilize and prevent unacceptable degradation to natural and cultural resources&* minimize threats to life or property resulting from the effects of the fire&* construct physical improvements necessary to prevent degradation of land or resources&* and prescribe cost effective post-fire stabilization and rehabilitation measures necessary to protect human life, property, and critical cultural and natural resources. | None |  | None |  | This treatment also includes mechanical and hand treatments. Both BAR and ESR funding, some implemented in house and the rest contracted out. | 6:25
Model 29 | Central Basin and Range | Post-burn herbicide |  | 43348 | 16809 | Implemented | Unknown | 1 | 2017-08-01 | 2017-12-23 | Acres | 2000 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | [7 empty] | S5 - Disallow further expansion of noxious weed populations within fire affected areas. Treatments will attempt to reduce or eliminate infested acreages within the fire-affected areas. Coordinated monitoring/treatment will document and remove new infestations of noxious weeds. R5 - Primary objective is to reduce annual grasses and establish perennial vegetation |  | S5 - Inventory and control of noxious weeds within the Monroe Fire burned area. R5 - The treatment applied the aerial-seeded area with herbicide to control annual invasive plants in year one. This noxious weed treatment occurred prior to seeding, for seed bed prep, to suppress non-native invasive annual plants, and enhance success of seeding operation. This treatment is a coordination of herbicide treatment with a seeding treatment to advantage germination and seedling establishment of native or selected non-native perennials. |  | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2017-12-06 | 2430.2404 | 2428.2695 |  | Contractor | Establishment of seeded species, Habitat productivity, Habitat quality, Loss of desirable species, Invasion by non-native annuals, Invasive species, Noxious weeds | This treatment is a coordination of herbicide treatment with a seeding treatment to advantage germination and seedling establishment of native or selected non-native perennials. |  |  |  |  | S5 - 8/1/2017 R5 - 12/1/2017 - 12/23/2017 | 47:34
Model 29 | Central Basin and Range | Post-burn herbicide | 2,4-D; imazapic; glyphosate | 50661 | 20499 | Implemented | See Comments | 1 | 2018-03-01 | 2019-09-09 | Acres | 6063 | Herbicide/Weeds/Chemical | Herbicide | Herbicide Application | 0 | [7 empty] | For the purposes of biotic integrity decrease invasive species to 0.1-10 percent cover within the areas treated by herbicide within 5 years. | Invasive Exotic Plants and Noxious Weeds: Reduction of eighty percent cover of infestation. If invasive exotic and noxious weed treatments do not met objectives, an IDT will meet to decide if the site has the potential to meet objectives, if additional treatments are added. Up to five years of additional treatments may be requested on this site. | FY2020 - Lake Mead sprayed the fire on August 7th through 9th. They sprayed Russian Knapweed, Hoary Cress (Cardaria draba), and Russian thistle (Salsola Kali). A total of 14.35 total gallons of mix was sprayed. There were 3 different mixes used mix one was habitat and a surfactant, mix 2 was transline and a surfactant and mix 3 was Tordon 22K and a surfactant. The park service relayed that the fire\u2019s patches of noxious weeds has greatly reduced since they started treating. While monitoring the fire the monitoring crew also reported that the lines that were created when the fire was sprayed in 2018 for Cheatgrass are still visible. 2019 - Lake Mead Sprayed the fire on August 7, 8, 9, 10th and September 9th. There they spayed A. repens focusing on not just respraying the area that was sprayed the previous year (around and in the private enclosure) but also getting the patches that are on the roadway and new patches that appeared within the intermittent streams\u2019 ditches. Within the fire the spray lines from when the B. tectorum was sprayed in FY 2018 can still be seen when the fire was visited in July. 2018 - The flats were sprayed with Imazapic and Glyphosate. Bromus tectorum (Cheatgrass) was treated aerially through a contract that sprayed in April/May. The contract was only for the low lands and excluded the stream that runs through the fire. | FY 2018: Discussion: Bromus tectorum (Cheatgrass) was treated aerially through a contract that sprayed in April/May. The contract was only for the low lands and excluded the stream that runs through the fire. In regards to the noxious weeds, in October 2017 funding was placed into an interagency agreement with the National Park Service\u2019s (NPS) Lake Mead National Recreation\u2019s (LAKE) Invasive Plant Management Team (IPMT) for future treatments. They were on the ground treating from August 8th to the 13th. Results: Acroptilon repens (Russian Knapweed) was the only noxious weed that was treated. The rest of the fire was monitored for noxious weeds and none were found. A total of 592 gallons of chemical was sprayed one the sites with a mix of Weeder 64 and either Tordon 22K or Transline. The Cheatgrass was sprayed and looking at the site later on the chemical had an impact, and there was minimal missed areas. ? Recommendations: Continue treatments of the site and funding the LAKE EPMT. FY 2019: Discussion: Lake Mead Sprayed the fire on August 7, 8, 9, 10th and September 9th. There they spayed A. repens focusing on not just respraying the area that was sprayed the previous year (around and in the private enclosure) but also getting the patches that are on the roadway and new patches that appeared within the intermittent streams\u2019 ditches. Within the fire the spray lines from when the B. tectorum was sprayed in FY 2018 can still be seen when the fire was visited in July. Recommendations: Continue to treat for Noxious Weeds FY 2020: Discussion: Lake Mead sprayed the fire on August 7th through 9th. They sprayed Russian Knapweed, Hoary Cress (Cardaria draba), and Russian thistle (Salsola Kali). A total of 14.35 total gallons of mix was sprayed. There were 3 different mixes used mix one was habitat and a surfactant, mix 2 was transline and a surfactant and mix 3 was Tordon 22K and a surfactant. The NPS relayed that the fire\u2019s patches of noxious weeds had greatly reduced since they started treating. While monitoring the fire the monitoring crew also reported that the lines that were created when the fire was sprayed in 2018 for Cheatgrass are still visible. FY 2021: Discussion: NPS Lake Mead IMPT crew continued treatments of Russian thistle and then mostly focused on reducing hoary cress within the area. They inventoried new areas for noxious weeds as well. Results: Treatments have been effective at reducing noxious weeds within the burned area. Not much growth of Russian thistle during current year, but this is likely due to drought conditions observed within the area. Hoary cress and Russian knapweed were found and spot-treated within the area. Recommendations: Continue inventory and spot-treatment of noxious weeds throughout the burned area, focusing on elimination of small patches found during inventory first. FY 2022: Discussion: NPS Lake Mead IMPT crew continued treatments of hoary cress within the area. Results: Treatments have been effective at reducing noxious weeds within the burned area. However, Russian thistle did expand within the area due to more precipitation in the past spring. Overall, objectives for noxious weed control have been met due to significant decrease in density of noxious weeds within the area. It was difficult to measure with changes in precipitation patterns that drastically changed density of invasive species in the area from year to year, but the overall density of invasive species decreased and this trend should continue with the successful establishment of perennial grasses present. Recommendations: Continue monitoring by field office staff, as possible, to ensure health of vegetation established from seeding. | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2019-08-01 | 6061 | 6060 |  | Contractor | Invasive species, Habitat quality, Invasion by cheatgrass, Invasion by non-native annuals | Bromus tectorum (Cheatgrass) | Unknown | Unknown | Unknown | Unknown |  | 54:08
Model 29 | Central Basin and Range | Post-burn herbicide | Imazapic | 50730 | 18412 | Implemented | See Comments | 2 | 2016-10-19 | 2016-11-03 | Acres | 4820.5 | Herbicide/Weeds/Chemical | Herbicide | Herbicide Application | 0 | No seed list | [6 empty] | 1.) Imazapic: The objective of the Imazapic treatment is to suppress cheatgrass in order to establish the favorable perennial grasses, forbs, and shrubs into the site. The presence and abundance of the forage kochia as well as cheatgrass would be compared between years to determine treatment effectiveness. 2.) Fuelbreak: The objective of the treatment is to create a break in the continuity of fuels that will, in the event of a wildland fire, allow for suppression actions to be conducted safely and reduce overall fire size. The treatment objectives will be met if there are one and a half forage kochia seedlings per square meter. | Monitoring implementation/effectiveness: Monitoring data to determine if objectives are being met are being completed by crews from Eastern Nevada Landscape Coalition. Further evaluations on data will be made in the summary. | The Aerial Imazapic/Aerial Overseed Rock Creek PHMA & GHMA Treatment was an aerial herbicide application of Imazapic in the fall of 2016 | Density: The Aerial Imazapic/Drill Rock Creek PHMA & GHMA Treatment was an aerial herbicide application of Imazapic in the fall of 2016, followed by an aerial seeding in the winter of 2016-2017 and a drill seeding the following winter of 2017-2018. The ground seeding was applied via rangeland drill to the public burned land in areas selected to be in accordance with the ecological sites and elevation and was comprised of Snake River Wheatgrass, Bluebunch Wheatgrass, Siberian Wheatgrass, Gooseberry Leaf Globemallow, Four-wing Saltbush Sandberg\u2019s Bluegrass. AIM Plots 04 and 05 were monitored in 2019. The four-wing saltbush establishment is showing reduced progress towards success: there were a recorded average of 0.03 seeded four-wing saltbush plants per square meter in 2018 surveys and none recorded in the two plots in 2019. The treatment is considered successful when one big sagebrush seedling, one and a half forb species (yarrow or flax) and one and a half grass seedlings per square meter are established. Regrowth of Sandberg bluegrass and crested wheatgrass was observed on the plots. Forb seedlings are displaying reduced establishment success in these sites: 0.80 seeded blue flax plants per square meter were recorded in 2018 monitoring and none were recorded in the two plots in 2019. Seeded grasses have are still showing rehabilitation success and are very successful in third year monitoring: there were an average of 50.34 seeded grasses per square meter in the treatment area. Cover: Average foliar canopy cover has decreased to 69.3% in the treatment area. Perennial grasses have 39.7% cover. Cheatgrass cover had reduced cover (12.5%) in 2017, an intended positive correlation to the aerial herbicide treatment. Cheatgrass cover more-than doubled, to 27.6%, from 2017 to 2018. The cheatgrass coverage is up to 33.3% at least in the two-plot average of 2019 monitoring. This level of cheatgrass cover is less cover than all other non- imazapic treated areas in the Hot Pot rehab area. Native perennial plant regrowth has been reduced, with perennial grasses at 39.7% cover and perennial forbs at 1.3% cover. Sandberg\u2019s bluegrass (Poa secunda) cover decreased to 14.7%, while squirreltail (Elymus elymoidies) improved to 8% cover. Tall tumble mustard cover increased to 7.7% - it appeared to be hampered initially by the herbicide as it had only 0.8% cover in 2017. Overall, the native and seeded perennial plant species are competing well against the annual invasive grasses and forbs; this positively correlated with the aerial herbicide application in the fall of 2016. These results display a success in the aerial imazapic treatments. Gaps: Gaps in canopy foliar cover have increased from the second to third growing seasons but have not reached 2017 levels. The majority of gaps are between 101 and 200cm. Canopy cover represents less than half of the average 25m transects. These gaps make the site susceptible to wind and water erosion. Species Richness: 2017: An average of twenty-two (21.6) different plant species was observed within the 2,827.4 square meter monitoring plots. 2018: An average of thirty-six different plant species was observed within the 2,827.4 square meter monitoring plots. 2019: An average of twenty-five (24.5) different plant species was observed within the two 2,827.4 square meter monitoring plots. Ecological sites and Erosion: Hot Pot Rock Creek Imazapic AIM Plot 02 is located in a Rangeland Loamy 8-10\u201d P.Z. R024XY005NVsite in a former / / Artemisia tridentata ssp. wyomingensis / Achnatherum thurberianum (/ Wyoming big sagebrush / Thurber's needlegrass) vegetation community. 2017: Wind and water erosion effects were present on the plot in minimal ways; there were short and rarely occurring water flow patterns, rare deposition and runoff, and rarely occurring pedestals. 2018: Soil and site stability were not impaired by the very few rills and few pedestals on the site. 2019: Plot not monitored in 2019. Hot Pot Rock Creek Imazapic AIM Plot 04 is located in a Rangeland Loamy 8-10\u201d P.Z. R025XY019NV site in a former / / Artemisia tridentata ssp. wyomingensis / Achnatherum thurberianum - Achnatherum hymenoides (/ Wyoming big sagebrush / Thurber's needlegrass - Indian ricegrass) vegetation community. 2017: Wind and water erosion effects were commonly occurring on the plot; there were moderately long but rarely occurring water flow patterns, very few rills, and commonly occurring deposition and runoff and pedestals. 2018: Soil and site stability have improved into the second growing season: there were only very short and rarely occurring water flow patterns, rarely occurring deposition and runoff, and few pedestals. 2019: Similar pedestalling was observed as in 2018, whereas increased deposition/runoff and decreased water flow patterns were observed. Hot Pot Rock Creek Imazapic AIM Plot 05 is located in a Rangeland Loamy 8-10\u201d P.Z. R025XY019NV site in a former / / Artemisia tridentata ssp. wyomingensis / Achnatherum thurberianum - Achnatherum hymenoides (/ Wyoming big sagebrush / Thurber's needlegrass - Indian ricegrass) vegetation community. 2017: Wind and water erosion effects were commonly occurring on the plot; there were very short, rarely occurring water flow patterns, very few rills, and commonly occurring deposition and runoff and pedestals. 2018: Soil and site stability were minimally impacted by the moderately long (but rarely occurring) water flow patterns and common pedestals. 2019: Similar pedestalling and water flow patterns were observed along with increased deposition/runoff compared to the 2018 surveys. Hot Pot Rock Creek Imazapic AIM Plot 06 is located in a Rangeland Loamy 8-10\u201d P.Z. R024XY005NV site in a former / / Artemisia tridentata ssp. wyomingensis / Achnatherum thurberianum (/ Wyoming big sagebrush / Thurber's needlegrass) vegetation community. 2017: Wind and water erosion were present on the plot; there were moderately long and commonly occurring water flow patterns, widespread deposition and runoff, and commonly occurring pedestals. Other soil disturbance present were widespread animal burrows 2018: Not monitored in second year. 2019: Plot not monitored in 2019. Hot Pot Rock Creek Imazapic AIM Plot 07 is located in a Rangeland Loamy 8-10\u201d P.Z. R024XY005NV site in a former / / Artemisia tridentata ssp. wyomingensis / Achnatherum thurberianum (/ Wyoming big sagebrush / Thurber's needlegrass) vegetation community. 2017: Wind and water erosion were present on the plot; there were long and commonly occurring water flow patterns, widespread deposition and runoff, and commonly occurring pedestals. 2018: Not monitored in second year. 2019: Plot not monitored in 2019. Aerial Imazapic and Drill Rock Creek PHMA & GHMA Treatment Recommendations: Monitoring results have shown that the aerial application of Imazapic herbicide has effectively targeted and reduced the cover of annual, invasive grasses while leaving perennial, desirable plants intact. Monitoring results have also shown that drill seeding treatment ESR rehabilitation objectives have exceeded objectives for grass seedling establishment in their third growing season. However, seeded shrubs and forbs require more rest to establish if they are to present on the plots at all. An allotment closure was issued for the Twenty Five allotment in the North Six Mile pasture where Imazapic Plots 02, 04, 05, 06, and 07 are located. The closure objective of three perennial grasses per square meter has been met. It is advised that grazing management include resting, rotations, and other measures to give more time for the seeded species to establish well in the area. | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2024-04-19 | 4908.72 | 4675.62 |  | See Cooperators List | Establishment of seeded species, Hazardous fuels reduction, Invasion by cheatgrass, Invasion by non-native annuals, Invasive species | 1) Suppress cheatgrass in order to establish the favorable perennial grasses, forbs, and shrubs. 2)create a break in the continuity of fuels that will, in the event of a wildland fire, allow for suppression actions to be conducted safely and reduce overall fire size. |  |  |  |  | Estimate cost calculated using contract order and actual acres treated. $25 an acre multiplied by 4820.5 acres equal $120,512.50. Original contract was only for 509 acres, however feature size and PARs show that much more was treated. | 0:47
Model 29 | Central Basin and Range | Post-burn herbicide | Imazapic | 51025 | 20559 | Implemented |  | 2 | 2017-09-27 | 2017-10-12 | Acres | 16352 | Herbicide/Weeds/Chemical | Herbicide | Herbicide Application | 0 | [7 empty] | Establish desirable species at 3 per square meter or more (density) within 3 years. |  | Plateau Contract completed 9/27-10/12/17 on 16,352 acres by Hammond Helicopter at $5.88/ac. for the application. Used 5 oz. imazapic/ac. in 3 gal water/ac. w/ 1 qt. non-ionic surfactant per 100 gal. solution. Herbicide and surfactant cost=$69,691. Total imazapic treatment cost = $10.30/ac. | Plateau treatment successfully reduced the amount of returning cheatgrass which was prominent in this area, particularly at lower elevations. | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2019-09-10 | 16322.33 | 16092.8 |  | Contractor | Establishment of seeded species | Establish desirable species. | [5 empty] | 38:22
Model 29 | Central Basin and Range | Post-burn herbicide | Imazapic | 54109 | 21239 | Implemented | See Comments | 1 | 2018-10-22 | 2018-10-31 | Acres | 1505 | Herbicide/Weeds/Chemical | Herbicide | Herbicide Application | 0 | [7 empty] | For the purposes of biotic integrity decrease invasive annual grass by 80 percent density within the burn perimeter within 2-12 months. | Aerially apply imazapic (commonly known as 'Plateau') on approximately 1,558 acres impacted by the Sheep Creek Fire in the fall of 2018. With the elimination of the standing cheatgrass it is anticipated that the herbicide treatment would provide a good control of cheatgrass for two growing seasons to allow the existing vegetation to recover and the seedings to establish with limited competition. | Aerial Herbicide Implemented, verified by RIPS report, As Built Map, and Pesticide Application Record. | 2019 Herbicide Treatment Density: AIM Plot 10 received no seeding, but was stratified within the herbicide treatment area with the objective of decreasing invasive annual grass by 80 percent density within the burn perimeter within 2-12 months. While there were no seeded species on this plot, it does have the highest number of perennial grass regrowth. Large form grasses were observed at a frequency of 1.08 per square meter and small form grasses at 30.67 per square meter. The treatment seems to have reduced the cover of cheatgrass (Bromus tectorum) and allowed native perennials to take up the ecological space left. See 2019 AIM Data Results for more details. 2020 Density Results: Herbicide Treatment Density: AIM Plot 10 received no seeding, but was stratified within the herbicide treatment area with the objective of decreasing invasive annual grass by 80 percent density within the burn perimeter within 2-12 months. While there were no seeded species on this plot, it does have the highest number of perennial grass regrowth. Large form grasses were observed at a frequency of 0.50 per square meter and small form grasses at 32 per square meter. The treatment seems to have reduced the cover of cheatgrass (Bromus tectorum) and allowed native perennials to take up the ecological space left. 2020 AIM Data Results: Sheep Creek AIM Plot 10: Increased pedestalling and similar long water flow patterns as 2019 were observed. This is an indication of slight increase in erosion on the site. | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2020-06-08 | 1605.88 | 1519.91 | Treatment acres less than feature and planned acreage. | BLM and Cooperators | Invasion by cheatgrass, Invasion by non-native annuals, Invasive species | Invasive annual grass |  |  |  |  | Cheatgrass was the noted pest from the Pesticide Application Record. 400 gallons per load of pesticide mix. | 1:51
Model 29 | Central Basin and Range | Post-burn herbicide |  | 54650 | 21328 | Implemented | Failure | 1 | 2018-11-01 | 2022-06-21 | Acres | 716 | Herbicide/Weeds/Chemical | Herbicide | Herbicide Application | 0 | No seed list | [6 empty] | For the purposes of soil and site stability decrease non-native grasses by 80 percent cover to assist with stabilization measure for 3 years | Invasive Exotic Plants and Noxious Weed Treatments: Invasive exotic plants are known to occur within the Copper Fire perimeter and in the surrounding landscape. In order to maximize a successful rehabilitation outcome, the BLM must strive to reduce both invasive exotic plants and Nevada listed noxious weeds. These species will often times outcompete desirable native and non-native species and disrupt the overall function of any given ecosystem. Several examples of invasive exotic plants are known to occur within the area of the Copper Fire include Bromus tectorum (Cheat Grass), Alyssum desertorum (Desert Madwort), Halogeton glomeratus (Saltlover), and Lepidium perfoliatum (Clasping Pepperweed). There were no known Nevada listed noxious weed species found within the fire. Nevada State Law requires that all populations of noxious weed be treated. There is an increased potential for these populations to establish and expand within burned areas. Invasive exotic and noxious weed species can have seeds banks that persist through a burn and are often times the first species to germinate following a fire. Existing seed sources can be supplemented by wind, vehicles, and livestock moving through the area. Given the extent of invasive exotic species populations, especially in the lowland treatment area, there is a limited potential for recovery without specific invasive exotic and noxious weed species treatments. The BLM is proposing both chemical and targeted grazing treatments to manage the spread of invasive exotic and noxious weed species populations. The BLM generally spot treats populations of noxious weed species and most invasive exotic species as part of post fire rehabilitation. The BLM will use an approved herbicide mix, which will be sprayed at a recommended rate. Monitoring and treatments will be funded under this project for a period of five years. The BLM will use lmazapic within the fire perimeter to reduce the Cheat Grass, assist the reseeding measures, and promote native plant recovery. lmazapic is a relatively selective herbicide. It is used primarily to suppress Cheat Grass, and it will not affect the success of seeding efforts. If this treatment occurs prior to the growing season of desirable perennial species, then the BLM will consider the inclusion of a Glyphosate herbicide. Glyphosate herbicides will kill all plants it comes into contact with as long as they are actively growing. The BLM will implement this treatment in the fall or early spring. All chemical treatments will be entered into the National Invasive Species Information Management System (NISIMS) or a BLM accepted alternative. | This fire was sprayed by NDOW in November 2018. FY2020 - Due to a failed spraying this fire was resprayed in November 2019. | FY 2019: Discussion: Fire was surveyed for Noxious Weeds while the monitoring crew were on the fire and while the fence contract was happening. Results: No noxious weeds found Recommendations: Continue to monitor FY 2020: Discussion: Fire was surveyed for Noxious Weeds while the monitoring crew were on the fire. Results: No noxious weeds found. Recommendations: Continue to monitor. FY 2021: Discussion: Fire was surveyed for Noxious Weeds while the monitoring crew were on the fire. Results: No noxious weeds found. Recommendations: Continue to monitor. FY 2022: Discussion: Fire was surveyed for Noxious Weeds while the monitoring crew were on the fire. IMPT crew inventoried and treated previously sprayed areas. Results: No noxious weeds found by BLM crew near monitoring plots, but noxious weeds were observed and treated by IPMT crew. Recommendations: Continue to monitor and retreat infestations observed. | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2020-08-04 | 716.09 | 716.09 |  | See Cooperators List | Noxious weeds | Cheatgrass | Unknown | No documentation | Unknown | No documentation |  | 25:39
Model 29 | Central Basin and Range | Post-burn herbicide | Imazapic | 57018 | 21751 | Implemented | See Comments | 1 | 3/00/2020 | 2022-06-08 | Acres | 1480 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | [9 empty] | In March of 2020 the fire was sprayed with Imazapic by the Nevada Department of Wildlife (NDOW). FY 2021 7/10/21, 7/13/21 The area was inventoried and treated by the Lake Mead IPMT crew (7/10/21). The burn was also surveyed by BLM monitoring crew (7/13/21). FY 2022 6/7/22, 6/8/22 The area was inventoried and treated by the Lake Mead IPMT crew and surveyed by BLM monitoring crew. | 2022 Monitoring report results FY 2020: Discussion: The National Park Service Lake Mead National Recreation Area\u2019s Invasive Plant Management Team (IPMT) treated the fire for Carduus nutans (musk thistle) they sprayed a total of 0.75 gallons of mix of Transline (clopyralid). Recommendations: Continue to treat the fire, as it recovers there will probably be more noxious weeds appearing in the fire based on the seed bank that was present pre-fire. FY 2021: Discussion: The Lake Mead IPMT crew inventoried and spot-sprayed noxious weeds found within the area. The monitoring crew also surveyed the area for presence of noxious weeds. Results: The crew found and sprayed hoary cress and musk thistle within the burned area. Recommendations: Continue to have the crew survey as spot-spray noxious weeds within the area. FY 2022: Discussion: The Lake Mead IPMT crew inventoried and spot-sprayed noxious weeds found within the area. The monitoring crew also surveyed the area for presence of noxious weeds. Results: The crew found and sprayed hoary cress within the burned area. Recommendations: Continue to have the crew survey as spot-spray noxious weeds within the area. | Polygon | Confirmed | Exported from an internal USGS Fire Perimeter Layer | 2021-03-08 | 1480.22 | 1480.22 |  | Other Agency | Invasion by cheatgrass | The Horse Fire burned in an area that has not burned before. On three sides of Horse Fire the 1999 Trailcanyon Fire burned, and there were also other fires in this area since then but none as close as the 1999 fire. Empirical evidence from these fires show that with human assistance, this area can recover but without assistance, this area trends towards a Bromus tectorum (Cheat Grass) monoculture. |  |  |  |  | Discussion: In March of 2020 the fire was sprayed with Imazapic by the Nevada Department of Wildlife (NDOW) | 35:23
Model 29 | Central Basin and Range | Post-burn herbicide | Glyphosate, imazapic | 57035 | 21762 | Implemented | See Comments | 2 | 3/00/2020 | 3/00/2020 | Acres | 6442 | Herbicide/Weeds/Chemical | Herbicide | Herbicide Application | 0 | [7 empty] | Objectives: For the purposes of soil and site stability decrease non-native grasses by 80 percent cover to assist with stabilization measure for 3 years The objective of the additional treatments is to treat and remove invasive exotic annual grasses and forbs (mainly Cheatgrass) found within the burned area around the campground. Treatments would be found successful if they result in an 80 percent effectiveness rate with chemical treatments. |  | The fire was sprayed in March of 2020. It was sprayed Aerially with a mix of Glyphosate, and Imazapic. FY2021- FY 2021: Discussion: Fire surveyed by monitoring crew and Lake Mead IPMT crew. Spot-sprayed noxious weeds. Results: IPMT crew sprayed hoary cress found within the burned area. Recommendations: Continue to monitor, survey, and spot-spray noxious weeds within the area. | The area showed signs of spraying during the spring growth of cheatgrass. Recommendations: monitor but the fire shouldn\u2019t need to be resprayed. 2022 ESR Monitoring Results R14: Additional Treatment Objective: The objective of the additional treatments is to treat and remove invasive exotic annual grasses and forbs (mainly Cheatgrass) found within the burned area around the campground. Treatments would be found successful if they result in an 80 percent effectiveness rate with chemical treatments. FY 2020: Discussion: The fire was sprayed in March of 2020. It was sprayed Aerially with a mix of Glypohsoate, and Imapzapic. Results: The area showed signs of spraying during the spring growth of cheatgrass. Recommendations: Monitor but the fire shouldn\u2019t need to be resprayed. | Polygon | Confirmed | Exported from an internal USGS Fire Perimeter Layer | 2021-03-09 | 6447.05 | 6447.04 |  | Contractor | Invasion by cheatgrass, Invasion by non-native annuals | Most of the acreage within the Summit Fire has burned before. The 1985 Dixie Fire, the 2006 Smelser Pass Fire, and the 2011 Buffalo Valley South Fire all intersect with the Summit Fire. Empirical evidence from these fires show that with human assistance, this area can recover but without assistance, this area trends towards a Bromus tectorum (Cheat Grass) monoculture. Emergency Stabilization will focus on stabilizing the hills to prevent further erosion. Burn Area Rehabilitation efforts will focus on treating invasive plants and re-vegetating native grasses, forbs, and shrubs in the low lands to enhance ecological diversity and to re-establish vegetation on and around the area. Seeding will also reduce the extent of invasive exotic plants within the area. The expectation is to not only re-establish the correct plants within their ecological zones, but also reduce the potential for fires within this area in the future. |  |  |  |  | No amounts of herbicide given, application was a mix of glyphosate and imazapic. | 58:35
Model 29 | Central Basin and Range | Post-burn herbicide |  | 69326 | 24616 | Implemented | See Comments | 1 | 00/00/2021 | 00/00/2021 | Acres | 2039 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | No seed list | [6 empty] | To promote biotic integrity, decrease frequency and cover of noxious species. | Treat 4,778 acres of the burned area for 3 years. This would include yearly weed inventory/survey, and treatment of any discovered noxious species. | Aerial broadcast herbicide treatment were applied to the Baldy and Flat Fires. | 2022 Monitoring Results Monitoring crews noted bull thistle (Cirsium vulgare) in one monitoring plot. The herbicide treatment did not appear to reduce the abundance of invasive annual grasses such as cheatgrass, which were found at very low covers in both the herbicide treated and untreated portions of the burn. | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | None | 2039.39 | 2039.39 |  | Unknown | Habitat quality, Invasion by cheatgrass, Invasive species, Noxious weeds | To promote biotic integrity, decrease frequency and cover of noxious species. |  |  |  |  | Trade Name is Panoramic, Manufacturer is Alligare, adjuvant was water, target was cheatgrass | 19:05
Model 29 | Central Basin and Range | Post-burn herbicide | Imazapic | 69625 | 24727 | Implemented | Unknown | 2 | 2022-09-01 | 9/00/2022 | Acres | 4410 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | No seed list | [6 empty] | reduction or eradication of target species. This would mitigate weed spread and reduce wildfire risk. Tank mixes would strictly follow the label of the chemical involved. Target species is cheatgrass and red brome. | Approximately 4,410 acres would be treated with a pre-emergent herbicide during summer, fall/winter or early spring depending on site conditions. A 2gal/acre formulation of the herbicide Panoramic would be applied aerially at a rate of 6-10oz/acre of the active ingredient imazapic. This treatment is an effort to reduce the frequency and density of invasive annual grasses such as cheatgrass and red brome and reduce wildfire risk. Herbicide application would strictly adhere to the herbicide label directions and Ely District SOPs. Timing of application would occur in coordination with the Nevada Department of Wildlife (NDOW) to mitigate any wildlife concerns. | In September 2022, the entire BLM portion of the burned area was aerially applied with Imazapic herbicide. Target Species Cheatgrass/Red brome. Adjuvant used was Alligare Water Conditioner with an intended application rate of 2-4 pints/100 gal spray solution. | unknown | Polygon | Confirmed | Digitized by BLM field office personnel, using an aircraft GPS unit | None | 4324.14 | 4316.01 |  | Unknown | Invasive species, Noxious weeds | To inhibit invasive plant species. |  |  |  |  | EPA Registration Number = 66222-141-81927 Manufacturer = ALLIGARE Intended Rate of Application (Formulated) = 6-10 Fluid Ounces/Acre Pounds Per Acre = 0.09-.16 pounds/acre acid equivalent | 11:22
Model 29 | Central Basin and Range | Post-burn herbicide | Imazapic | 69661 | 24733 | Implemented | See Comments | 2 | 9/00/2022 | 9/00/2022 | Acres | 3700 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | No seed list | [6 empty] | To promote biotic integrity, decrease frequency and cover of noxious species on 12,718 acres for 3-5 years. This would include yearly weed inventory/survey, and treatment of any discovered noxious species. | Approximately 12,450 acres would be treated with a pre-emergent herbicide during summer, fall/winter or early spring depending on site conditions. A 2gal/acre formulation of the herbicide Panoramic would be applied aerially at a rate of 6-10oz/acre of the active ingredient imazapic. | A broadcast pre-emergent herbicide was applied to the western half of the burned area in September 2022 to control invasive grasses. | 2022 monitoring crews noted Sahara mustard (Brassica tournefortii) on one monitoring plot: BISH-AMIX-02 and the identity was confirmed with photos. It is unlikely to be a satellite infestation. Further survey is needed to understand the size this infestation, which is likely to expand in 2023 given the wet 2022/23 winter. Monitoring data and reconnaissance by BLM staff also documented a large Russian thistle (Salsola tragus) infestation on the west side of the burn that likely expanded in size and abundance following a strong summer monsoon season in 2022. | Polygon | Confirmed | Digitized by BLM field office personnel, using an aircraft GPS unit | None | 3699.48 | 3699.48 |  | Unknown | Invasive species, Invasion by cheatgrass, Noxious weeds | To reduce the frequency and density of invasive annual grasses such as cheatgrass and red brome and reduce wildfire risk. | [5 empty] | 24:36
Model 29 | Central Basin and Range | Post-burn herbicide |  | 69802 | 24759 | Implemented | Unknown | 2 | 2016-10-19 | 2016-10-21 | Acres | 2500 | Herbicide/Weeds/Chemical | Herbicide | Herbicide Application | 0 | No seed list | [6 empty] | Apply herbicides in select locations for control of Medusahead Rye and Cheatgrass. | The work consists of applying herbicides in select locations for control of Medusahead Rye and Cheatgrass on BLM administered lands. The work shall consist of application of contractor-furnished herbicide using an aircraft within the potential project area as defined on attached maps. Application will occur within 7 to 20 units totaling 2,500 acres. Herbicide will be applied utilizing water as a carrier, with no less than an average of 10 gallons/acre of tank mix applied. | Herbicide application of approximately 3,100 acres in accordance with the Statement of Work. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 2499.93 | 2499.93 |  | Contractor | Invasive species, Invasion by cheatgrass | To control of Medusahead Rye and Cheatgrass. |  |  |  |  | Treatment dates verified using the Pesticide Application Record | 22:40
Model 29 | Central Basin and Range | Post-burn herbicide |  | 70358 | 24944 | Implemented | Unknown | 2 | 2017-10-01 | 2018-04-20 | Acres | 1310 | Herbicide/Weeds/Chemical | Herbicide | Herbicide Application | 0 | No seed list | [6 empty] | The purpose of this project is to remove hazardous fuels and conduct long term maintenance of the fuelbreaks in order to enhance protection and limit the potential spread of wildfire. | Apply herbicide as part of an on going fuelbreak maintenance and by applying herbicide | Herbicide applied to the Santa Rosa Fuelbreak. Implementation verified by GIS attribute table. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1309.34 | 1279.88 |  | Unknown | Hazardous fuels reduction, Habitat for wildlife, Invasive species, Noxious weeds | To maintain existing fuelbreak. | [5 empty] | 50:30
Model 29 | Central Basin and Range | Post-burn herbicide |  | 70406 | 24967 | Implemented | Unknown | 2 | 2017-10-01 | 2017-11-30 | Acres | 2350 | Herbicide/Weeds/Chemical | Herbicide | Herbicide Application | 0 | No seed list | [6 empty] | To inhibit invasive plant species |  | 2 herbicide/pesticide applications over the entire unit 10/1/2017 - 11/30/2017 2,251 acres treated as part of the BPSS Annual Control Project. 10/27/2017 - 11/1/2017 2,290 acres treated as part of the BPSS Annual Control Project. Implementation verified using GIS attribute table. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 2291.77 | 2291.58 |  | Unknown | Invasive species | Invasive plant species control |  |  |  |  | Acres, herbicide chemical, and application method verified using monitoring reports | 45:05
Model 29 | Central Basin and Range | Post-burn herbicide |  | 71152 | 25100 | Implemented | Unknown | 1 | 00/00/2022 | 00/00/2022 | Acres | 3050 | Herbicide/Weeds/Chemical | Herbicide | Herbicide Application | 0 | No seed list | [6 empty] | Reduce annual invasive grass cover, restore degraded rangelands within Greater sage-grouse PHMA, GHMA, and OHMA areas, and to promote landscape resistance and resilience while reducing wildfire susceptibility. | BLM is proposing to utilize herbicide within the project boundary for invasive plant and noxious weed management. Treatment would be applied by aircraft, tractor, truck, UTV, or backpack sprayer depending on plant distributions and terrain limitations. Areas could be retreated depending on previous treatment success. BLM would also conduct a noxious weed inventory within the general project areas and treat noxious weed infestations. Treatments would consist of an integrated weed management approach utilizing mechanical and chemical methods. Chemical treatments would be done in accordance with all label requirements and conform to the BLM Chemical Pest Control Handbook H-9011-1. All herbicides, surfactants, and dyes shall be approved for use on BLM administered lands and applied following standard safety and operation procedures. | Aerial herbicide application, implementation verified by BLM aerial aircraft GPS data. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, using an aircraft GPS unit | None | 3082.09 | 3082.06 | BLM FO aerial herbicide GIS data. | Contractor | Invasive species, Noxious weeds | Hazardous fuels reduction |  |  |  |  | The BLM is proposing treatments totaling a footprint no more than 50,000 acres in the East Range, Pershing County and Humboldt County, Nevada over the span of 10 years. Annual treatment workloads would be ~1,000-5,000 acres. | 38:31
Model 29 | Central Basin and Range | Post-burn herbicide | Imazapic | 71274 | 24960 | Implemented | Unknown | 2 | 2021-10-01 | 2021-10-03 | Acres | 1905 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | No seed list | [6 empty] | Inhibit invasive annuals to reduce wildfire risk and improve habitat for various wildlife species. | Adaptive management techniques used on areas throughout the Tuscarora field office to include the use of imazapic to target cheatgrass and medusahead. | Aerial herbicide application completed, verified by GIS attribute table. | Unknown. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | 2021-11-03 | 1907.34 | 1890.48 | Treatment acres based on GIS attribute table and are slightly lower than feature acres. | Unknown | Habitat for wildlife, Invasion by cheatgrass, Invasion by non-native annuals | Improve habitat for various wildlife species, and reduce the potential for future wildfires through the reduction of fine fuels. |  |  |  |  | PHMA_NON_FIAT_TFO_AM_Herbicide for Sheep Creek and Little Antelope annual grass treatments. | 15:42
Model 29 | Central Basin and Range | Post-burn herbicide |  | 71478 | 24196 | Implemented | Unknown | 2 | 2020-10-06 | 2020-10-06 | Acres | 955 | Herbicide/Weeds/Chemical | Herbicide | Herbicide Application | 0 | No seed list | [6 empty] | Fuelbreak maintenance. | Unknown. | Aerial herbicide application at 2 gallon/acre formulation completed, verified by GIS attribute table and as built map. | Unknown. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | 2021-04-06 | 955.65 | 955.65 |  | Unknown | Fire hazard | Over time established fuel break has become less able to reduce wildfire risk through brush re-establishment and cheatgrass encroachment. | [5 empty] | 17:15
Model 29 | Central Basin and Range | Post-burn herbicide | Imazapic | 71513 | 25225 | Implemented | Unknown | 2 | 2021-09-24 | 2021-09-26 | Acres | 2000 | Herbicide/Weeds/Chemical | Herbicide | Herbicide Application | 0 | No seed list | [6 empty] | Use adaptive herbicide maintenance to reduce annual grass fine fuel loading and treat any invasive/noxious plants that may become established within the fuel break. | Herbicide applications will utilize Imazapic, or other BLM-approved herbicide, to reduce the spread and establishment of noxious or invasive weeds. Herbicide may be applied aerially or using ground-based equipment. No ground disturbance or treatments will occur in ROWs. The construction of fuelbreaks would primarily occur in late September through February to avoid impacting greater sage-grouse during critical life stages (e.g. lekking, nesting, and brood rearing). | Herbicide was applied to Cheatgrass, confirmed by PAR. | Unknown | Polygon | Confirmed | Digitized by LTDL data entry personnel, merged map from various sources |  | 1999.23 | 1998.89 |  | Contractor | Fire hazard, Habitat for greater sage grouse, Hazardous fuels reduction, Public safety | To decrease fragmentation and impacts to habitat. Reduce fuel loads near roadways enabling suppression resources to more effectively engage a fire by reducing fire behavior. |  |  |  | Zero wind, 45-75 degrees F |  | 5:32
Model 29 | Central Basin and Range | Post-burn herbicide |  | 71628 | 25256 | Implemented | Unknown | 2 | 2022-05-20 | 2022-06-05 | Acres | 3724 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | No seed list | [6 empty] | Herbicide application to Scotch thistle (Onopordum acanthium) & Hoary cress (Lepidium draba). | Unknown. | Ground herbicide application completed, verified by GIS attribute table. | Unknown. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | 2022-10-06 | 3726.53 | 3380.25 |  | Unknown | Invasive species, Hazardous fuels reduction | Weed Control |  |  |  |  | Both Terrestrial and Aquatic mix include surfactant & dye. | 42:56
Model 29 | Central Basin and Range | Post-burn herbicide |  | 72545 | 21378 | Implemented | Unknown | 1 | 10/00/2020 | 9/00/2021 | Acres | 1746 | Herbicide/Weeds/Chemical | Herbicide | Herbicide Application | 0 | No seed list | [6 empty] | Not explicitly mentioned in the ESR plan or monitoring, however shape matching FY20 Drill Seeding suggests that the purpose was to help with the establishment of seeded species. | Conduct noxious weed surveys, treatments, and monitoring on known noxious weed infestations found within and in close proximity to the burned area. Hoary cress is known to exist in close proximity to the fire perimeter. Cheatgrass is also known to be prevalent in the fire area. It is anticipated that there would be an increase in noxious and invasive weeds resulting from the disturbance created by the fire and fire suppression activities. Treatments would consist of an integrated weed management approach emphasizing mechanical and chemical means. | 2022: The ESR rehabilitation objectives of the aerial and drill seedings have not been fully met, a year after treatments have been completed. The plot is showing small signs of recovery but it is still recommended that closures continue to allow for the plots to receive appropriate rest to allow for seeded species to establish root systems and communities. | 2022: The ESR rehabilitation objectives of the aerial and drill seedings have not been fully met, a year after treatments have been completed. The plot is showing small signs of recovery but it is still recommended that closures continue to allow for the plots to receive appropriate rest to allow for | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2024-03-20 | 1837.13 | 1804.13 |  | Unknown | Establishment of seeded species, Invasion by cheatgrass, Invasion by non-native annuals, Invasive species | Cheatgrass is also known to be prevalent in the fire area. It is anticipated that there would be an increase in noxious and invasive weeds resulting from the disturbance created by the fire and fire suppression activities. Treatments would consist of an integrated weed management approach emphasizing mechanical and chemical means. |  |  |  |  | Feature shape and treatment acres obtained from As Built Map, herbicide used taken from 2022 monitoring summary. | 33:17
Model 29 | Central Basin and Range | Post-burn herbicide |  | 72657 | 22004 | Implemented | Successful | 2 | 2019-10-14 | 2019-10-14 | Acres | 1001.21 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | No seed list | [6 empty] | Inhibit Cheatgrass | Noxious weed inventories and treatments would be conducted on new and existing infestations found within and/or close proximity to the Echo Fire perimeter several years post-fire. The known noxious weeds near or within the fire perimeter include Scotch thistle. It is anticipated that there would be an increase in the amount of noxious weeds resulting from the disturbance created by the fire and fire suppression activities. Inventory methods would be a broad scale ocular observation for qualitative and quantitative data. Infestations found would be documented using the global positioning system (GPS) for mapping and would be included in the plan for treatment at the next appropriate treatment time. The access roads through the fire and the dozer lines would also be surveyed. Treatments would consist of an integrated weed management approach emphasizing mechanical and chemical methods. Chemical treatments would be done in accordance with all label requirements and conform to the BLM Chemical Pest Control Handbook H-9011-1. Chemicals used would be approved for use on BLM administered lands and applied following standard safety and operating procedures. | Herbicide applied, confirmed by Pesticide Use Report. | 2021: The presence and potential infestation of Scotch thistle (Onopordum acanthium) and cheatgrass weeds within or near the fire perimeter is a concern. Inventory and treatment in the area are ongoing. Imazapic treatment was implemented on 1,218 and 976 acres the falls of 2018 and 2019 respectively. Recommendations: Inventory and treatment of above identified weeds should continue into the future. Aggressive treatment and inventory will control the noxious species that are present in the fire area now. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | 2019-10-10 | 1002.43 | 1001.42 |  | Contractor | Invasion by cheatgrass | To inhibit cheatgrass growth/establishment. | [5 empty] | 54:09
Model 29 | Central Basin and Range | Post-burn herbicide |  | 72687 | 21201 | Implemented | Successful | 2 | 2019-10-14 | 2019-10-14 | Acres | 1238.33 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | No seed list | [6 empty] | For the purposes of biotic integrity decrease noxious species by 80 percent in post fire monitoring within 5 years. | It is anticipated that there will be an increase in the amount of noxious weeds resulting from the disturbance created by the fire and suppression activities. Treatments would consist of an integrated approach using mechanical and chemical means. Due to non-motorized access in the WSA, inventory efforts on the Hogan Fire will be more time-consuming and labor intensive than fires outside a WSA. | Aerial Herbicide application completed, verified by Pesticide Application Report and Record. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | 2019-09-23 | 1239.83 | 1239.82 |  | Contractor | Invasion by cheatgrass | Cheatgrass control | [5 empty] | 25:54
Model 29 | Central Basin and Range | Post-burn herbicide |  | 73145 | 24930 | Implemented | Unknown | 2 | 2018-05-15 | 2018-06-02 | Acres | 1900 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | No seed list | [6 empty] | Control of thistle within the Adobe Fire Area | Unknown. | Phase 2 of herbicide spraying complete | Unknown. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | 2020-04-09 | 1885.62 | 948.72 |  | BLM | Noxious weeds | Control of non-native thistle. |  |  |  |  | LF31 claimed 1500 acres and L1020 WEEDS claimed 400 acres. | 52:34
Model 29 | Central Basin and Range | Post-burn herbicide |  | 73204 | 25777 | Implemented | Unknown | 1 | 2022-05-27 | 2022-06-24 | Acres | 6079 | Herbicide/Weeds/Chemical | Herbicide | Noxious Weeds: Weed Control - Herbicide Application | 0 | No seed list | [6 empty] | Weed Control | Unknown. | Herbicide treatment for Scotch thistle, Hoary Crest, and Russian Knapweed completed, verified by GIS attribute table. | Unknown. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | 2022-10-06 | 6079.34 | 5805.53 | Feature acres used for treatment acres. | Unknown | Noxious weeds | Weed Control |  |  |  |  | Both Terrestrial and Aquatic herbicide mixes include approved surfactant and dye. | 32:49