## model06-treatment-info
Model | Ecoregion | Treatment | LO_notes | Trt_ID | Prj_ID | Plan_Imp | Success | Dates_Confirmed | Init_Date | Comp_Date | Units | Num_Units | Trt_Type_Major | Trt_Type_Sub | Treatment_Type | Treatment_Seeded | Seed_List | Seed_Mix_Name | Seeds_or_Seedlings | Seed_List_Confirmed | Control_Areas | Seed_Application_Rate | Seed_Notes | Objectives | Planned_Implementation | Actual_Implementation | Treatment_Effect_and_Results | Trt_Feature_Type | Feature_Status | How_Feature_Created | Feature_Creation_Date | Total_Acres | BLM_Acres | GIS_Notes | Initiated_By | Trt_Concerns | Trt_Concerns_Desc | Problems_Apply_Trt | Problems_Apply_Trt_Desc | Conditions_At_Trt | Conditions_At_Trt_Desc | Trt_Notes | User_Updated
Model 6 | Northwestern Great Plains | Prescribed burn |  | 12235 | 4381 | Implemented | None | 2 | 2010-09-07 | 2010-09-07 | Acres | 478 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Major issues pertaining to the Fort Meade Recreation Area include: ~ Risk of catastrophic wildfire. ~ Encroachment of pine and loss of meadow/park habitat. ~ Decadent stands of bur oak woodlands. ~ Insect and disease infestation. ~ Habitat, forage, and vegetation diversity for wildlife species. Wildlife ~ Increase vegetation diversity and effective edge where possible. Retain and/or enhance key habitat components for game and non-game wildlife species. ~ Identify and protect traditional high value roost trees, nesting areas, and brood rearing areas for wild turkeys. ~ Protect cavity bearing trees. ~ Increase browse, enlarge fringe areas, and improve oak and mast reproduction. ~ Increase forage production. ~ Increase the amount of edge habitat for wildlife by restoring natural forest openings. ~ Identify and protect thermal and escape cover for wildlife. Forestry ~ Maintain existing stands of ponderosa pine, control insect and disease infestation, prevent excessive fuel buildups, and reduce safety hazards. ~ Improve wildlife habitat and enhance opportunities for recreation and scenic viewing. ~ Maintain open-park like stands of ponderosa pine for scenic values. ~ Remove and control pine encroachment in meadow areas and deciduous draws. ~ Maintain existing acreage and increase regeneration of hardwoods. ~ Encourage hardwood establishment and rejuvenate decadent bur oak woodlands. ~ Break up dense forest canopies to improve production diversity of understory vegetation in forested areas. ~ Develop sustainable forest conditions while restoring the area back to its natural ecological system. Fire Management ~ Reduce the threat of wildfire to adjacent private land. ~ Protect, maintain or enhance native plants and sensitive plant communities; reduce the spread of exotic plant species; reduce hazardous fuel buildups, and stimulate grasses, forbs, shrubs, or trees. ~ Reduce fuel loads, forest density, and the potential for wildfire while reducing conflicts with key wildlife habitat components. ~ Reduce the risk of uncharacteristically intense fires. ~ Increase the average crown base height by thinning out smaller trees. ~ Reduce risk to life, property, and natural resources. Grazing );>- Maintain and improve all rangeland uplands and riparian areas in proper\xb7 functioning condition. );>- Increase the production and diversity of herbaceous plants in meadows and forest understory. );>- Improve the quality of forage by burning dry, cured grass to allow vigorous new growth and added nutrients the following spring or fall. Visual Resources );>- Enhance and preserve the overall visual character of the Fort Meade Recreation Area. Cultural Resources );>- Reduce the threat of catastrophic wildfire destroying the National Register Eligible built environment. );>- Create opportunities to identify additional pre-historic sites by removal of dense ground cover. );>- Protect historic trails and roads from encroachment of trees. );>- Protect the visual character of the fort for interpretation of the forts history. | The boundaries of this prescribed burn will consist of roads, mowed fireline, and some handline. This prescribed burn has been broken up into 14 different blocks. Smaller burn blocks will increase the opportunities to burn and meet the prescribed fire objectives. Some of the burn blocks will have solid black around portions of the unit from previous burning that will have taken place. This will reduce the risk of an escaped fire occurring and reduce the area that the holding crews will need to cover. The allowable area for this prescribed burn is the unit boundaries. This prescribed burn will not be allowed to burn outside of the unit boundaries. | Burning of Unit Block M and N totaling 478 acres |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | 2014-12-12 | 477.771 | 477.6591 |  | BLM | Encroaching vegetation, Hazardous fuels reduction, Fire hazard | Due to fire suppression and a lack of active forest management in the Fort Meade Recreation Area (FMRA), the forest, rangeland, and ecosystem structure and health has been declining. Currently, the forested areas of the Fort Meade Recreation Area are susceptible to catastrophic wildfires. If this happens, a catastrophic wildfire would threaten lives, consume property, and have a negative impact on the ecosystem and historic value of the area. Management of these ecosystems will promote a healthy, diverse, and resilient landscape that could be maintained and used for recreation for generations to come. With multiple resource management goals and objectives, the proposed treatments would maintain and improve the ecological structure and aesthetic values of both the forested and rangeland areas of the Fort Meade Recreation Area, while enhancing watershed values and wildlife habitat. A primary goal of ecological restoration is to reverse the decline of ecosystem health by restoring the structure and function. Ecological restoration is also referred to as the process of renewing and maintaining ecosystem health. The focus of ecosystem management is on long term ecosystem sustainability. By protecting forests and grasslands from unnaturally intensive and destructive wildfires, the conditions of our public lands are improved, firefighter and public safety improves, and the landscape attributes valued by society are conserved. | None |  | None |  |  | 25:53
Model 6 | Northwestern Great Plains | Prescribed burn |  | 12238 | 4381 | Implemented | None | 2 | 2009-11-05 | 2009-11-05 | Acres | 776 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Major issues pertaining to the Fort Meade Recreation Area include: ~ Risk of catastrophic wildfire. ~ Encroachment of pine and loss of meadow/park habitat. ~ Decadent stands of bur oak woodlands. ~ Insect and disease infestation. ~ Habitat, forage, and vegetation diversity for wildlife species. Wildlife ~ Increase vegetation diversity and effective edge where possible. Retain and/or enhance key habitat components for game and non-game wildlife species. ~ Identify and protect traditional high value roost trees, nesting areas, and brood rearing areas for wild turkeys. ~ Protect cavity bearing trees. ~ Increase browse, enlarge fringe areas, and improve oak and mast reproduction. ~ Increase forage production. ~ Increase the amount of edge habitat for wildlife by restoring natural forest openings. ~ Identify and protect thermal and escape cover for wildlife. Forestry ~ Maintain existing stands of ponderosa pine, control insect and disease infestation, prevent excessive fuel buildups, and reduce safety hazards. ~ Improve wildlife habitat and enhance opportunities for recreation and scenic viewing. ~ Maintain open-park like stands of ponderosa pine for scenic values. ~ Remove and control pine encroachment in meadow areas and deciduous draws. ~ Maintain existing acreage and increase regeneration of hardwoods. ~ Encourage hardwood establishment and rejuvenate decadent bur oak woodlands. ~ Break up dense forest canopies to improve production diversity of understory vegetation in forested areas. ~ Develop sustainable forest conditions while restoring the area back to its natural ecological system. Fire Management ~ Reduce the threat of wildfire to adjacent private land. ~ Protect, maintain or enhance native plants and sensitive plant communities; reduce the spread of exotic plant species; reduce hazardous fuel buildups, and stimulate grasses, forbs, shrubs, or trees. ~ Reduce fuel loads, forest density, and the potential for wildfire while reducing conflicts with key wildlife habitat components. ~ Reduce the risk of uncharacteristically intense fires. ~ Increase the average crown base height by thinning out smaller trees. ~ Reduce risk to life, property, and natural resources. Grazing );>- Maintain and improve all rangeland uplands and riparian areas in proper\xb7 functioning condition. );>- Increase the production and diversity of herbaceous plants in meadows and forest understory. );>- Improve the quality of forage by burning dry, cured grass to allow vigorous new growth and added nutrients the following spring or fall. Visual Resources );>- Enhance and preserve the overall visual character of the Fort Meade Recreation Area. Cultural Resources );>- Reduce the threat of catastrophic wildfire destroying the National Register Eligible built environment. );>- Create opportunities to identify additional pre-historic sites by removal of dense ground cover. );>- Protect historic trails and roads from encroachment of trees. );>- Protect the visual character of the fort for interpretation of the forts history. | The boundaries of this prescribed burn will consist of roads, mowed fireline, and some handline. This prescribed burn has been broken up into 14 different blocks. Smaller burn blocks will increase the opportunities to burn and meet the prescribed fire objectives. Some of the burn blocks will have solid black around portions of the unit from previous burning that will have taken place. This will reduce the risk of an escaped fire occurring and reduce the area that the holding crews will need to cover. The allowable area for this prescribed burn is the unit boundaries. This prescribed burn will not be allowed to burn outside of the unit boundaries. | Burning of Unit Block K and L totaling 776 acres |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 776.2599 | 769.6113 |  | BLM | Encroaching vegetation, Hazardous fuels reduction, Fire hazard | Due to fire suppression and a lack of active forest management in the Fort Meade Recreation Area (FMRA), the forest, rangeland, and ecosystem structure and health has been declining. Currently, the forested areas of the Fort Meade Recreation Area are susceptible to catastrophic wildfires. If this happens, a catastrophic wildfire would threaten lives, consume property, and have a negative impact on the ecosystem and historic value of the area. Management of these ecosystems will promote a healthy, diverse, and resilient landscape that could be maintained and used for recreation for generations to come. With multiple resource management goals and objectives, the proposed treatments would maintain and improve the ecological structure and aesthetic values of both the forested and rangeland areas of the Fort Meade Recreation Area, while enhancing watershed values and wildlife habitat. A primary goal of ecological restoration is to reverse the decline of ecosystem health by restoring the structure and function. Ecological restoration is also referred to as the process of renewing and maintaining ecosystem health. The focus of ecosystem management is on long term ecosystem sustainability. By protecting forests and grasslands from unnaturally intensive and destructive wildfires, the conditions of our public lands are improved, firefighter and public safety improves, and the landscape attributes valued by society are conserved. | None |  | None |  |  | 21:45
Model 6 | Northwestern Great Plains | Prescribed burn |  | 12268 | 4390 | Implemented | Unknown | 1 | 2004-09-15 | 2004-09-18 | Acres | 891 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | 1. Create a mosaic of grassland and sagebrush areas and increase production and forage quality of herbaceous vegetation on about 900 acres each year. 2. Increase wildlife use, habitat edge-diversity, and forage production in the dense stand of rocky mountain juniper vegetation type. 3. Reduce fuel loading and create breaks in continuous stands of heavy fuels to reduce the potential for a large scale loss of habitat to wildfire. 4. Reduce fuel loading and create fuel breaks in the Wildland Urban Interface areas associated with active oil and gas production facilities. | See PBP (pp. 17-21). | See Fall 2004 PFR. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | 2004-10-18 | 891.5603 | 651.6303 |  | BLM and Cooperators | Brush control, Encroaching vegetation, Fire hazard, Forage for livestock, Forage for wildlife, Forage quality, Habitat for mule deer, Habitat for elk, Hazardous fuels accumulation, Habitat quality, Public safety, Sagebrush, Wildland Urban Interface | The primary resource objective is to improve forage and other habitat for mule deer and elk by applying various vegetation treatments including prescribed fire. | Other (See Trt Notes) | Numerous spot fires occurred across the primary and secondary control line. Dense smoke limited visibility and access to some spots presented safety issues requiring holding forces to back out. The prescribed burn was declared a wildland fire (escaped prescribed fire) at about 15:30. The Double Gate wildland fire No. BFQ8 ran about 1.8 miles with the wind and burned about 289 acres outside the unit, but within the MMA. | None |  | No costs reported by treatment - only total project costs. Treatment costs estimated from PBP estimates. | 44:11
Model 6 | Northwestern Great Plains | Prescribed burn | Reduce ponderosa pine | 18467 | 6700 | Implemented | None | 2 | 2009-06-04 | 2009-06-13 | Acres |  | Prescribed Burn | Prescribed Burn | Prescribed Burn | 0 | [7 empty] | Conduct all burn activities in a safe and efficient manner. Confine the fire to the burn unit. Under burn a minimum 75% of Ponderosa Pine stands. Consume a minimum of75% of 1hr and 10 hr. fuels within timber stands. Top kill a minimum of 50% of the juniper and Douglas fir less than 3" dbh. Limit mortality in trees 9&& dbh and larger to 30%. | A test fire will be conducted by ground crews, on the up hill I down wind side of the unit as directed by the RXB2 and if results are satisfactory firing will commence into the wind I down slope in order to initiate a backing fire and to begin establishing black lines. Black lining may be conducted by the holding forces and will consist of an ignition team progressing along each flank. As black lines attain sufficient depth, or it becomes apparent that the majority of the burn unit perimeter will not support fire spread due to sparse, and or, green fuels then Aerial ignition of the interior may begin at the direction of the Burn Boss/FIRB. The Aerial ignition operation will concentrate on the North facing timbered slopes and will consist of running strips on the contour across the slope, beginning at the top and progressing down slope I up wind whenever possible. The preferred sequence for Aerial ignition of the interior would be to lag behind black lining operations, and progress down slope toward Lion coulee. Communication between Ground and Aerial resources will be maintained at all times for safety and to coordinate between ignition and holding forces. Firing will continue along the flanks of the unit as directed by the RXBB/FIRB. Aerial Ignition will be done using PSD. | Lion Coulee EAST Unit 1 2013 Days 1 and 2: (Narrative provided by Jennifer Walker) 2022 Needle litter carried fire nicely except during early mornings. Adequate consumption of 1hr and 10hr fuels. 2022 Herbaceous green-up was advanced (cool season grasses were in flowering stage), but old litter carried fire through green during daytime operations. Even so, ignitions had to focus on more receptive fuels in timbered areas. 2022 All conifers were actively growing from recent bud-break so were reluctant to sustain fire; but plentiful juniper ladder fuels with needle litter contributed to isolated torching of canopy trees. There were very long lag periods for heat buildup prior to torch-outs, so igniters had difficulty judging the timing of their dots/strips. The isolated torching contributed to scorching of adjacent trees and associated mortality of those trees. Lion Coulee EAST Unit 1 2013 Day 3: (Narrative provided by Karly Krausz) Fire behavior and effects were variable, dependent of fuel bed: 2022 Overall, fire behavior was more favorable this day, than the two previous days. There was generally less isolated torching in the timber. Fire carried through the grass and needle litter by mid-morning. There was also adequate consumption of 1- and 10-hour fuels. 2022 Two firing operations took place during this burn period. One small operation on the north flank and the other, larger operation on the south flank. Although observations were taken at both sites during the day, most of the observations were taken on the south flank. 2022 At 1057 hours, the south flank had increased isolated torching and fire carried more through the grasses than just a few hours prior. I observed pockets of regeneration torching/consumed. Juniper was readily consumed. On the north flank, ignition operations were just getting started. 2022 At 1155, the north flank operations were in full swing, the blackline on north flank is wide and appears to be complete from K-F. Crews continue to reinforce K-F down the slope. The south flank continues to have some isolated torching. Crews used firing pistol to ignite deep draws, while others hand-lite to reinforce pistol operations. Smoke dispersal is to the E/SE. Pocks for regeneration (D. fir and p.pine) readily ignite. 2022 At 1305, the south flank continues to have good fuel consumption from firing operations. The north flank has been smoked in due to downslope drafts. A wind change from the north occurred around this time. 2022 At 1811, winds are steady out of the west 2013 timber & juniper are most receptive to ignitions. Lighters are bottom lighting big trees, maybe firing patterns have contributed to increased mortality. 2022 At 2200, ignition operations were complete on the south flank. The crews plan to allow the fire to back down the slopes into the steeper draws overnight. Some overall fire behavior observations were recorded post-burn on day 3. 2022 More than 30% scorch (including trees less than 30201d) on south aspect. Overall, scorch was estimated at 40%. 2022 North aspect: Overall scorch is 70%. 2022 Canopy trees of all sizes, 30% or more green of all size classes remain. \xbd of the canopy is greater than 9201d dbh. Lion Coulee EAST Unit 2: (Narrative provided by Jennifer Walker) 2022 Needle litter carried fire nicely except during early mornings. Adequate consumption of 1hr and 10hr fuels. 2022 Herbaceous green-up was advanced (cool season grasses were in flowering stage), but old litter carried fire through green during daytime operations. Even so, ignitions generally had to focus on more receptive fuels in timbered areas. Spotting occurred in the bottom of Lion Coulee during mop-up ignitions midday on 6/13 when the fuel moisture dropped to 2% at 82oF for a probability of ignition of 100%. There was some cheat-grass in the bottom. 2022 All conifers were actively growing from recent bud-break so were reluctant to sustain fire; but plentiful juniper ladder fuels with needle litter contributed to isolated torching of canopy trees. There were very long lag periods for heat buildup prior to torch-outs, so igniters had difficulty judging the timing of their dots/strips. The isolated torching contributed to scorching of adjacent trees and associated mortality of those trees. NOTES: In this mixed fire regime of DF, PP, and juniper, consider increasing the mortality objective for big trees. Or instead, use a crown replacement objective for ~20% (or other appropriate) of unit. |  | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2014-09-05 | 253.5271 | 185.424 |  |  | Forest health, Hazardous fuels reduction | The BLM has identified two units for treatment. The East Unit, totaling approximately 730 acres, contains mature stands of ponderosa pine and Douglas fir with a dense understory of small diameter conifers and juniper. In this unit, fire would be used to reduce understory fuels and provide fuel breaks in areas with a closed, continuous canopy. The West Unit, 960 acres in size, contains areas of heavy fuel loading as a result of blowdown from a summer Tornado that went through the area in 2002. It is proposed to treat about 50-70% of a unit providing a mosaic of burn intensities and vegetative diversity. | None |  | None |  |  | 57:03
Model 6 | Northwestern Great Plains | Prescribed burn | Reduce pine and conifers | 31895 | 11804 | Implemented | None | 2 | 2010-05-13 | 2010-05-15 | Acres | 1361.08 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Underburn a minimum of 75% of pine stands Top kill 30 % to 50% of conifers less than 3" dbh Limit mortality in trees 8&& dbh and larger to 30% |  | There was no FEMO on Day 1, so there are no photos or documented fire behavior observations. This narrative is from Walker's observations in combination with Krage&$s weather documentation. Grass had greened to about 6" height. Some p-pine had begun to break bud. Needle litter was damp in the morning and dry in the afternoon. Early in the day, jackpot fuels were targeted to achieve objectives. Fire behavior was minimal so igniters spot-fired pine stringers in coulees. As the day progressed, fire carried readily in green grass with cure and strip-firing was used in some locations to bring black along with the lighters. Winds were terrain-driven and caused isolated torching where a.m. behavior would not. There were no photo points in this portion of Unit D. Midmorning conditions were drier than Day 1. Test fire ignitions at 0930 in needle/grass litter carried fairly well except in areas with light fuel loads in green grass. Backing fire through needle litter achieved objectives nicely; p-pine seedlings and juniper in grassy areas experienced scorching or isolated torching. Scorch heights in canopy trees was generally less than 1 O&$ and rarely up to 20&$. At 1400, 1-hr fuel moisture (calculated) dropped to 3% with a Pl of 80%. Fire behavior was meeting treatment objectives, but ignitions were stopped and the line was checked because prescribed fire parameters were exceeded. By 1600, calculated fuel moistures were within prescription, and at 1700 ignitions were resumed. Fire behavior was active until after 1900. At 2000 fuel moistures rose to 9% and ignitions targeted jackpot fuels until ignitions were complete. Test fire was initiated at about 1000 under drier conditions than Day 2. Fire carried readily in the needle litter, backing at about 6&& /min. Pine seedlings readily torched if ignited. Large trees scorch heights were 5&$ to 10&$, sometimes 20&$. Treatment objectives were achieved, but were anticipated to exceed large tree mortality as conditions became warmer and drier. Ignitions were stopped at about 1100. By 1200, weather observations had exceeded prescribed fire parameters. Another spot Wx was requested at - 1500 which indicated RH recoveries would allow evening/nighttime ignitions. By 1600 weather conditions were within prescription parameters and ignitions were resumed, but shifting wind from the north again shut down operations at about 1800. At - 1900 ignitions were resumed in the southern end of the unit with a new test fire . Fire effects achieved treatment objectives, so operations continued and were completed by about 2 100. Isolated torching occurred from firing= until about 1930, after which strip-firing was required to produce isolated torching of juniper and seedling pockets. |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1361.0792 | 914.5418 |  |  | Unknown, Forest health, Rangeland health, Habitat for wildlife | The purpose of the proposed action is to reduce stand density and fuel loadings while improving or maintaining the existing fire regime / condition classes. Improvements to the overall condition class within the project area will likely result in benefits to wildlife habitat through an increase in the diversity and production of herbaceous vegetation. | None |  | None |  |  | 30:33
Model 6 | Northwestern Great Plains | Prescribed burn | Reduce ponderosa pine and conifers | 31897 | 11805 | Implemented | None | 2 | 2013-05-02 | 2013-05-02 | Acres | 1642.76 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Reintroduce fire into the project area. Conduct all prescribed burn activities in a safe and efficient manner Reduce natural fuel loadings. Confine the fire to the burn unit Reduce ladder fuels and stand density in forested Under burn a minimum 75% of ponderosa pine areas. stands Reduce conifer encroachment into adjacent Top kill 40% - 60% of conifers less than 3"dbh meadows and rangelands. Limit mortality in trees 8&& dbh and larger to 30% or less | A. Ground Based Ignition: All operations will be managed by an RXB2. Various firing techniques including strip, backing, flanking, and head fires will be used depending on fuels, weather, topography, and observed fire behavior. The RXB2/FIRB will select the best firing pattern(s) that will provide for safety, minimize escape potential and smoke impacts, and meet objectives. Initial operations will focus on using manmade and natural barriers, along with areas of sparse fuels, to confine the fire to the unit and begin backing or flanking the fire down slope, and/or, into the wind as necessary in order to establish black lines. As black lines obtain sufficient depth for control purposes, interior ignition will begin and may utilize a variety of ignition patterns such as strip head or chevron firing in order to generate the desired fire behavior. Holding resources may assist with ignition operations as allowable. Generally, ignition operations will progress from the top of the slope downward, and/or into the wind, until tying into the bottom of the coulee(s) or an established control line. Interior two track roads, natural barriers, and constructed control lines within the units will provide for burning the units in sections over the course of several days as/if needed. The fire's edge will be secured at the end of each operational shift. Ignition may be conducted using drip torches, ATV/UTV torches, fusees, and flare lanchers. B. Simultaneous Ground based and Aerial Ignition: A test fire will be conducted by ground crews, on the uphill and/or downwind side of the unit as directed by the RXB2/FIRB. If results are satisfactory, firing will commence into the wind and/or down slope in order to initiate a backing fire and to begin establishing black lines. Black lining may be conducted by the holding forces and will consist of an ignition team progressing along each flank. As black lines attain sufficient depth, or it becomes apparent that the majority of the burn unit perimeter will not support fire spread due to sparse, and/or green fuels, aerial ignition of the interior may begin at the direction of the Burn Boss/Fl RB. The aerial ignition operation will concentrate on target fuels within the interior of the unit and will consist of running strips on the contour across the slope, beginning at the top and progressing down slope and/or up wind whenever possible. The preferred sequence for aerial ignition of the interior would be to lag behind black lining operations, and progress down slope toward coulee bottom(s) or established control lines. Communication between ground and aerial resources will be maintained at all times for safety and to coordinate between ignition and holding forces. Firing will continue along the flanks of the unit as directed by the RXBB/FIRB. Aerial ignition may be completed using a PSD or helitorch. | The unit was blacklined by hand crews, followed by a helicopter used to finish ignition in the interior of the unit. The helicopter was funded by contributions from RMEF. |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1642.7601 | 960.7139 |  |  | Forest health, Rangeland health, Hazardous fuels reduction | Prescribed fire will be used to reduce natural fuel loadings and improve or maintain Fire Regime Condition Class (FRCC) in the project area. Mixed age Ponderosa stands in the project area vary from open stands to closed stands with thick understory and scattered pockets of conifer seedlings becoming established under the mature over story and encroaching into adjacent rangelands. Treatment in timber vegetation types will target juniper, small diameter conifers and seedlings, and surface fuels. Treatment in adjacent rangelands will reduce conifer encroachment and increase species variability in herbaceous cover. Prescribed fire will be applied in a manner that creates low to moderate intensity surface fire with occasional single and group tree torching into the forest canopy | None |  | None |  |  | 19:51
Model 6 | Northwestern Great Plains | Prescribed burn | Reduce ponderosa pine and conifers | 31899 | 11806 | Implemented | None | 2 | 2012-04-09 | 2012-05-18 | Acres | 4945.61 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | The prescribed fire objectives of this project would be to: I. Under burn a minimum 75 percent of the ponderosa stands. 2. Top-kill 30-60 percent of conifers less than 3" dbh (diameter at breast height) 3. Limit mortality in trees 8&& dbh and larger to 30 percent. | Prescribed fire operations would be conducted under specific conditions which result in low to moderate fire intensity and create a mosaic of burned and unburned areas. Small trees and those encroaching on open areas would be reduced while minimizing the risk to the mature overstory. The conditions under which prescribed fire would be used and implemented would be addressed in a project-specific burn plan. | On April 9, 2012 ignition began for the 201cMIDDLE BLOCK201d portion of Unit B. The test fire was initiated at 15:12 pm. Test fire results were favorable so continued hand-lighting along the unit boundary for a solid black line to reinforce holding operations for the planned aerial ignition to begin the following day. At 19:00 the black-lining operations were completed. On April 10, 2012 the aerial ignition test fire was initiated at 13:00 utilizing a Plastic Sphere Dispenser (PSD) and Helicopter N910BR (Central Air Service). Fire carried readily in the grass and pine seedlings and saplings torched if ignited. Occasional wind gusts briefly exceeded prescription, but sustained winds were well within prescription and fire was meeting resource objectives, so decision was to continue with operations. Aerial ignition on the MIDDLE BLOCK was completed at 17:00. The firing pattern of 201cflanking fire201d did not meet objectives, so the decision was made to 201cstrip head fire201d which did meet resource objectives. On April 21, 2012 ignition began on the final phase of the unit 2013 the 201cWEST BLOCK201d at 12:02 pm by hand lighting to create black-line along the unit boundary. The test fire carried well in the decadent grass but stopped where green-up was occurring. The sage-brush had moderate consumption and isolated torching occurred in the pine seedlings and saplings. Aerial ignition began by PSD began at 15:19. |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 3350.0071 | 2716.3745 |  |  | Fire hazard, Rangeland health, Forest health, Hazardous fuels reduction, Habitat for wildlife | The purpose of the proposed action is to shift the vegetation structure and composition in the Tin Can Hill project area to fall within the historical fire regime. The current condition is an abundance of polesized trees 5 - 9 inches diameter at breast height (dbh) and 9 - 21 inches dbh. The need for action is for a healthy diverse forest that is within the historical fire regime. Timber stands are overstocked and poles and saplings are encroaching on adjacent rangeland, due to departure from historical fire frequency. Improvements to the overall condition class within the project area will likely result in benefits to wildlife habitat through an increase in the diversity and production of herbaceous vegetation . | None |  | None |  |  | 18:49