## model15-treatment-info
Model | Ecoregion | Treatment | LO_notes | Trt_ID | Prj_ID | Plan_Imp | Success | Dates_Confirmed | Init_Date | Comp_Date | Units | Num_Units | Trt_Type_Major | Trt_Type_Sub | Treatment_Type | Treatment_Seeded | Seed_List | Seed_Mix_Name | Seeds_or_Seedlings | Seed_List_Confirmed | Control_Areas | Seed_Application_Rate | Seed_Notes | Objectives | Planned_Implementation | Actual_Implementation | Treatment_Effect_and_Results | Trt_Feature_Type | Feature_Status | How_Feature_Created | Feature_Creation_Date | Total_Acres | BLM_Acres | GIS_Notes | Initiated_By | Trt_Concerns | Trt_Concerns_Desc | Problems_Apply_Trt | Problems_Apply_Trt_Desc | Conditions_At_Trt | Conditions_At_Trt_Desc | Trt_Notes | User_Updated
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 4792 | 1721 | Implemented | None | 2 | 2010-06-05 | 2010-06-05 | Acres | 381.53 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Jackpot | 0 | No seed list | [6 empty] | 1. Burn 30% to 70% of project area in a mosaic pattern. 2. Create 2 to 5 foot flame lengths to achieve mortality on existing juniper seedlings. 3. Burn under cool prescription to stimulate grass and forb production with <50% mortality of shrubs. 4. Achieve 70% to 90% consumption of juniper slash. | Ignition pattern will be determined by wind directions. Strip-head firing pattern will start on downwind edge of unit and proceed into wind. This will minimize smoke and heat impact to fire fighters. If no wind exists firing will start at uphill edge of unit and strip-head firing will proceed in a down-slope direction. | A jackpot burn was completed to target juniper for the benefit sagebrush. | None | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | 2021-03-16 | 381.53 | 381.53 |  | Unknown | Loss of vegetation, Rangeland health | The proposed action is implementation of the Bully Creek LAMP recommendations and decision to control invading juniper in the Bully Creek pasture of the Willow Basin allotment. | None | No documentation. | None | No documentation. |  | 26:36
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted sagebrush | 5057 | 1829 | Implemented | Unknown | 2 | 1991-10-07 | 1991-10-09 | Acres | 1700 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Remove 60% of sagebrush from 1700 acres. Kill 50% of Juniper in the pasture. | Burn area is divided into two units, one unit to be burned each day. Burn out down wind side and flanks using backing fires. Use ATV's to light strip head fires inside the unit. Additional ignition on heavier fuels on unit interior as needed. Concentrate on heavy sage and youth juniper areas. | 10/7/91: Day 1, Burned out lines on eastside of both units and south side of south unit. Predicted winds were for W-NW winds. Burning commenced at 1:30 p.m. and ended at 7:00 p.m. Completed east and south lines. 10/8/91: Day 2, continued to burn out lines on south unit. Winds from east and south east. Burning commenced at 11:30 a.m. on the west lines of the south unit. Lines completed by 1:00 p.m. Proceeded with total ignition of the south unit after lines were in. Burning ended by 5:00 p.m. 10/9/91: Day 3, North unit burn. Completed burning out lines on the west and north side in the morning. Commenced with total burn of unit at 11:30 a.m. Winds out of the east and south east. Burning ended at 3:00 p.m., crews returned to Lakeview. | Remove 60% of sagebrush from 1700 acres. Kill 50% of Juniper in the pasture. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1714.5049 | 1354.7979 |  |  | Provide cover for wildlife, Habitat for sage grouse | The purpose of using prescribed fire in the Button spring Allotment is that it offers a viable, safe, and cost-effective method to reintroduce fire as an ecological process. Fire is a natural component of this area, and its use will result in the smallest disturbance of the rangeland ecosystem. | None |  | None |  |  | 33:27
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted sagebrush | 7376 | 2662 | Implemented | Successful | 2 | 1987-08-13 | 1987-09-08 | Acres | 1890 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | - - - - - EA - - - - - Reduce big sagebrush canopy cover by 10%-15% within one year. Increase herbaceous production by 250-300 1bs/acre within 3 years. The proposed action is to prescribe burn approximately 70-80% of 2,900 acres of public land within the Conover Allotment. | - - - - - EA - - - - - An estimated 70-80% of the project area vegetation is expected to be burned. The percentage of vegetation actually affected is dependent upon the environmental conditions at the time of ignition. The area has been rested from grazing for at least a year, leaving a satisfactory understory for carrying the fire. Primary means of ignition would be a truck-mounted propane burner. - - - - - DR - - - - - The burn will be conducted to minimize damage to perennial grasses and forbs by burning during their dormant period (August or first half of September). Two hundred acres of seeding that is known sage grouse nesting habitat would be excluded from burning. In addition, 420 acres of old growth Wyoming big sagebrush within this pasture will also be excluded from burning. | - - - - - Final Report - - - - - Planned 2700 Acres; Burned 1890 (70%). Approximately 70-80% of the vegetation for the 2700 acre project was expected to be burned. The prescribed burn was successful, burning about 1890 acres or 70% of the project. The burn wagon, a propane tank mounted on a 2-1/2 ton truck was the major tool for ignition for all three tries. | - - - - - Final Report - - - - - The prescribed burn was successful, burning about 1890 acres or 70% of the project. Actual Burning pattern: The pattern was excellent with most of the area being in a patchy design. The southern end did not burn very well. Success: The prescribed burn went pretty well, although the crews had to go down and burn three different times. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1351.89 | 1351.89 |  | BLM and Cooperators | Provide forage for livestock | The purpose of the project is to increase livestock forage by increasing grass production. | None |  | None |  |  | 10:31
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 10715 | 3818 | Implemented | Unknown | 2 | 1998-02-19 | 1998-03-05 | Unknown |  | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | The objective of the burn is to remove the new encroaching juniper and brush piles from the chaining. Juniper control and riparian maintenance | PRESCRIBED FIRE PLAN I. INTRODUCTION Paul Makela of the Snake River Resource Area has requested our help in burning through prescription approximately 50 acres of Juniper Seedlings on the East Jim Sage Chaining Area. The objective of the burn is to remove the new encroaching juniper and brush piles from the chaining. The site will be burned through It has been determined that this would be the preferred method of maintaining the chaining. II. BURN AREA DESCRIPTION LEGAL DESCRIPTION: COUNTY: T. 15 S. R. 26 E. Section 08 Acres 50 Cassia ELEVATION: ASPECT: 6500 Ft. East ADMINISTRATIVE DECISION NUMBER: East Jim Sage Chaining Maintenance EA # ID-020-94-017 TOPOGRAPHY: mostly flat, rolling terrain 5 -15% slope FUEL TYPEIDESCRIPTION: chaining brush piles and juniper seedlings III. OBJECTIVES Removal of brush piles as a result of chaining and slow encroachment of new, young juniper seedlings through burning. IV. BURN PRESCRIPTION ACCEPTABLE PRESCRIPTION RANGE (low) (high) (desired) Temperature 35 55 40 Relative Humidity 40 80 50 1 Hour Fuel Moisture na na na Wind Speed none Wind Direction na na na V. FIRE BEHAVIOR The fire should burn intensely consuming all dry and cured fuels at the site. The brushpiles and dormant seedlings will be ignited with drip torches to promote a hot fire of short duration to consume the fuel as soon as possible an lessen the impact on other perennial vegetation in the chaining. SMOKE MANAGEMENT DISTANCE AND DIRECTION FROM SMOKE SENSITIVE AREAS: The Craters of the Moon National Monument which is the closest Class I Airshed lies approximately 66 miles North of the burn site. Interstate 84 is approximately 22 miles North of the proposed site. NECESSARY TRANSPORT WIND DIRECTION: Any wind direction should be sufficient to transport the smoke away from the Class I Airshed and not risk impacting traffic on Interstate 84; however, the amount of smoke generated from the burn site should be very minimal and of short duration. It is anticipated that this proposal would only have a limited, short duration impact. VISIBILITY HAZARDS (roads, airports, etc. ): Interstate 84 RESIDUAL SMOKE PROBLEMS: There are no anticipated problems. SPECIAL CONSTRAINTS/CONSIDERATIONS: Interstate 84 VII. IGNITION SCHEDULING SEASON: spring Date: 3/1 - 4/30 Time: 1200 - 1600 IGNITION METHOD: Drip Torches. TYPE OF FIRE: individual LENGTH OF IGNITION PHASE: 2 hours VIII. PUBLIC INFORMATION DAY OF BURN CONTACTS: 1. City of Malta 3. Power County 2. City of Rockland 4. Cassia County IX. FIRING & HOLDING FIRING PLAN: The crew will burn-out each existing pile and seedling. The primary ignition should create an aggressive, hot fire of short duration which will consume the majority of the fuel in within one hour. POTENTIAL HOLDING PROBLEMS: There are no holding problems anticipated because the project area has 8 - 12 inches of snow. ESCAPE CONTINGENCY PLAN: In the event the fire should escape all ignition will cease immediately. Personnel on the scene will respond to the escaped fire and begin a coordinated direct suppression effort. The Shoshone Dispatch will be immediately notified. The Burn Boss will coordinate with Dispatch for additional crew needs. Additional forces will be on stand-by in Burley in case of a escaped fire. If the status of the stand-by help changes then Shoshone Dispatch will immediately notify the Burn Boss. SAFETY CONSIDERATIONS/HAZARDS: Crews will wear all their Personal Protective Equipment including fire shelters, nomex shirt, gloves, goggles, and helmets. The Burn Boss and crew members will maintain visual and voice contact with each other. In the event of an accident the Burn Boss will be notified. If the accident is life threatening the Burn Boss will activate the Emergency Evacuation Plan via the Shoshone BLM Dispatch. An on-site briefing will take place the day of any activity. The Burn Boss will conduct a critique when the project is completed. X. PERSONNEL & EQUIPMENT PRESCRIBED FIRE MANAGER: R. Mitchell BURN BOSS: Mark Wiseman/ Dave Smith PERSONNEL: 04 ENGINES: 0 XI. ESTIMATED COST IGNITION HOLDING COSTS Drip Torches, Fuel $150.00 Support Vehicles $120.00 TOTAL COSTS: $270.00 All fire personnel costs will be paid from 2810 funds. Any equipment costs and overtime will be paid from the benefitting activity. | On Thursday 2/19/98, Jim Tharp, Ecologist, and Kurt Pavlat, Rangeland Mgmt. Spec. and I worked from approximately 10am to 4pm burning young junipers that had survived the chaining or had germinated since 1991. Where sufficient grasses, such as bluebunch wheatgrass , western wheatgrass etc. or shrubs had accumulated near the base of the seedlings/saplings, we probably had fairly good success in charring cambium. We worked 2 areas. The northernmost zone, harbored less snow due to its generally southeast exposure. It was also receiving fairly heavy deer use on grass greenup and on some shrubs. The southern unit contained more snow though we did have some success, again where there were accumulated fine fuels. This area had been worked in prior years. We need to continue with several visits per year, working designated patches systematically. It would be helpful to have 8-10 or more people with torches. We also discussed the possibility of some limited prescribed burning (fall?), maybe 5- 10 acres a year. This would be much less labor intensive than burning individual trees in winter, though would result in mortality of some bitterbrush, sagebrush and fourwing. On Thursday March 5, 1998 we resumed with burning junipers and brush piles within the Jim Sage Chaining, using drip torches. With six people, we were able to cover approximately 25-30 acres along the northern portion, east of the leave area "peninsula&&. We had best success with drip torches; Dave Smith (burn boss) attempted using a propane burner, but this proved too time-consuming, as it took too long to ignite the fuels. In general, we felt we made substantial progress today, again owing to the grass accumulated around the trees, and generally clear skies , although clouds moved in later on. If we could continue at this rate, using several personnel, we could conceivably cover all or most of the chaining in a few more trips. |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 4378.84 | 4375.42 |  | BLM | Brush control, Invasion by pinyon-juniper, Pinon-juniper, Hazardous fuels accumulation, Hazardous fuels reduction, Loss of riparian vegetation | The proposed action as described will enhance the long term viability of the Jim Sage Chain and Seed project. Removing the remaining young juniper trees will help ensure that this important deer winter range seeding is not compromised by secondary juniper invasion. Burning the remaining trees individually on a small scale will not cause resource damage and is within the scope of the original impacts assessment for the chaining . By not controlling the remaining junipers now, they will grow rapidly, necessitating more drastic control measures if the integrity of the initial browse seedings to be maintained. | Unknown |  | Unknown |  |  | 2:33
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted sagebrush | 11002 | 3916 | Implemented | None | 1 | 7/00/1983 | 5/00/1984 | Acres | 3500 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Reduce Wyoming Big Sagebrush by 80-100%. Provide seed bed preparation for rangeland drilling; which will increase forage production from 60 AUMs to about 750 AUMs. Enhance wildlife habitat by creating islands and extend the edge effect for wildlife. | The proposed action is to prescribe burn approx. 3500 acres of public land during August and/or September of 1983. |  | It is expected that 80 to 90 percent of the shrubs will be affected in the area that will be burned and seeded, and 10 to 20 percent of the shrubs in the area that will be burned only. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 3101.4342 | 3088.9015 |  | BLM and Cooperators | None | Environmental - Due to fire line construction and seeding by rangeland drills, considerable surface soil disturbances is anticipated. The affects will be temporary since there will be sufficient cover the following year from the seeded species, surviving perennials. and weedy annuals to provide effective soil cover. An archaeological and T & E plant clearances will be obtained prior to any fire line & fence construction and burning - and following burning an additional clearance in the proposed drilled area. The relatively large amounts of smoke created by the fire will occur during periods of excellent smoke dispersal. Dust and smoke will quickly be dispersed into the atmosphere. Detrimental effects on wildlife will be loss of some escape cover and possible nesting areas for birds. | None |  | None |  | this treatment is marked implemented due to photos showing burning. There are no confirmed acreages for this treatment. | 30:17
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted sagebrush and juniper | 11946 | 4266 | Implemented | Unknown | 2 | 1995-10-07 | 1995-10-10 | Acres | 1000 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | The purpose of the proposed action is to reinstate fire as an ecological process within the sagebrush mosaic/juniper woodland vegetation in Fisher Canyon | BURN AREA DESCRIPTION Size: Total Area,\xb7 1,000 Acres | Burn results indicate a true mosaic pattern. Some acres of sage were total removal as areas were broken into units. | Kill 40% of the Wyoming Big Sage. Kill 20-40% of Western Juniper < 10 ft. tall. Create a "fire mosaic&& - a spotty discontinuous burn that results in patches of unburned ground surrounded by burned areas. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 2595.2436 | 2592.6586 |  |  | Threatened Species, Habitat for mule deer, Erosion | The purpose of the proposed action is to reinstate fire as an ecological process within the sagebrush mosaic/juniper woodland vegetation in Fisher Canyon. A fire plan has been developed to address this need. This EA analyzes the impacts of implementing this plan. Decades of fire suppression, coupled with historic overgrazing (1870-1934) have significantly altered the presettlement fire regimes of most High Desert plant communities over the past 100 years (Kauffman and Sapsis 1989). The current abundance of shrubs and western juniper (Juniperus occidentalis) saplings and juveniles within Fisher Canyon represent a local expression of this general trend. | None |  | None |  |  | 31:33
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 12449 | 4453 | Implemented | See Comments | 0 | 2000-09-25 | 2000-09-25 | Acres | 1500 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Achieve mix (mosaic) of 60% grass/forb and 40% shrub/grass/juniper sites across landscape. Reintroduce the natural role of fire in rangeland ecosystems through a landscape style burn within a 8200 acre area. Reduce the expansion of juniper woodlands within the primary burn areas of both units by 70% to 90% and maintain old growth juniper woodlands. Achieve 70% to 90% mortality of juniper (<6' tall) within primary burn areas of both units by creating 2' - 8' flame lengths while keeping mortality of old growth at less than 10%. | Protect fences. Protect juniper old growth stands. Saw large group of ODFW people on south side of Frederick Butte vicinity Lake County line - not sure if there's anything of significance here; but probably shouldn&$t burn too much of this area. Burn under summer like conditions to mimic the natural role of fire in rangeland ecosystems. | N/A. | A 10-15% deviation from objectives is acceptable. | Polygon | Confirmed | Digitized by LTDL data entry personnel using a map of unknown origin | 2010-07-13 | 1294.4572 | 1294.1954 |  | BLM and Cooperators | None |  | None |  | None |  |  | 29:48
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted sagebrush and juniper | 12455 | 4457 | Implemented | None | 1 | 9/00/1986 | 10/00/1986 | Acres | 3900 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Use prescribed burning to reduce sagebrush and juniper and increase forage base. | Treat 50 to 75% of Unit (4000 acres) through Prescribed Burning, except those leave areas identified prior to burning. Construct 7 to 8 miles of fire or control lines in Unit I. Approximately 2 of the 8 miles of handline will be constructed, needing little or no erosion control structures because of the quick re-growth from grasses and forbs (one growth season). The remaining 6 miles of line will be constructed by a D-6 Dozer, the appropriate erosion structures will be provided during construction. The widths of the control line varies from 4' to 8&$ of hand line to a 10&$ to l3&$ width for Dozer line. Dozer line can take up to 2 growth seasons to re-vegetate. Slope and topography can vary from 5% to 50% with flat basins to rolling hills to mountain peaks. The use of existing roads (see attached map) as fire lines will decrease new line construction by 60%, thus reducing soil erosion and loss of vegetation within the control lines. | Summary of items of interest: 3900 acres- Total Perimeter Acres (Project Boundaries) 2700 ac. 67%- Total black acres within perimeter 881 ac 22%- Total designated leave areas acres, all leave areas protected with minor exceptions of less than 1-2 acres. 537 ac .- Slop Overs (areas outside origin 1 perimeter- no adverse resource damage as result, area will be protected). The proposed action was to treat 50 to 75% of Unit I, 67% was blacken which was within this range . All designated leave areas were protected with only 1-2 acre exceptions. 70 to 90% of Big Sagebrush burned was killed. Livestock forage is the most affected by Prescribe fire. All indicators point toward twice the normal grass production with a good chance of 3 to 4 times. | Kill 70 to 90% of the big sagebrush treated. Limit mortality to key forage species to 10%. | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2011-05-04 | 2184.6915 | 2145.6223 | This shapefile represents the portions of the project area that were affected during prescribed burning. The burn was carried out in a mosaic pattern. |  | Provide forage for livestock, Fire hazard, Erosion | Reasons for treating included reducing big sagebrush, increasing perennial grasses, improving livestock distribution throughout the project area, and improving water quality by encouraging livestock use away from the lakeshore. | None |  | None |  | Since there were "leave areas" within the project area to achieve a mosaic effect, the final number of units represents the entire treatment area, not the total burned area. | 33:11
Model 15 | Nothern Basin and Range | Prescribed burn |  | 12997 | 4662 | Implemented | None | 2 | 9/00/1998 | 9/00/1998 | Acres | 800 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | To improve the diversity of vegetation, improve overall health of the local ecosystem, and increase forage for grazing. |  |  |  | Polygon | Confirmed | Not Determined |  | 1480.2524 | 1324.5564 |  |  | None |  | None |  | None |  |  | 57:03
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted sagebrush | 13830 | 4971 | Implemented | See Comments | 2 | 1983-08-12 | 1983-09-13 | Acres | 150 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Reduce big sagebrush ground cover by 80-90% in preparation for seeding. | A three mile, one-blade width cat line would be constructed on the north, east and south boundaries of the burn area. These control lines would be burned out, and widened prior to ignition. An archaeological clearance would be required. Ignition after burnout will begin in the northwest corner of the fire and will proceed along the south line. If the fires spread is retarded by lack of fine fuels or rocky conditions, additional fires will be started in the project interior. Helitorch will be the primary means of ignition, complimented by truck mounted propane burner. | Part of the burn went quite well on the southwest portion of the project in the area below the canal. This area, about 80 acres, burned very rapidly and produced a relatively clean burn. This occurred on august 12. a second attempt to burn the area was made on September 13th, but results were disappointing. All ignition was performed with a propane torch and fusees. | climatic conditions coupled with the failure on the part of the permittee to get a management fence up prior to some grazing, produced rather poor results. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 310.09 | 298.15 |  | Contractor | Provide forage for livestock, Provide forage for wildlife | Burn was proposed to reduce brush competition and to prepare a suitable seedbed for artificial seeding. | None |  | None |  |  | 18:07
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted sagebrush | 14771 | 5332 | Implemented | Unknown | 2 | 1992-10-12 | 1992-10-17 | Acres | 4500 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Remove 50-80% of the sagebrush depending on the area. Limit kill on bitter brush and mountain mahogany. Burn aspen stands hot enough to kill the overstory (protect specific sites.) Kill juniper in the fringe areas. | Prescribed burn of about 4700 acres within a 8000 acre area to reduce shrub component and increase grasses and forbs. Remove 50-80% of the sagebrush depending on the area. Burn aspen stands hot enough to kill the overstory, with protection of specific sites. Kill juniper in the fringe areas. Limit kill on bitterbrush and mount ain mahogany. Existing roads will be bladed prior to the burn; a handline will be built in the unit 4 aspen stand. |  |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 5506.8461 | 4879.3482 |  |  | Habitat for sage grouse, Provide forage for wildlife | Vegetation in the Hillcamp Allotment #0215 has a history of disturbance, whether natural or man-induced. Wildfires have been a major factor influencing the assemblance and succession of communities found in the allotment. Due to suppression of wildfire, these communities are becoming increasingly brush dominated. Sagebrush dominance along with juniper encroachment are leading to less diverse and more monotypic communities&* decreasing the overall vegetative diversity of the area. Prescribed burning will be used as a management tool to obtain the desired species diversity in the allotment and reincorporate the natural process of fire on a fire dependent ecosystem. | None |  | None |  |  | 46:06
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted sagebrush | 15181 | 5482 | Implemented | Unknown | 1 | 00/00/1982 | 1982-10-14 | Acres | 800 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | ...to burn approximately 60-70% of the sagebrush within the shown perimeter. | The burn [2780 ac.] will be conducted over as short a period as possible to minimize costs and take advantage of suitable conditions. Fire lines will utilize existing roads as much as possible to reduce the amount of line construction needed. They may be cleaned with a grader to improve their effectiveness and light grading along several fenced roads would be permissible if necessary to control the fire. Only 60-70% of the areas within the perimeter is expected to burn. The fire is expected to finger throughout the area leaving 30-40% of the existing sagegrass vegetation unaffected. | This past summer the Boise District of the BLM conducted several prescribed burns in the Jarbidge Resource Area. | The success of the burns varied from one area to the next. Success was limited due to prior grazing, low fuel density, high fuel moisture, and a lack of adequate wind during burning operations. | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2012-07-17 | 1922.777 | 1918.1356 |  | BLM and Cooperators | Habitat for wildlife, Provide forage for livestock, Fire hazard | ...to improve livestock forage and wildlife habitat... The primary purpose of the burning is to increase available forage production, produce a greater variety of vegetation and create &&edge effect.&& A secondary purpose is to evaluate the effectiveness of burning as a grass release mechanism in this area and reduce the possibilities of a conflagration by breaking up large continuous areas of sagebrush. The burns are intended to improve the overall visual character of the landscape by modifying the large areas of uniform sagebrush cover to include a greater variety of vegetative form, line, color, and texture. | None |  | None |  |  | 42:54
Model 15 | Nothern Basin and Range | Prescribed burn |  | 18892 | 6859 | Implemented | Unknown | 1 | 1999-09-09 | 1999-09-20 | Acres | 12600 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Burn 20-30% of the project area (Maximum of 60% Coverage) Create a "fire mosaic&& - a spotty discontinuous burn that results in patches of unburned ground surrounded by burned areas. | Desired fire behavior would include a 5 to 12 foot flame length with a rate of spread of 7 to 80 chains per hour, with and desired rate of 30 to 40 chains per hour. Rate of spread is less critical and some higher rates are acceptable as it is controlled by firing patterns. The maximum rate of perimeter increase based on fuel models outside but adjacent to the burn unit, will no exceed available holding force line production. |  | Remove 30 to 60% of the sagebrush within project area. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 17784.4022 | 17687.8178 |  |  | None |  | None |  | None |  | it appears as if units 2 and 3 were combined. | 52:19
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 21939 | 8001 | Implemented | None | 2 | 00/00/1999 | 00/00/2001 | Acres | 325 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Pile Burn | 0 | [7 empty] | In 1999, 2000, and 2001 the area received a treatment for western juniper to reduce fuels. |  |  |  | Polygon | Confirmed | Digitized by LTDL data entry personnel using a map of unknown origin | 2010-06-24 | 310.7325 | 310.7325 |  |  | None |  | None |  | None |  | This treatment was listed as completing 325 ac, however, it does not indicate what the treatment was. | 43:35
Model 15 | Nothern Basin and Range | Prescribed burn | Prep for seeding | 22164 | 8084 | Implemented | None | 1 | 1990-09-06 | 1991-09-13 | Acres | 3450 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | The purpose of this project is to burn and seed 3,530 acres to crested wheatgrass, to restore suspended AUMs, and develop methods and procedures for prescribed burns in the Lakeview District, in order to effectively and safely move from fire control to fire management. At the present time, 5000 AUMs are needed to restore all AUMs of suspended non-use in the Viewpoint Allotment. This proposed burn and seed project would provide approximately 774 AUMs of additional livestock forage. | The proposal is to complete a prescribed burn and seeding of about 3,530 acres drilling it to crested wheatgrass. |  |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 3651.2867 | 3649.4715 |  |  | Habitat for antelope, Habitat for Desert Valley Kangaroo Mouse | Provide sufficient forage capable of sustaining large numbers of cattle during gathering and shipping operations. Reduce the heavy truck traffic through the seeding complex by relocating the main shipping facilities closer to the Wagon tire Co. road. Three of the existing pastures within the eight pasture seeding complex receives continuous intermittent critical growing season use during normal gathering and shipping operations. This type of annual use can affect the overall plant vigor of the seeding. This new forage base would help in alleviating the extended growing season use of Poverty seeding during the shipping operations. | None |  | None |  |  | 9:14
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted sagebrush | 23480 | 8579 | Implemented | None | 2 | 1990-08-02 | 1990-08-02 | Acres | 180 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | A maintenance burn of the old Berger Burn Reseeding #1137. Burn at least 70% of sagebrush on treatment site. |  | Ignition was started at 1230. Actual RH was 24% according to Berger Raws station. Good burn, no leave areas, easy to accomplish, killed probably 95% of Brush. Burned clean. |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 204.1062 | 204.0805 |  |  | None | A maintenance burn of the old Berger Burn Reseeding #1137. | None |  | None | RH: 70%? Temp: 77 Wind speed: 8-10 G15 NW |  | 27:31
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 26261 | 9672 | Implemented | Unknown | 1 | 1990-09-14 | 1990-09-14 | Acres | 2100 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Reduce juniper densities by 80% over 50% of the project area thus improving the burned area to good ecological condition | The proposed action is to prescribed burn approximately 50% of the two identified units, #1A and #2 in August or early September of 1987. Unit #1B is proposed for prescribed burning within the next five years when proper conditions exist. The impacts of a prescribed burn in unit #1B will be analyzed in this document along with the impacts to units #1A and #2. See maps #2 & #3 for the location and acreage of each unit identified for burning. | From GIS: 2 burn areas; 436 state acres; was P# 6948; 2100ac treated. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 3317.07 | 2992.17 |  | Unknown | Invasion by non-native annuals, Habitat quality,Rangeland health | The primary purpose of this project is to control western juniper invasion on loamy sites. The project would result in increased herbaceous production initially, but a more significant long-term benefit would be the improvement of vegetative diversity. Overall ecological condition is currently rated as fair and the burn is expected to improve this condition to a rating of good. | None |  | None |  | Cost is based on planning for one day of burning. Cost for two days was planned to be $6,836.08. Implementation was confirmed in GIS. | 45:47
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 29595 | 10940 | Implemented | Unknown | 1 | 00/00/1997 | 00/00/1997 | None |  | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Prescribed Fire Objectives: 1. Removal of 40-70 % of total vegetative cover. 2. Ensure natural ecological conditions are perpetuated or reestablished in special management areas. Tolerable Deviation of Objectives: 1. Percentage of removal may vary by plus or minus 15 %. | V. PRE-BURN PREPARATIONS A. The South Steens Mountain prescribed burn has been approved within the South Steens Allotment Management Plan and Environmental Assessment. B. Control Line construction will be necessary, but minimal. All control lines will be black line. Specific boundaries on the burn units will require black lining in advance of the actual ignition of the prescribed fire. The majority of the boundaries on the burn units will be roads, streams, aspen stands, mature juniper stands, ridgelines, other natural fuel break and fence lines. These natural and other barriers will be adequate to hold the fire from the buffer areas. C. Fuel monitoring will be conducted periodically prior to the burn. D. Spot weather forecasts will be based on data collected on site prior to any burning and will be obtained before any ignition on the date of burning and relayed to the prescribed burn crew. E. Prescribed burn crew members will be briefed on the Burn Plan, Safety Plan, JHA's and burn unit/firing pattern maps will be given to all personnel at the pre-burn briefing. F. On the day of the burn and prior to the ignition, the Dispatcher will contact all persons and organizations listed on the Prescribed Burn Contact List on Page 15 of this burn plan. G. Pre-burn and Post-burn monitoring will be accomplished by personnel of the Eastern Oregon Agricultural Research Center (EOARC). H. Contract prescribed burn vendors will be contacted to verify availability and to give an up-dated tentative schedule. Catlow Rim Unit No black lining will be necessary due to natural fuel breaks and the lack of fuel continuity within the contingency area of the unit. 1- Aerial ignition (PSD machine) will ignite drainage bottoms of the unit with slope and wind driven strip head fires. In addition, three other areas that are critical for Big Horn Sheep were identified during a prior aerial recon of the unit. Jim Buchanan, prescribed burn resource advisor, will be on board the PSD helicopter during ignition of the unit and will locate and identify these additional areas to the aerial ignition specialist. Add and adjust strips, widths and direction as necessary. |  |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 3078.1412 | 2628.5741 |  |  | Fire hazard, Watershed degredation, Habitat for desert bighorn sheep | Within this 16,000 acres (approximate) located on the South Steens Allotment fire has been removed as a natural ecosystem function. Due to the mature and decadent vegetative stands in this area, vegetative regeneration is necessary with stimulation occurring through fire. Areas dominated by juniper on deep soil sites have priority for treatment by fire. The second priority would be big sagebrush areas containing 5 percent or more canopy cover of young juniper trees (determined by height and age class). In both of these communities plant species diversity is being lost. The juniper dominated sites have only a limited number of years when fire would be effective in reestablishing species and structural diversity without long recovery periods. Prescribed fire will be restricted from mature juniper stands due to the lack of fine fuels, severity of burn required to carry through crowns, and long recovery time following a burn. Resource Objectives and Desired Effects: 1. Maintain watershed integrity to enhance hydrologic function. 2. Achieve a mosaic of forage production and cover needs for wildlife and livestock. 3. Document the effects of fall burning on native vegetation. 4. Enhance the richness of plant and animal species. 5. Manage for natural succession by using fire in a role that it plays in the natural ecological process on the Steens Mountain. Treatment will result in a desired mosaic effect. 6. Fire Hazard reduction. | None |  | None |  |  | 9:05
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 30494 | 11248 | Implemented | Unknown | 1 | 9/00/2002 | 9/00/2002 | Acres | 6093 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Pile Burn | 0 | [7 empty] | The Proposed Action is to burn approximately 35 percent (3600 acres) of the Stonehouse Allotment. The burns would be in mountain sagebrush-bunchgrass communities, aspen, remnant aspen, and wet meadow plant communities. These burns would create a landscape mosaic within the treatment area of 40-55 percent of the mountain sagebrush-bunchgrass plant communities actually being burned and 45-60 percent of the mountain sagebrush-bunchgrass plant communities actually being burned and 45-60 percent unburned. Forty percent or less of the wet meadow plant communities will actually be burned. The aspen and remnant aspen plant communities identified for the fire reintroduction (130 acres) would require juniper cutting to allow these communities to burn. These stands would be expected to have 90 to 100 percent burn and would require temporary net protective fences (8 feet in height) around them. | The proposed action is the reintroduction of fire through prescribed burning on approximately 35 percent of the allotment 36000 acres, of which 500 acres is within the Wilderness Study Areas. Most of the area proposed for reintroduction of fire is mountain big sagebrush-bunchgrass communities in an early transition state to juniper woodlands. | GIS is implementation data | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 2686.778 | 2675.652 | This shapefile was provided by the field office and matched the paper maps provided by the project information. | BLM and Cooperators | Loss of vegetation | The Stonehouse Burn is located on the East side of the Steens Mt. The project objectives are to reintroduce fire with juniper cuts back into a fire-dependent ecosystem, which is well beyond the historical fire frequency for the associated plant species. Due to past grazing practice and fire suppression activities, fire has not been allowed to function as would be expected. This has resulted in many of the scrub species and grasses, which would normally carry fire to be reduced or eliminated by competition with encroaching juniper. | None |  | None |  | This project included various plans and documents. No RIPS Report or other detailed report was included. Due to various email documents and cost summary reports the project was considered to be implemented. | 3:35
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted sagebrush | 31353 | 11558 | Implemented | None | 1 | 1989-09-04 | 1989-09-04 | Acres | 550 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | The purpose of the proposed action is to increase the usable productivity and improve the condition of the areas identified by reducing the shrub component of the vegetative community. The need for these improvements have been identified in the Twin Falls MFP RM 2.1 and 2.4 and the Cassia RMP. The plan objectives are: 1 . Obtain at least 70% kill on sagebrush plants within the perimeter of the burns . 2 . Increase production of forage species within three (3) growing seasons by the amount shown on Table 1 (Net Increase). | The prescription for the burn plan would be as described in Table 4 . These conditions are optimum and insignificant deviations can be made from these windows if opportunities present themselves. If these conditions are not all met, but test firing indicates that a burn has a high probability of meeting objective #1 the burn boss may proceed. Safety of crews will be the prime factor in determining if the burn should proceed when conditions are at the high extreme. Fire lines would be constructed using a motor patrol or cat by area personnel, fire crews , or operations staff . Debris would be pushed to the outside of the breaks to reduce mop-up time and costs . Black lines would be used to widen grader or cat lines. The lines around leave areas would be widened first to ensure as much protection for these areas as possible. In the event of a breakout or multiple breakouts the following priorities would be followed in at tacking: 1. crew safety, 2. protection of private property and public structures, 3 . protection of designated leave areas . 4 . protection of other adjacent public lands . Ignition method and firing technique would be described by the burn boss and carried out by the firing crew . The burn boss would be responsible for: 1. Accessing the AFFIRMS program in order to verify that the prescription criteria and conditions would be acceptable . 2 . Obtain 3-5 day favorable weather forecast with no frontal pressure anticipated near the burn area . 3 . Install, read, and record daily the fuel moisture sticks for 5 days prior to burning . 4 . Obtain spot weather forecasts as conditions near prescription . No burning would be undertaken if weather conditions are such that smoke dispersion is poor . Burning permits will be issued prior to burning. Idaho Department of Fish and Game comments on each burn area will be considered before t he fire lines will be constructed . Archeological clearances will be obtained prior to any fire line construction. |  |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 540.2232 | 540.1633 |  | BLM | Endangered Species, Habitat for sage grouse, Habitat for wildlife, Impact on Cultural Resources, Provide forage for livestock, Sensitive Species, Threatened Species | The purpose of the proposed action is to increase the usable productivity and improve the condition of the areas identified by reducing the shrub component of the vegetative community. The need for these improvements have been identified in the Twin Falls MFP RM 2.1 and 2.4 and the Cassia RMP. | None |  | None |  |  | 23:05
Model 15 | Nothern Basin and Range | Prescribed burn | Prep for seeding | 31355 | 11559 | Implemented | Unknown | 1 | 00/00/1992 | 00/00/1992 | Acres | 1100 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Maintain a crested wheatgrass seeding. Obtain at least 70% kill on sagebrush plants within the perimeter of the burns. Once this objective is reached, no "cleaning up" of the unburned area would be done Increase productions of forage species within three growing seasons | Prescriptions: The prescription for the burn plan would be as described in Table 1. These conditions are optimum and insignificant deviations can be made from these windows if opportunities present themselves . If these conditions are not all met , but test firing indicates that a burn has a high probability of meeting the above objectives, the burn boss may proceed. Safety of crews will be the prime factor in determining if the burn should proceed when conditions are at the high extreme. Some fire lines would be constructed using a motor patrol or cat by area personnel, rancher help, fire crews, or operations staff. Debris would be pushed to the outside of the breaks to reduce mop-up time and costs. This debris will be bladed back over the line after the burns are completed, if funds and manpower are available. Black lines would be used to widen grader or cat lines. The lines around leave areas would be widened first to ensure as much protection for these areas as possible. In the event of a breakout, or multiple breakouts , the following priorities would be followed in attacking: a. Crew safety. b. Protection of private property and public structures. c. Protection of designated leave areas. d. Protection of other adjacent public lands. Ignition methods and firing techniques will be described by the burn boss and carried out by the firing crew. The burn boss would be responsible for the following constraints and procedures: Constraints a. All burns will be checked through the first two burning periods. b. Prescribed burns adjacent to heavy-use highways and interstates will only be ignited under the following condition: Present and predicted winds will carry the smoke away from the road or else Department of Highway, personnel or other individuals, will be on site prior to ignition to stop travel if needed. c. On fireline segments where there is a high risk of an escaped fire, there must be a complete mineral soil , wet, black, or foam line. d. No burns will be ignited during any present or proposed "Red Flag && warnings or when lightning activity is predicted above Class 3. Procedures a. Weather will be obtained three days prior to the burn either from the nearest RAWS station or the Boise Weather bureau. This will be part of the burn plan package. b. Boise fire weather forecast on the day of the burn will be viewed prior to burning for &&Red Flag&& watch and predicted conditions. c. A spot weather forecast will be requested on the day of the burn. d. Each prescription will include a back-up plan and equipment requirement. e. The Dispatch pre-notification will include, under landmarks, a clear local geographic landmark (i.e. lake, mountain, town, canyon, etc.) See attached Control Burn Notification List Plan. f. A strategy and safety briefing will be held before burning. No burning would be undertaken if weather conditions are such that smoke dispersion is poor. Burning permits will be issued prior to burning. Idaho Department of Fish and Game comments will be considered on each burn area before fire lines are be constructed. Archeological clearances will be obtained prior to any fire line construction. A pre-burn conference will be held with the Area Manager, Wildlife Biologist, and Fire Management Officer to determine the site-specific firing techniques and leave areas for each burn. An area resource advisor will be on-site during the prescribed burning, when possible. | A second attempt at burning Mud Lake Seeding. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1045.37 | 1045.37 |  | Unknown | Aesthetics, Endangered Species, Erosion, Habitat for wildlife, Impact on Cultural Resources, Livestock in treated area, Provide forage for livestock, Provide forage for wildlife, Sensitive Species, Threatened Species, Competition for resources, Brush control, Sagebrush | The purpose of the proposed action is to increase the usable productivity and improve the livestock forage condition of the areas identified by reducing the shrub component of the vegetative community. At the same time, it is the purpose to not adversely impact wildlife needs. The proposed action is to eliminate sagebrush competition | [5 empty] | 24:35
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted sagebrush | 34480 | 12813 | Implemented | None | 1 | 00/00/1985 | 00/00/1985 | Acres | 1000 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Reduce big sagebrush densities from 16,000 plants per acre to 2,000 plants per acre over 80% of the treatment area. | After black lining along the fences or roads, ignition would start on the east side and proceed westward. The headfires would be allowed to run into the barriers around the project. The primary means of ignition would be a truck mounted propane burner. |  |  | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2012-08-24 | 1342.8351 | 1333.3986 |  |  | Invasion by non-native annuals, Provide forage for livestock | The purpose of this project is to reduce big sagebrush competition thus increasing herbaceous production. | None |  | None |  | Acres given are from the EA, and are only an estimate of what was burned. | 55:31
Model 15 | Nothern Basin and Range | Prescribed burn | Brush control | 35047 | 13011 | Implemented | Successful | 2 | 1984-08-09 | 1984-08-09 | Acres | 1263 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | Confirmed seed list | [6 empty] | Reduce the mixed shrub cover by 80-90% on an estimated 30% of the project area, by prescribed burning. Increase livestock forage by 175-250 lbs/acre within three years | Ignition will begin in the southeast corner of the project and northward along the east boundary. Ignition will proceed counterclockwise around the entire perimeter back to the southeast corner. | The burning was carried on Thursday August 9. The fire crews and area personnel arrived at the burn area about 9:30 am. Suppression equipment included two tankers, two slip-ons, and two propane-mounted trucks. The two burn trucks were ignited on the south perimeter where a road split the project in half. The burn on the north perimeter was ignited when the southern perimeter was secured. On the southwest the fire did cross the cat line, but two tanker crews were put to suppress the fire before the fire could burn any substantial acreage. Fusees were used on smaller areas in the project. The winds were light and erratic, but mostly eastern in direction. | The burn went very well and as planned. It was accomplished in a single day. The actual burning pattern was fingering and patchy inside the perimeter. The area to be treated was successfully burned. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1285.8 | 1022.98 |  | BLM | Loss of vegetation, Provide forage for livestock, Rangeland health | This project was proposed for the purpose of improving rangeland condition and increasing livestock forage production. Competition from mixed desert shrubs will be reduced along with the establishment of perennial grasses and forbs by seeding. | Unknown |  | Other (See Trt Notes) | Winds were light and erratic but mostly eastern in direction. | Winds were light and erratic but mostly eastern in direction. | 26:24
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted sagebrush | 35345 | 13117 | Implemented | None | 2 | 1984-09-13 | 1984-09-15 | Acres | 4369 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | 1. Achieve a 60-100% kill of sagebrush in the burned area. 2. Kill less than 10% of bunchgrass. | See burn plan. |  | The first objective is presumed to be met. A 96% burn of the entire burn area was achieved. Due to the high susceptibility of sagebrush to fire is assumed the percent kill of sagebrush will be approximately the same as the burned area percentage. Post burn studies to be read in the summer of 85 will give the final results of percent kill on sagebrush and also on the bunchgrasses for the second objective. It appears that all resource objectives have been met. All in all the burn was a good one. I think we may need to design better our wildlife save areas in consideration to the overall area we are affecting. This corresponds to local population needs and also migratory populations that may use the area. If a resource person works with the burn boss on fire effects I think both could come up with a good idea of what is needed to save and how to accomplish it. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 2810.5649 | 2807.6031 |  | BLM | Provide forage for wildlife, Provide forage for livestock | 1. Increase quality and species diversity of forage plants. 2. Reduce the overs tory component of sagebrush to allow access of wildlife and livestock to forage plants. 3. Increase ecological range condition from early to middle. 4. Increase habitat diversity and edge effect by opening up homogeneous stands of sagebrush. | None |  | None |  |  | 47:42
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 52046 | 20821 | Implemented | See Comments | 2 | 2008-09-06 | 2008-09-10 | Acres | 3943 | Prescribed Burn | Prescribed Burn | Prescribed Burn | 0 | No seed list | [6 empty] | Control seral juniper on 60% of the area within the burn perimeter as measured by the percentage of canopy burned in pre and post fire plots. --Maintain watershed function, stability, and reduce accelerated erosion by maintaining and increasing shrub and diverse herbaceous plant communities --Restore suitability of mountain big sagebrush/bitterbrush-bunchgrass communities as sage grouse nesting habitat. --Improve wildlife habitat for sage grouse, elk, deer, antelope, migratory birds, small mammals, amphibians, reptiles by creating and maintaining vegetative mosaics. | --Ignition is planned for late summer through fall, with a potential window occurring from August through October. The blackline ignition may occur as a separate operation, with a minimum of resources, if a window occurs in late fall or early spring. Ignition of the main unit would follow when the typical fall window is available. --Blackline divided into four sections, each expected to require 1 day to complete for a total of 4 days. Aerial ignition of interior is expected to require 2 days with a Heli torch. Use of a PSD device in marginal conditions would likely take longer. | Prescribed burn began September 6, was completed on September 9 2008. Total acreage burned was 3943 acres. As described, fire activity was most consistent in the shrub fuel model, where large pockets of Sage/Ceanothus were consumed. Over the remaining portions of the unit there were minimal surface fuels under juniper stands. In these areas fire consumption was low. | Observations indicate that all of the objectives either have been met or are trending upwards towards being met. Fire has been reintroduced, resulting in the opening of the juniper canopy allowing for a more diverse ecosystem. Within the monitoring plots, trees per acre have been reduced from 244 to 43 per acre. Brush stands have been opened up patches reducing cover up to half of pre-burn conditions in monitored locations. Forb production has been maintained and even increased from prior burn conditions. Perennial grasses have doubled in plants per square meter. Regarding perennial grass recovery, observations indicate an increase in numbers but observations from year 3 shows that many of the plants were seedlings and not yet developing seed heads or were grazed down to 1.5 inches or less. It should be noted that prior to year 3, no livestock grazing occurred in the treated pastures allowing for good recovery and seed head production due to a 2 season rest post treatment. After 2 seasons of rest, livestock was allowed to resume on the allotment. Year 3 observations find very few plants with seed heads persisting occurred unless they were up in rocks or areas that livestock or wildlife were unable to get to. Substantial grazing occurred in those mosaic areas that were treated and were particularly targeted by livestock. The treatment appears to be beneficial to the project area but the continued success of the treatment may depend on a review of livestock management in the allotment. During the implementation of the RX burn all of the plots received a portion of the treatment. However the entire unit was not treated as the prescription called for a mosaic pattern. All 4 Data Plots were treated with prescribed fire but they are not representative of the whole unit due to the mosaic pattern of the treatment. This was easily achieved since much of the Juniper landscape was not conducive to fire treatment without some prior pretreatment. No juniper pretreatments were attempted when this project was carried out due to the WSA status that much of the project area encompassed. In 2010 the WSA status was dropped and some of the project area was declared wilderness and the northern potion of the project area was simply released from WSA status. Tree Data: Pre-treatment: 244 trees per acre average 3 Years Post Treatment: 43 trees per acre average Tree Species: (mountain mahogany, western juniper) Line Intercept: Pre-treatment: 35% Brush Cover 3 Years Post Treatment: 15% Brush Cover Shrub Species: (bitterbrush, big sagebrush, ceanothus, snowberry) Density: Pre-Treatment: 3.6 Perennial Grasses per Sq/M Immediately Post Treatment: 2.6 Perennial Grasses per Sq/M 1 Year Post Treatment: 1.5 Perennial Grasses per Sq/M 2 Years Post Treatment: 6.8 Perennial Grasses per Sq/M 3 Years Post Treatment: 7.6 Perennial Grasses per Sq/M Perennial Grass Species: (Thurber\u2019s needlegrass, crested wheatgrass, mountain brome, squirrel tail, Idaho fescue, bulbous bluegrass, sandberg bluegrass) Pre-Treatment: 90 Forbs per Sq/M Immediately Post Treatment: 38 Forbs per Sq/M 1 Year Post Treatment: 10 Forbs per Sq/M 2 Years Post Treatment: 142 Forbs per Sq/M 3 Years Post Treatment: 71 Forbs per Sq/M Forb Species: (western yarrow, pale agoseris, wild onion, arrowleaf balsamroot, Oregon-grape, grand collomia, tiny trumpet, tapertip hawksbeard, larkspur, geranium, nineleaf biscuitroot, lupine, prairie-dandelion, yampah, phacelia, phlox, knotweed, goatsbeard, violet, mule-ears) See the attached Monitoring Data FFI excel reports for more monitoring data. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | 2020-01-02 | 3925.6 | 3810.99 |  | BLM | Erosion, Forage for wildlife, Forage quality, Habitat for sage grouse, Habitat for wildlife, Habitat productivity, Habitat quality, Invasion by pinyon-juniper, Rangeland health, Sagebrush, Watershed health, Pinon-juniper | Improve herbaceous components within mountain big sagebrush/bitterbrush-bunchgrass communities and low sagebrush/bunchgrass communities by controlling juniper with prescribed fire on approximately 60% of the project area. | Unknown | Unknown | Unknown | Unknown |  | 38:00
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted sagebrush and juniper | 56213 | 21594 | Implemented | See Comments | 2 | 9/00/2009 | 9/00/2009 | Acres | 16367 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | In areas targeted for a broadcast burn, the objective is to burn 40 to 60 percent of the mountain big sagebrush-bunchgrass communities in early to mid-juniper woodland transition and 90 percent of mountain big sagebrush plant communities in mid to late transition. | 2008 and 2009 Rx Burning. Broadcast Burning Broadcast burning is the controlled application of fire to wildland fuels within a predetermined area during specific environmental conditions in order to attain resource management and fuels reduction objectives. Broadcast burning would be another form of prescribed fire applied under the proposed action. Portions of shrub land communities that are in middle to late juniper woodland transitional stages would require mechanical pretreatment to create ladder fuels that allow fire to spread. Individual trees would be periodically felled against standing trees and allowed to cure; creating a ladder allowing ground fire to move into canopies of standing uncut trees. Sites not supporting large trees typical of communities in earlier stages of juniper woodland development would not require mechanical treatment prior to application of prescribed fire. Other pretreatment activities that may occur within or near broadcast burn units include wet lining, 13 blacklining, jackpot burning, and handline construction around interior leave islands and fire -sensitive assets such as range improvements or cultural resources or to decrease heat from the broadcast burn in some communities. Holding operations near property boundaries may be accomplished with pretreatment using small amounts of jackpot burning, juniper cutting, and/or piling and burning. Scheduling of burning during the 7 to 15-year implementation period is dependent upon resource objectives, weather, fuel conditions, project funding, and arrangements with grazing permittees, and other private property owners. These factors, especially weather, make it difficult to accurately project the number of acres burned in a given year. As described in PDE #8, broadcast burning operations require one growing season of rest from livestock grazing prior to treatment and at least two growing seasons of rest following treatment. The duration of the rest period would be determined by the Field Manager based on rangeland monitoring by a BLM ID Team of plant community response. | Data obtained from this treatment's GIS Attribute Table - Broadcast Burn Completed | Prior to the Unit 2 prescribed burn, photo monitoring and plant species inventories were collected by the BLM at permanent monitoring sites in the uplands and along riparian areas within the Project Area. Project objectives were met for 2009 due to close coordination and cooperation with Burns BLM Resource Area Staff, Burns Interagency Fire Zone, Harney County Soil and Water Conservation District (SWCD), Harney County Watershed Council, USGS, ARS and five grazing permittees/private land owners. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 16367.36 | 7026.22 |  | Unknown | Brush control, Competition for resources, Encroaching vegetation, Habitat productivity, Habitat quality, Invasion by pinyon-juniper, Invasive species, Loss of desirable species, Rangeland health, Pinon-juniper, Vegetal cover, Fire hazard, Hazardous fuels reduction, Hazardous fuels accumulation | Communities in early to mid-juniper woodland transition. |  |  |  |  | Unit 2 - Burn Boundary Line Preparation/Range Improvement Protection - $32,400.00 | 26:54
Model 15 | Nothern Basin and Range | Prescribed burn |  | 56252 | 21599 | Implemented | See Comments | 2 | 9/00/2010 | 9/00/2010 | Acres | 15260 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Fuels Reduction | Portions of shrub land communities that are in middle to late juniper woodland transitional stages would require mechanical pretreatment to create ladder fuels that allow fire to spread. Individual trees would be periodically felled against standing trees and allowed to cure; creating a ladder allowing ground fire to move into canopies of standing uncut trees. Sites not supporting large trees typical of communities in earlier stages of juniper woodland development would not require mechanical treatment prior to application of prescribed fire. Other pretreatment activities that may occur within or near broadcast burn units include wetlining, 13 blacklining, jackpot burning, and handline construction around interior leave islands and fire -sensitive assets such as range improvements or cultural resources or to decrease heat from the broadcast burn in some communities. Holding operations near property boundaries may be accomplished with pretreatment using small amounts of jackpot burning, juniper cutting, and/or piling and burning. Scheduling of burning during the 7 to 15-year implementation period is dependent upon resource objectives, weather, fuel conditions, project funding, and arrangements with grazing permittees, and other private property owners. These factors, especially weather, make it difficult to accurately project the number of acres burned in a given year. As described in PDE #8, broadcast burning operations require one growing season of rest from livestock grazing prior to treatment and at least two growing seasons of rest following treatment. The duration of the rest period would be determined by the Field Manager based on rangeland monitoring by a BLM ID Team of plant community response. | Data obtained from this treatment's GIS Attribute Table - Broadcast burning completed. | Overall, project objectives were met for 2010 due to close coordination and cooperation with Burns BLM Resource Area Staff, Burns lnteragency Fire Zone, Harney County Soil and Water Conservation District (SWCD), Harney County Watershed Council, USGS, ARS and four grazing permittees/private land owners. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 15260.4 | 11715.02 |  | BLM | Brush control, Hazardous fuels accumulation, Hazardous fuels reduction, Invasion by pinyon-juniper, Encroaching vegetation | Broadcast burning is the controlled application of fire to wildland fuels within a predetermined area during specific environmental conditions in order to attain resource management and fuels reduction objectives. Broadcast burning would be another form of prescribed fire applied under the proposed action. |  |  |  |  | Burn Boundary LinePreparation/Range Improvement Protection - $51,284.00 | 24:02
Model 15 | Nothern Basin and Range | Prescribed burn |  | 56325 | 21617 | Implemented | Unknown | 2 | 9/00/2011 | 10/00/2011 | Acres | 7684 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Fuels Reduction | Broadcast burning is the controlled application of fire to wildland fuels within a predetermined area during specific environmental conditions in order to attain resource management and fuels reduction objectives. Broadcast burning would be another form of prescribed fire applied under the proposed action. Portions of shrub land communities that are in middle to late juniper woodland transitional stages would require mechanical pretreatment to create ladder fuels that allow fire to spread. Individual trees would be periodically felled against standing trees and allowed to cure; creating a ladder allowing ground fire to move into canopies of standing uncut trees. Sites not supporting large trees typical of communities in earlier stages of juniper woodland development would not require mechanical treatment prior to application of prescribed fire. Other pretreatment activities that may occur within or near broadcast burn units include wetlining, 13 blacklining, jackpot burning, and handline construction around interior leave islands and fire -sensitive assets such as range improvements or cultural resources or to decrease heat from the broadcast burn in some communities. Holding operations near property boundaries may be accomplished with pretreatment using small amounts of jackpot burning, juniper cutting, and/or piling and burning. Scheduling of burning during the 7 to 15-year implementation period is dependent upon resource objectives, weather, fuel conditions, project funding, and arrangements with grazing permittees, and other private property owners. These factors, especially weather, make it difficult to accurately project the number of acres burned in a given year. As described in PDE #8, broadcast burning operations require one growing season of rest from livestock grazing prior to treatment and at least two growing seasons of rest following treatment. The duration of the rest period would be determined by the Field Manager based on rangeland monitoring by a BLM ID Team of plant community response. | Data obtained from this treatment's GIS Attribute Table - Broadcast burning completed. | unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 7684.04 | 5737.95 |  | BLM | Encroaching vegetation, Fire hazard, Hazardous fuels accumulation, Hazardous fuels reduction, Invasion by pinyon-juniper, Pinon-juniper | Fuels Reduction | [5 empty] | 10:27
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 56484 | 21632 | Implemented | See Comments | 2 | 2016-03-01 | 2016-03-03 | Acres | 400 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Jackpot | 0 | [7 empty] | The broadcast burn will be implemented under conditions designed to result in 70-90% of available jackpot fuels ignited. | 2016-Berry Gulch Unit (approx. 1,400 acres): This prescribed fire will use one helicopter. 1. Timberland Helicopter Services will provide the helitorch, mix truck, aircraft, pilot, mechanic and fuel. \u2022 Day One: The helicopter will arrive in Boise the day before the ignition and marry up with the helicopter manager, get a pre-use inspection, load frequencies and obtain a briefing for the next day\u2019s work. \u2022 Day Two: The helicopter will fly to Pole Creek, land, get a briefing from the helibase and burn boss. Required checklists including \u201cGo/No-go\u201d will be completed and checks on the equipment will be made. The helitorch will light the unit. The aircraft will return to Boise at the end of the day. \u2022 Day Three: The helicopter will continue to light the unit as needed. At the end of the day the aircraft can either go to Boise for RON or leave for their home base in Ashland, OR. | Jackpot burn 3/2/2016 Began ignitions at 1049 in the middle of the unit. Fine Dead Fuel Moisture was at 8, Burning went well worked to the south and west. 250 acres completed. Stopped burning at 1700 3//3/2016 Began ignitions at 1030, worked to the east and south in the major drainage, 150 Acres completed. Left the unit at 1640.' 3/2/2013 \u2013 Arrived on the unit at 1030 to begin jackpot burning the Pole Creek Unit. Soils were very moist with pockets of snow here and there. We lit a test fire on some large juniper in the middle of the unit. Test fire showed that juniper would ignite very easily with consumption of the 1hr and 10hr fuels but limited consumption of the 100hr and 1000hr fuels. We began lighting from the north to south across the unit while working our way back to the west. Ignitions of the jackpots of fuels was not difficult but covering the ground and did take considerably more time than I had anticipated. We burned until 1630-1700 that day and returned back to Boise with about 250 acres completed for the day. We arrived in Boise at 2100. 3/3/2016- We arrived back at the unit at 1000 the next day and picked up burning from where had started the previous day. This time we worked two big draws towards the east, again working north to south across the unit. Several times we had to stop burning and back track to light in a manner that didn\u2019t smoke everyone out. Progress was slow due to the amount of slash that we had to walk through and around. Also waiting for other burners to stay in lightning pattern slowed progress down. The further we got away from vehicles took more time to refuel leading to more lost time. We ended the day with a total of 150 acres completed for the day and returned back to Boise at 2100. 3/7/2016- Weather had moved in to southwest Idaho on 3/4/2016 bringing wide spread rain and snow to the area. I had two people return back to Pole Creek to check the unit but they were only able to get within 15 miles of the unit and had to turn around due to impassable roads. As expected they did not see any obvious signs of fire spread/smoke coming from the unit. 3/14/2016- The weather did turn better for the week but the day that I sent down employees again to check the unit they were unable to access the unit due to impassable roads. No signs of smoke coming from the unit. 3/29/2016- Employees were finally able to access another unit adjacent to the burn unit on this day but it was snowing. They did not see any signs of fire activity coming from the unit. 4/1/2016- I was able to access the unit by UTV on this day which turned out to be very nice with dry soils and warm weather. I walked the entire perimeter of the unit and did not see any smoldering or smoke coming from the unit. I saw no signs of previous fire spread since the two days that we had burned. I called the unit out on this day. | Unable to complete all acres due to Sage-grouse timing restrictions. Excess funds were moved to SODA Archeological clearances for SODA fuel breaks. 4,091 Acres of clearances completed. Young Trees \tPre- 135.2/acre \tPost- 46.1/acre Mature Trees \tPre- 118/acre \tPost-24.8/acre Grass \tPre- 16.3/m2 \tPost- 19.2/m2 Shrubs \tPre- .5/m2 \tPost- .2/m2 | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 1550.28 | 1550.28 |  | BLM and Cooperators | Fire hazard, Forest health, Habitat quality, Invasive species, Loss of desirable species, Public safety, Rangeland health, Threatened species, Endangered species, Habitat for wildlife, Hazardous fuels reduction, Invasion by pinyon-juniper, Loss of sagebrush, Pinon-juniper, Sensitive species, Wildlife in treated area | The objective is to move the area towards meeting rangeland health standards by reducing juniper encroachment. The burn should result in a mosaic of burned and unburned patches within the jackpot unit. |  |  | Snow, Wet | Soils were very moist with pockets of snow here and there. | Berry Gulch Unit Partners: Nonprofit, Private, State | 55:48
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 56487 | 21632 | Implemented | Unknown | 2 | 2017-04-04 | 2017-04-16 | Acres | 505.74 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Jackpot | 0 | [7 empty] | Project involves jackpot burning of slash and girdled juniper in the spring as not to burn surrounding vegetation | Planned treatment in HL focus area. Project involves jackpot burning of slash and girdled juniper in the spring as not to burn surrounding vegetation. Treatment is located adjacent to the Southern Idaho Northern Nevada SFA as well as the Southern Owyhee. | Jackpot burn | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 505.74 | 505.44 |  | BLM and Cooperators | Fire hazard, Forest health, Habitat quality, Invasive species, Loss of desirable species, Public safety, Rangeland health, Threatened species, Endangered species, Habitat for wildlife, Hazardous fuels reduction, Invasion by pinyon-juniper, Loss of sagebrush, Pinon-juniper, Sensitive species, Wildlife in treated area | Reduce hazardous fuels accumulations as the result of past juniper treatments by igniting red needle juniper. |  |  |  |  | Dutcher Spring Partners: Nonprofit, Private, State | 22:07
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 56488 | 21632 | Implemented | Unknown | 2 | 2017-09-26 | 2017-09-30 | Acres | 6608 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | The broadcast burn will be implemented under conditions designed to result in 50-70% seral juniper mortality within the treated areas. A mosaic burn patch size ranging from \xbd acre to approximately 20 acres is anticipated, although larger burn patch sizes would be acceptable. | Planned treatments in HL focus area.. This project is located within 5 miles of two SFA. Project will expand SFA boundaries. A. \tIgnition Time Frames/Season(s): All Units-August to October B. \tProjected Duration: Blacklining operations are expected to last 1 operational period and aerial broadcast ignitions are expected to last 2-3 operational periods. Mop-up/patrol are expected to last 3-7 operational periods until the project can be safely left and/or the prescribed fire is declared out. | 9/26/2017 At approximately 1100 on September 26th, 2017, BLM resources arrived at the Pole Creek Rx and began setting up camp. Engine 1422 had a mechanical problem and was replaced with Engine 1421 in Jordan Valley, Oregon. At approximately 1500, resources were briefed and sent to their respective divisions on the Dutcher Spring Unit (DIV Alpha and DIV Zulu) to begin blacklining operations. At 1645 all resources were on the line, go-no-go checklist completed, and the test fire was initiated. All weather and fuel parameters were within prescription and blacklining was initiated at 1655 on both DIV Alpha and DIV Zulu. A few spot fires occurred along the northwest line (ridge road) and northern control line but were easily controlled. Blacklining operations were completed at 2045 and all resources were off the line and back in camp by 2130. Approximately 100-300\u2019 of depth was overserved along blacklines with some minor clean-ups needed during next operational period on 9/27. 9/27/2017 All resources were briefed at 0930 and aerial ignitions with the heli-torch and PSD platform began at approximately 1130 on the Dutcher Spring Unit. Some hand ignitions along blacklines were conducted in DIV Zulu to add depth to the blackline on the northwest corner of the unit. Hand ignitions were completed by 1330 and aerial PSD ignitions were used on the northwest corner of DIV Zulu at approximately 1400. All aerial ignitions were completed by 1900 with approximately 3,000 acres accomplished. One issue with PSD machine occurred during ignitions when the pins became clogged. The PSD machine was swapped out with another unit and ignitions commenced with minimal down time. All resources were off the line and back in camp by 1900. 9/28/17 All resources were briefed at 0930 and aerial ignitions with the heli-torch and PSD platform began at approximately 1100 on the Dutcher Spring Unit. At approximately 1200 the BLM fuel tender (FT) 1199 supplied the Timberland contractor with 500 gallons of fuel for torch mix. At 1300 it was decided to send FT 1199 back to Boise to get fuel for the contractor in the event they were unable to be re-supplied. FT 1199 stayed in Boise overnight and was to return the following morning (9/29) with fuel to support aerial ignitions. All aerial ignitions were completed by 1900 with approximately 3,000 acres completed. The Dutcher Spring Unit was completed with some clean-up needed the following operational shift (9/29). All resources were of the line and back in camp by 1900. Engine 1433 was demobed from the burn by 1600 however all remaining resources were adequate to meet the minimum required organization necessary according to the burn plan. 9/29/2017 All resources were briefed at 0930 and aerial ignitions with the heli-torch and PSD platform began at approximately 1130 on the Hoot Owl Unit. Hoot Owl was ignited starting on the northeast corner of the unit and was completed within approximately 40 minutes. Burning conditions during the day were very favorable and the best that had been observed throughout the week. All ground resources were consolidated under Division Alpha and some mop-up and minimal hand ignitions were needed on the Dutcher Spring Unit. Once Hoot Owl was completed, both the heli-torch and PSD platform returned to the Dutcher Spring Unit and began ignitions within small pockets of unburned fuel. Ground resources were moved to the Payne Ranch while burning the last section of the Dutcher Spring Unit along meadows of private land. At approximately 1415 all ignitions were completed. The hoselay along the handline was pulled and all resources except Engines 1415 and 1416 were released by 1600. Total acres completed between the Dutcher Spring and Hoot Owl Unit was 6,608 acres. 9/30/2017 The line was patrolled during the morning hours and was deemed secure. All remaining resources broke down camp and were demobed back to Boise by 1100. A light wetting rain was observed over both units during the morning hours. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 6613.34 | 5101.63 |  | BLM and Cooperators | Fire hazard, Forest health, Habitat quality, Invasive species, Loss of desirable species, Public safety, Rangeland health, Threatened species, Endangered species, Habitat for wildlife, Hazardous fuels reduction, Invasion by pinyon-juniper, Loss of sagebrush, Pinon-juniper, Sensitive species, Wildlife in treated area | The objective of the Pole Creek prescribed burn is to move towards meeting rangeland health standards by reducing juniper encroachment. The resource objective is to move the area closer to reference conditions through the utilization of juniper treatments and to further improve upland and riparian conditions in combination with a grazing decision that implements changes to livestock management. |  |  |  |  | Dutcher Spring Unit and Hoot Owl Unit partners: Nonprofit, Private, State | 30:24
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 56489 | 21632 | Implemented | Unknown | 2 | 2018-04-09 | 2018-04-22 | Acres | 2431.5 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | The jackpot burn will be implemented under conditions designed to result in 70-90% of available jackpot fuels ignited. | Juniper trees within all units have been pretreated with a combination slashing and girdling. This has created \u201cjackpots\u201d of fuels across the landscape. The juniper trees have been allowed to sit on the ground for anywhere from 1-3 years to cure out prior to ignition and provide for better consumption when ignited. Once cured, the jackpots of trees will be ignited during the late fall to early spring when the risk of spread is low. This treatment allows for only the jackpot fuels to be burned and not the surrounding vegetation. Since burn patches would normally be confined to the individual tree debris zone, most patches would be small (less than two acres), although some larger patches may also occur. Timberland Helicopter Services will provide the helitorch, mix truck, aircraft, pilot, mechanic and fuel. Pole Creek: (approximately 2,400 ac). \u2022 Day One (4/9/2018): The helicopter will arrive in Jordan Valley, OR the day before the ignition and marry up with the helicopter manager, get a pre-use inspection, load frequencies and obtain a briefing for the next day\u2019s work. \u2022 Day Two (4/10/2018): The helicopter will fly to Pole Creek, land get a briefing from the helibase and burn boss. Required checklists including \u201cHelitorch Operations Go/No-Go Checklist\u201d will be completed and checks on the equipment will be made. The helitorch will light the unit. The aircraft will return to Jordan Valley at the end of the day. \u2022 Day Three (4/11/2018): The helicopter will continue to light the unit as needed and aim to complete all firing. The aircraft will return to Jordan Valley at the end of the day. \u2022 Day Four (4/12/2018): If all firing was not completed on the prior day and hours are available on the contract then the helicopter will continue to light the unit as needed to complete the unit. It is anticipate that this would be a minimal amount of FT. If all acres are completed then the aircraft will released to Home Unit at the end of the day. | 4/9/2018 At approximately 1030 on April 9, 2018, BLM resources arrived at the Pole Creek Jackpot RX Helibase and received a briefing. At 1100 aviation personnel conducted pre-use inspections on Helicopter 73U, a GO/NO GO checklist for helitorch operations was completed, and ground resources drove UTVs out to the Horse Flat Unit. At 1225 a prescribed fire GO/NO GO checklist was performed and test fire completed on the northeast corner of the unit. Winds were out of the South at 1-3mph with gusts to 5mph. At 1230 a recon flight was conducted with the pilot and RXB2(t) to familiarize with the burn unit. Aerial ignitions with the helitorch began at 1300. At 1400 it was determined that only jackpot piles that had come into direct contact with the burn gel were igniting and the decision was made for the helicopter to concentrate on the highest density areas of jackpot fuels. Helicopter 73U averaged 3 helitorches per hour before having to refuel. At 1640 the helicopter had a torch malfunction (could not get wick to light), had to return to helibase and exchange torches for the spare torch, and was on the ground for approximately 30 minutes. Hand ignitions occurred simultaneously throughout the day in areas that didn\u2019t affect aerial burning operations. At 1840 ignitions were completed totaling 250 acres burned for the day. BLM resources returned to Boise and helicopter 73U returned to Jordan Valley, OR. 4/10/2018 All BLM resources briefed at Pole Creek Jackpot RX Helibase at approximately 0915. Ground resources then drove UTVs out to the Horse Flat Unit. Helicopter 73U arrived at helibase at 1030 and the pilot voiced concerns over high winds encountered from the ferry flight from Jordan Valley, OR to helibase. At 1045 a prescribed fire GO/NO GO checklist was completed followed by a test fire near the middle of the burn unit. Winds on the unit were out of the South at 5-7mph with gusts to 9. Hand ignitions began promptly after the test fire was completed. Aerial ignitions began at approximately 1215. Aerial ignitions ended at approximately 1540 due to unfavorable winds between helibase and the burn unit and helicopter 73U was released from the burn. At 1630 hand ignitions were completed totaling 350 acres burned for the day and BLM resources returned back to Boise. 4/22/18 All resources (13 personnel) were briefed at Pole Creek Jackpot RX Helibase at 0925. Resources then drove UTVs out to the Horse Flat Unit. At 1115 a GO/NO GO checklist and test fire were completed and burning conditions were determined to be in prescription. Winds were observed to be 3-5mph w/ gusts to 7mph out of the northwest. A squad of 5 personnel conducted burning operations near Little Willow Spring, while remaining personnel started burning at the southeast corner of the unit (within the full-cut area). At 1322 BDC was contacted and informed that burning operations were on schedule and going well. At approximately 1400 the squad of five personnel tied back in with the main group to assist with hand ignitions. At 1635 ignitions were completed totaling 500 acres burned for the day. At 1750 all UTVs were loaded onto trailers and personnel returned to Boise. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 2431.5 | 2431.5 |  | BLM and Cooperators | Fire hazard, Forest health, Habitat quality, Invasive species, Loss of desirable species, Public safety, Rangeland health, Threatened species, Endangered species, Habitat for wildlife, Hazardous fuels reduction, Invasion by pinyon-juniper, Loss of sagebrush, Pinon-juniper, Sensitive species, Wildlife in treated area | Move area closer to reference conditions impaired due to juniper encroachment. |  |  |  |  | Pole Creek Jackpot RX - Horse Flat Unit | 42:19
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 56494 | 21633 | Implemented | Unknown | 2 | 2019-09-09 | 2019-09-22 | Acres | 13503.83 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | The objective of the Trout Creek prescribed burn is to move towards meeting rangeland health standards by reducing juniper encroachment. The resource objective is to move the area closer to reference conditions through the utilization of juniper treatments and to further improve upland and riparian conditions in combination with a grazing decision (DOI-BLM-ID-B030-2009-0030-EA) that implements changes to livestock management. The prescribed fire objective is to conduct prescribed burning under conditions designed to result in 50-70% seral juniper mortality within the targeted vegetation types | Boise BLM will be conducting a 5-10 day prescribed burn on Juniper Mountain within the dates of September 15-30th. During the prescribed burn up to 70 people will be camping out on site. Planned treatment in HL focus area. Broadcast burn on Juniper Mountain to treat encroaching juniper and restore sag-steppe. Treatment is located within the Southern Idaho Northern Nevada SFA as well as the Southern Owyhee FIAT PPA. The Trout Springs Prescribed fire will utilize both hand and aerial ignition to complete the prescribed burn over a window of 7 days for a total of 13,734 acres. During the prescribed burn large sections of burn unit will be ignited each day (+2,000 acres) Trout Springs Broadcast Prescribed Fire Project Dates: September 15th, 2019 \u2013 September 30th, 2019 Size: 13,734 acres There is one prescribed fire planned; Trout Springs Prescribed Fire. Helitorch Operations Timberland Helicopter Services will provide the helitorch, mix truck, aircraft, pilot, mechanic and fuel. Trout Springs: (approximately 13,3734ac). \u2022 Day One (9/15/19): The helicopter will arrive in Jordan Valley, OR the day before the ignition and marry up with the helicopter manager, get a pre-use inspection, load frequencies and obtain a briefing for the next day\u2019s work. \u2022 Day Two (9/16/19): The helicopter will fly to Trout Springs Helibase, land get a briefing from the helibase and burn boss. Required checklists including \u201cHelitorch Operations Go/No-Go Checklist\u201d will be completed and checks on the equipment will be made. The helitorch will begin unit ignitions. The aircraft will return to Jordan Valley at the end of the day. \u2022 Day Three (9/17/19): The helicopter will continue unit ignitions. The aircraft will return to Jordan Valley at the end of the day. \u2022 Day Four (9/18/2019): The helicopter will continue unit ignitions. The aircraft will return to Jordan Valley at the end of the day. \u2022 Day Five (9/19/2019): The helicopter will aim to continue to light the unit as needed to complete the unit. If all acres are completed then the aircraft will released to Home Unit at the end of the day. If ignitions are not complete aircraft will return on 9/20/2020. \u2022 Day Six (9/20/2019): The helicopter will aim to continue to light the unit as needed to complete the unit as well as final recon. If all acres are completed then the aircraft will released to Home Unit at the end of the day. This Burn Plan is written to address the broadcast prescribed burning of the 3 southern pastures within the Trout Springs Grazing allotment located in the Owyhee Field Office scheduled during the fall of 2019. Other pastures scheduled to be burned will be addressed through subsequent burn plans addressing those areas in the future. The Trout Springs allotment consists of a 5 pasture grazing system with an additional small pasture known as the Hanley Holding Field (total of 6 pastures). The pastures scheduled for broadcast burning fall of 2019 are: Twin Springs Middle Fork Thomas Creek Total = 13,734 acres | GIS is implementation data. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 13503.83 | 12515.27 |  | BLM and Cooperators | Forest health, Habitat for wildlife, Habitat quality, Hazardous fuels reduction, Invasion by pinyon-juniper, Loss of desirable species, Pinon-juniper, Public safety, Wildland Urban Interface, Wildlife in treated area | The Trout Springs broadcast prescribed burn will be treating acre of 13,734 acres of juniper woodland that has been found as a contributing factor in the Trout Springs Allotment\u2019s not meeting grazing standards. | [5 empty] | 57:33
Model 15 | Nothern Basin and Range | Prescribed burn |  | 57714 | 22049 | Implemented | Unknown | 2 | 00/00/2014 | 9/00/2014 | Acres | 12502 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [8 empty] | No documents - Unknown | Data obtained from this treatment's GIS Attribute Table - Units 1 and 2 Broadcast burning completed. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 12052.27 | 11801.24 |  | BLM | Fire hazard, Cover for wildlife, Habitat for sage grouse, Habitat for wildlife, Habitat productivity, Habitat quality, Hazardous fuels reduction, Loss of desirable species, Pinon-juniper, Rangeland health, Nesting bird species, Wildlife in treated area | Fuels reduction - Sagegrouse and Rangeland vegetation. |  |  |  |  | HFR and HLI initiative. | 18:02
Model 15 | Nothern Basin and Range | Prescribed burn |  | 58206 | 22144 | Implemented | Unknown | 1 | 00/00/2009 | 00/00/2010 | Unknown |  | Prescribed Burn | Prescribed Burn | Prescribed Burn | 0 | [7 empty] | Fuels reduction | Prescribed burning could occur in all units. During winter, spring, or fall piles in accessible areas would be burned using drip torches; some units could be ignited from the air using plastic sphere dispensers or \u201cheli-torches.\u201d All-terrain vehicles (ATVs) and/or horses may be used to transport fire personnel and equipment. The Proposed Action was designed to minimize surface disturbance by delineating the individual treatment units along natural barriers. Natural fuel breaks, roads, foam-lines, and hand lines would be used as fire lines when conducting prescribed burns. Hand lines, if required by the burn plan, would result in surface disturbance. All constructed lines would be rehabilitated (i.e., water barred and seeded) after the burn. When feasible, spring burning would use snow fields as natural fire breaks; this would reduce the need for fire line construction. Where treated areas (particularly aspen stands) are easily accessible to livestock, temporary protective fencing would be erected (e.g., buck and pole fence or trees dropped and jack-strawed around sensitive areas). | GIS is implementation data | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 686.52 | 635.36 |  | Unknown | Fire hazard, Hazardous fuels accumulation, Hazardous fuels reduction | The purpose of the Proposed Action is to (1) reduce the potential for large, high-intensity, high-severity wildland fires that harm or destroy life, property, and/or resources, and (2) improve forest and rangeland health by increasing disturbance to a more natural (i.e., historic) level within the Soda Hills project area. The project is needed because (1) the risk of intense and severe wildland fire (particularly crown fire) is high due to dense and continuous stands of vegetation (2) fuel loading in some areas of the project is high especially in Douglas-fir stands, and (3) aspen and mountain shrub regeneration is very low or is not occurring. | [5 empty] | 55:26
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 62111 | 22864 | Implemented | Unknown | 2 | 9/00/2008 | 9/00/2008 | Acres | 2379 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Broadcast burn |  | Broadcast burn completed GIS is implementation data | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 2378.98 | 2348.41 |  | BLM | Forest health, Hazardous fuels accumulation, Hazardous fuels reduction | Juniper, Post-Treat Cleanup, Fuels Reduction |  |  |  |  | Miller broadcast | 40:00
Model 15 | Nothern Basin and Range | Prescribed burn | Targeted juniper | 62112 | 22864 | Implemented | Unknown | 2 | 10/00/2011 | 10/00/2011 | Acres | 194 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Pile Burn | 0 | [7 empty] | Machine Pile burn |  | Pile burn completed GIS is implementation data | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 193.63 | 193.61 |  | Unknown | Hazardous fuels accumulation, Hazardous fuels reduction | Juniper, Post-Treat Cleanup, Fuels Reduction |  |  |  |  | Mahon West | 44:00