## model28-treatment-info
Model | Ecoregion | Treatment | LO_notes | Trt_ID | Prj_ID | Plan_Imp | Success | Dates_Confirmed | Init_Date | Comp_Date | Units | Num_Units | Trt_Type_Major | Trt_Type_Sub | Treatment_Type | Treatment_Seeded | Seed_List | Seed_Mix_Name | Seeds_or_Seedlings | Seed_List_Confirmed | Control_Areas | Seed_Application_Rate | Seed_Notes | Objectives | Planned_Implementation | Actual_Implementation | Treatment_Effect_and_Results | Trt_Feature_Type | Feature_Status | How_Feature_Created | Feature_Creation_Date | Total_Acres | BLM_Acres | GIS_Notes | Initiated_By | Trt_Concerns | Trt_Concerns_Desc | Problems_Apply_Trt | Problems_Apply_Trt_Desc | Conditions_At_Trt | Conditions_At_Trt_Desc | Trt_Notes | User_Updated
Model 28 | Central Basin and Range | Post-burn ground seeding | Possibly seeded sagebrush | 16089 | 5833 | Implemented | None | 2 | 2013-03-05 | 2013-12-19 | Acres | 258 | Seeding | Ground Seeding | Ground Seeding | -1 | Confirmed seed list | ARTRV seeding | Seeds | Confirmed on Paper | Unknown | Unknown | Application rate unknown. | The purpose of the treatment is to prevent the loss of priority sage-grouse habitat. The loss of nesting habitat in this small population would be detrimental to the populations' ability to successfully nest and rear young. | Seeding will occur in small (up to 10 acre) patches throughout the key habitat. Seeding will occur in the fall and early winter of 2012/2013 and/or fall/early winter of 2013/14. Based on past experience, availability of site appropriate seed for the southwestern Great Basin is sparse. Also due to the severity of the 2012 fire season it is expected that obtaining seed by the early winter of 2012 may not be reasonable therefore seeding may be delayed till the following year. Seed will be dispersed either by hand using a broadcast seeder or where appropriate by a drill seeder. | FY13: 2022 On 2/25/2013 seeding was attempted but the area was still not accessible due to snow. 2022 On 3/5/2013 a 50 acre area (see Seeding Treatment Area map) was seeded (with permission from the WO) with 80 bulk pounds of mountain big sagebrush (ARTRV). - Seeding was conducted on the front end of a predicted snow storm. - Seeding was done by hand. Conditions were very windy and snow was no longer present in the seeded area. - The predicted snows did not reach the seeded area and immediately following the seeding conditions were extremely windy. 2022 All of the unused seed was returned to the BLM Seed Warehouse. Of the reported treatment cost, over half is for seed that was returned to the Seed Warehouse. FY14: 2022 ARTRY was seeded on 12/19/2013. Seeding was done on this day because a light snow had fallen overnight and snow was predicted throughout the day and evening. Seed was dispersed with hand seeders on top of newly fallen snow. 2022 Sagebrush seed was also collected from nearby unburned areas and the seed was dispersed in the burn area. |  | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2015-02-23 | 258.8603 | 258.8606 |  | BLM | Erosion, Establishment of seeded species, Habitat for greater sage grouse, Habitat productivity, Invasion by non-native annuals, Native seedbank degradation, Noxious weeds | The purpose of the treatment is to prevent the loss of priority sage-grouse habitat. The loss of nesting habitat in this small population would be detrimental to the populations' ability to successfully nest and rear young. | None |  | None |  | All of the unused seed was returned to the BLM Seed Warehouse. Of the reported treatment cost, over half is for seed that was returned to the Seed Warehouse. | 18:47
Model 28 | Central Basin and Range | Post-burn ground seeding | Seeded wheatgrasses, wildrye, fourwing saltbush, sagebrush | 16425 | 5939 | Implemented | See Comments | 2 | 2004-01-05 | 2004-01-20 | Acres | 726 | Seeding | Ground Seeding | Ground Seeding: Broadcast | -1 | Confirmed seed list | Gandy Seeding | Seeds | Confirmed in GIS | Unknown | Species Specific | Acres taken from GIS. Most Wyoming Big sagebrush inoculated. See GIS attribute table for more information. | The reestablishment of plant species that provide browse and cover in the area would allow for improved habitat for many wildlife species associated with sagebrush habitat types on a seasonal or yearlong basis. | Treatment of the big sagebrush seed with a mycorrhizal fungi inoculant available on the market would be considered, as deemed necessary. Mycorrhizal fungi is a beneficial native organism of the soil that has likely been depleted or lost on the ecological sites due to disturbance. These thread-like fungi attach themselves to plant roots and help supply plants with nutrients. It allows sagebrush seedlings, as an example, to efficiently use available moisture and nutrients needed for survival to maturity. The plan called for overseeding approximately 130 acres along the drainages (in soil inclusions which supported big sagebrush range sites prior to the disturbance) in the seeding area classified as salt desert type in Phase II, and 400 acres consisting of every fourth swath or 1/4 of the acreage of the area classified as big sagebrush type in Phase II (based on soils). | The Izzenhood Phase II Big Sagebrush Seeding Project began with Ken Wilkenson (BLM Wildlife Biologist) touring the site with Marty Eldridge (BLM Equipment Operator) on December 22, 2003. There was a break due to the holidays and actual seeding began on January 5, 2004. The project was done "in house&& with BLM labor, the BLM's John Deere model 7800 4WD tractor and two Gandy seeders borrowed from NDOW for this project. There was an average of 6 to 10 inches of snow covering the area throughout the project. Tire drags were pulled behind the seeders to cover the seed in the snow. There was some speculation that this might compact the seed in the snow delaying its ability to filter down and establish in the soil. The plan called for overseeding approximately 130 acres along the drainages (in soil inclusions which supported big sagebrush range sites prior to the disturbance) in the seeding area classified as salt desert type in Phase II, and 400 acres consisting of every fourth swath or 1;4 of the acreage of the area classified as big sagebrush type in Phase II (based on soils). The seed mix used on the project consisted of: 900 bulk pounds of Wyoming big sagebrush, 580 bulk pounds of Basin big sagebrush and 530 pounds of rice hulls (as a dispersing agent). The recommended broadcast seeding rate on a bulk pound basis was: 1.7 bulk lbs./acre Wyoming big sagebrush, 1.1 bulk lbs./acre Basin big sagebrush, and 1.0 bulk lb./acre rice hulls for a total broadcast rate of approximately 3.8 bulk lbs./acre. An additional 440 bulk pounds of the mix was treated with inoculum and was to be broadcast over section 22 at a rate of 6.8 lbs./acre. Due to a misunderstanding, it actually went on at approximately 3.4 lbs./acre. Section 26 was also seeded with the mix treated with inoculum. There was approximately 920 lbs. of seed left over when the project area was seeded at a rate of approximately 3.4 lbs./acre. Upon investigation we noticed that the area in section 22 called for a rate of 6.8 lbs./acre which would account for approximately 540 pounds of the leftover seed. Then there was the additional 440 lbs. of seed with inoculum (which was not accounted for) bringing the expected total to 980 pounds, which would more than explain the surplus. With the 920 lbs. left over, two of the main drainages in section 14 were seeded. We then started back over the swaths already done in section 22 to bring it up to 6.8 lbs./acre (not considering the 440 lbs. inoculum, however). At Tom Warren&$s request, after redoing only a few swaths, we moved to the large drainage in Phase I, sections 28, 32, and 33. Marty Eldridge did the main drainage with the Gandy seeders. The main fork to the east of the drainage in section 33 was broadcast by ATV. ATVs were also used to broadcast most of the drainages in sections 22, 26, 28, and 29. The ATVs used approximately 200 pounds of the same seed mix and added approx. 40 pounds Sandburg&$s bluegrass. Approximately 20 pounds forage kochia was added along with the Sandburg&$s Bluegrass to the mix broadcast by the ATVs in sections 28 and 29, in the Phase I area. The project was completed on January 20th. Approximately 726 acres were seeded with 2,510 bulk lbs. of seed mix yielding an average rate of 3.5 bulk lbs./acre. | In December 2003 and January 2004 an effort was made to broadcast seed and drag certain areas around the Izzenhood Phase I where the previous seedings did not come in well. The area disturbed while building the Izzenhood Protection Fence was also selected which would include some of the ground where the perimeter outline was disked and seeded during Izzenhood Phase I but was not completed. For more specific locations on these seedings refer to the map in the project files or they are also incorporated into GIS. Seed mixes were selected based on available seed in the warehouse and on the soils of the different sites selected. In December, when there was no snow on the ground, approximately 12 acres along the eastern edge of the SE \xbc of section 30 on Izzenhood Phase I was seeded with a mixture of: Western wheatgrass, Indian ricegrass, Sandberg bluegrass, fourwing saltbush, Bozoisky Russian wildrye and Hycrest crested wheatgrass. This was 100% covered with a drag. Approximately 4 acres along the eastern edge of the NW \xbc of sec.33 was broadcast with: Hycrest crested wheatgrass, Bozoisky Russian wildrye and forage kochia. This was also 100% covered with a drag. Both these areas were broadcast in overlapping strips which would yield a seeding rate of approximately 8 lbs/acre. Along eastern portion of the protection fence, sections 6,1,2,3 and 4 were seeded with a mixture of approximately: 40% Secar Snake River wheatgrass, 25% Sandbergs bluegrass, 15% forage kochia, 10% Wyoming big sagebrush and 10% Indian ricegrass. Approximately 9.5 acres along the western edge of the Phase I seeding in T35N R44E secstions 4 and 5 was reseeded with Bozoisky Russian wildrye, Hycrest crested wheatgrass, Nordan crested wheatgrass, Siberian wheatgrass, forage kochia and Wyoming big sagebrush. The remainder of the fence going west, sections 5 and 6, was seeded with a mixture of Bozoisky Russian wildrye, Sandbergs bluegrass, Indian ricegrass, western wheatgrass, fourwing saltbush and forage kochia. The seed was broadcast in a strip roughly 25 feet wide mostly along the northern side of the fence. However, an effort was made to broadcast seed through to the southern side of the fence, tumble weeds permitting, to a distance of 5 to 10 feet. Where section outlines had been previously disk/drilled, the swaths were broadcast on both sides of the fence. The area seeded along the protection fence, including the 9.5 acres reseeded in sections 4 and 5 of Phase I, was approximately 35 acres. Areas were either broadcast in overlapping strips or gone over twice yielding a seeding rate of roughly 8 lbs/acre. Monitoring sites were not set up on these seedings in 2004. | Polygon | Confirmed | Digitized by BLM field office personnel, using a GPS unit on the ground |  | 603.6948 | 530.3395 |  |  | Provide forage for wildlife, Provide cover for wildlife, Erosion, Habitat for mule deer, Habitat for wildlife, Impact on Cultural Resources, Invasion by Cheatgrass, Loss of vegetation, Noxious Weeds, Rangeland health, Habitat for antelope | 1) General conservation and rehabilitation of wildlife habitat and ecological sites in the Great Basin within Nevada BLM- Elko Field Office area of responsibility. Rehabilitation would also help prevent soil erosion. The reestablishment of plant species that provide browse and cover in the area would allow for improved habitat for many wildlife species associated with sagebrush habitat types on a seasonal or yearlong basis. 2) Establishment of vegetation that would provide a &&network&& of vegetative fuel breaks to stop or slow down potentially large scale wildfires that might occur on the area in the future. Fuel breaks would help to provide protection to the remaining blocks of native vegetation in the area and would become part of the network of seeding projects on the general area completed in the last 10 years as part of rehabilitation efforts. 3) Allow a forage base for domestic livestock management options. In concert with present seedings in the area, this seeding would allow more livestock management options to help improve the condition of other rangeland areas within affected livestock grazing allotments. The need of the proposed action is to help rehabilitate ecological sites in the Great Basin within Nevada BLM- Elko Field Office area of responsibility. The area has been negatively altered as a result of man-caused disturbances that have affected fire regimes and the function of ecological sites. Implementation of the proposed project would ensure that cultural resources are located and evaluated within the area, contributing to the BLM&$s overall legally mandated inventory of cultural resources on all federally-managed (public) lands. | None |  | None |  |  | 43:12
Model 28 | Central Basin and Range | Post-burn ground seeding |  | 19841 | 7236 | Implemented | None | 2 | 2011-11-01 | 2011-11-11 | Acres | 40 | Seeding | Ground Seeding | Ground Seeding: Broadcast | -1 | Confirmed seed list |  | Seeds | Confirmed on Paper | Unknown | Species Specific | The seed mix did not indicate whether bulk or PLS rates were used, therefore, unknown has been listed and all seed mix information has been entered into the Bulk category. | The objectives for cover will be to obtain 70% of all perennial plant cover found in the associated reference site, or, when not possible, achieve 50% of the lowest value for perennial cover associated with the appropriate ecological or range site by the ned of the third year. | Broadcast seed and harrow a mix of native grasses, and shrubs, approximately 40 acres. Then press seed into soil surface with tractor drawn rubber tire packer when surface soil moisture is sufficient to bind. A Type III cultural survey will be conducted prior to treatment. Sensitive areas identified by the survey will be avoided. | Broadcast Seeded 40 acres with Sandberg bluegrass (Poa secunda), Snake River wheatgrass (Achnatherum thurberianum), and forage kochia (B. prostrata), Wyoming big sagebrush (A. tridentata ssp. wyomingensis), and shadscale saltbush (Atriplex confertifolia). |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 39.5557 | 39.5557 |  |  | Habitat for greater sage grouse, Habitat for desert bighorn sheep, Habitat for antelope, Habitat for mule deer, Invasion by cheatgrass, Invasion by non-native annuals, Rangeland health, Loss of perennialsLoss of sagebrush, Loss of vegetation |  | None |  | None |  |  | 52:35
Model 28 | Central Basin and Range | Post-burn ground seeding |  | 28890 | 10654 | Implemented | None | 2 | 00/00/2002 | 00/00/2003 | Acres | 1127.44 | Seeding | Ground Seeding | Ground Seeding: Broadcast | -1 | Planned seed list |  | Seeds | Plan | Unknown | Species Specific |  |  | The area would then be seeded with native/nonnative fire resistant species (see Appendix G) by aerial or ground broadcast. |  | None | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 563.8415 | 536.0253 |  | BLM | Public Safety, Fire Hazard | The purpose is to manage BLM lands, in conjunction with other land owners, in such a way that the occurrence of large wildfires would decrease, therefore increasing firefighter and public safety. The SLFO would like to reduce the impacts of wildfire on rural communities, and ensure sufficient firefighting resources for the future. The proposed treatment is needed to reduce fuel loading, protect the Skull Valley Band of Goshute Indians and their adjacent reservation, protect the Remote Automated Weather Station (RAWS) , and also protect those individuals residing within the Skull Valley area. The prescribed burn and discing treatments would reduce the sites potential for wildfire, as well as determine future wildfire initial attack strategies. | None |  | None |  | It's unclear if this treatment was drill or aerial seeded. | 24:59
Model 28 | Central Basin and Range | Post-burn ground seeding |  | 29238 | 13678 | Implemented |  | 2 | 2014-11-10 | 2014-11-12 | Acres | 34 | Seeding | Ground Seeding | Ground Seeding: Hand Broadcast | -1 | Confirmed seed list |  | Seeds | Confirmed on Paper | Unknown | Species Specific |  | In summary, the proposed seeding treatments would be expected to have a long-term indirect effect of decreased carbon emissions and increased soil carbon sequestration by potentially reducing high-intensity wildfires, slowing the rate of carbon turnover, and providing long-term below ground carbon storage. | The treatment will seed 59 acres of BLM lands with mountain sagebrush ( Artemisia tridentata ssp. vaseyana) and bluebunch wheatgrass ( Pseudoroegneria spicata). Application of seed would be by hand seeding or ATV. | Hand seeded with mountain sagebrush (Artemisia tridentata ssp. vaseyana), fourwing saltbrush (Atriplex canescens), and bluebunch wheatgrass (Pseudoroegneria spicata). | Conclusion: In the third year of monitoring, the plot met the perennial cover objective for ESR and for density. Perennial plant cover dropped 2% from the previous year. There is a dominance of cheatgrass on site; however, there is a strong presence and diversity of bunchgrasses on site. In the second year of monitoring, the plot met perennial cover objective for ESR, but not for livestock closure or density of seeded species. Although the site is dominated by invasive annuals, there is a strong presence of cool-season grasses. Perennial plant cover remained the same as in the previous year. In the first year of monitoring, plot does not meet all perennial cover or density objectives. Hand seeding has not established seeded species yet. Seeding success may be hindered by drought conditions. The biotic integrity within the plot is reduced due to the dominate presence of invasive annuals. Plot also shows potential for Pinyon-Juniper encroachment. | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2019-09-06 | 34.13 | 29.32 |  | BLM | Habitat for wildlife, Habitat for greater sage grouse, Habitat for mule deer, Loss of native species, Loss of native vegetation, Loss of perennials, Loss of sagebrush |  | None |  | None |  |  | 42:48
Model 28 | Central Basin and Range | Post-burn ground seeding |  | 43343 | 16808 | Implemented | See Comments | 1 | 2016-09-21 | 2016-12-21 | Acres | 77 | Seeding | Ground Seeding | Ground Seeding: Broadcast | -1 | Confirmed seed list | Marigold Fire | Seeds | Confirmed on Paper | Unknown | Species Specific |  | The objective is to prevent sagebrush communities to transitioning into an annual plant state and restoring essential forage and cover for greater sage grouse. 1. Obtain an average of 1.5 seeded plant per meter\xb2 by the end of the fifth year following fire ignition, which occurred on 06/27/2016. 2. Obtain 100% or greater perennial cover of the low potential perennial plant cover for the appropriate ecological site by the end of the fifth year following fire containment. 3. The aerial seeding would result in lower abundance (density and cover) of invasive annual plant species, and a higher abundance of desirable perennial plant species than the unseeded control area. 4. Seeded species would be well established and reproducing. |  | Broadcast seed 77 acres with Wyoming sagebrush seed and native perennial forbs and grasses. | Objectives for aerial seeding are as follows: 1. Obtain an average of 1.5 seeded plant per meter\xb2 by the end of the fifth year following fire ignition, which occurred on 06/27/2016. 2. Obtain 100% or greater perennial cover of the low potential perennial plant cover for the appropriate ecological site by the end of the fifth year following fire containment. 3. The aerial seeding would result in lower abundance (density and cover) of invasive annual plant species, and a higher abundance of desirable perennial plant species than the unseeded control area. 4. Seeded species would be well established and reproducing. Rangeland Ecological Site: R025XY005NV Loamy 8-10 P.Z.: The reference plant community is dominated by Wyoming sagebrush, and Thurber2019s needlegrass. Reference vegetation community composition is approximately 55% grasses, 35% shrubs, and 10% forbs. T79-NorthBuffalo-MAR-17 Treatment: Aerially seeded with Wyoming sagebrush, Sandberg bluegrass (Poa secunda), bluebunch wheatgrass (Pseudoroegneria spicata), Munro2019s globemallow (Sphaeralcea munroana), and spiny hopsage (Grayia spinose). 2017: This plot met all objectives for density of seeded species. Perennial cover exceeded the objective of 11% by 17%, while density was 2.8, with an objective of 1.5. Sandberg bluegrass and bluebunch wheat grass were well established. Cheatgrass was present on site but had been reduced from aerial herbicide treatments. Invasive annuals such as cheatgrass and tall tumble mustard seemed restricted by the extremely rocky ground. Litter and bare ground were within reference, but soil stability was below reference. This may degrade the soil, which could compromise stability and water infiltration. For a photograph of line 1, see Figure 1. 2018: This is a plot that exceeded the perennial ESR objective; the perennial cover objective was 12.5% and the plot perennial cover was measured to be 21.3%. This plot did not meet the density objective of 0.5 plants per square meter; density was less than 0.1 target species plants per square meter. It was previously seeded with Wyoming big sagebrush, bluebunch wheatgrass, Munro2019s globemallow (Sphaeralcea munroana), spiny hopsage (Grayia spinosa), and Sandberg bluegrass. This gravelly plot is on a slope and primarily dominated by grasses and forbs, including cheatgrass, with scattered shrubs of rubber rabbitbrush. For photographs, Figure 2. 2019: This plot did not pass the ESR perennial cover objective with 10.6% compared to the 39% annual cover. The seeding density objective was met with Sandburg bluegrass and a small amount of globemallow spread out to 8.1 plants per meter squared. This is the third and final visit to this plot after the 2016 Marigold fire. The area is a mix of established perennial plants and widespread cheatgrass and tumble mustered. Rubber rabbitbrush is almost evenly spaced across the plot with well-established pockets of basin wild rye. There was juvenile sagebrush growing infrequently between the rabbitbrush. The interspaces were completely covered by cheatgrass and fallen and collected tall tumble mustard. For photographs, Figure 3. 2020: No updates. Conclusions: The Marigold Fire failed the ESR objective but passed the density objective for recovery post burn after the third year of monitoring. Non-native annuals are present and have become dominate in the fire area as well as the surrounding area. Sparse Wyoming sagebrush, evenly spaced rabbitbrush, few globe mallow, and many Sandberg bluegrass have survived the fire and are recruiting. Recovery of pre-burn state seems unfortunately unlikely beyond a shrub state with an annual understory. | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2017-12-06 | 45.774 | 45.5037 |  | BLM | Cover for wildlife, Forage for wildlife, Habitat for greater sage grouse, Habitat for sage grouse, Habitat for wildlife, Habitat productivity, Habitat quality, Invasion by non-native annuals, Loss of desirable species, Loss of native species, Loss of sagebrush, Noxious weeds, Invasive species, Sensitive species, Wildlife in treated area | Prevent sagebrush communities to transitioning into an annual plant state and restoring essential forage and cover for greater sage grouse. |  |  |  |  | Broadcast Seeding Spatial Data was created using the map included in the Monitoring Summary. Contact FO for most accurate shapefiles. S2 Ground Seeding "Broadcasted" reported done the fall of 2016 however, the Part 8 - Monitoring Results states an "aerial" seeding was performed but there is no other mention/map of an aerial seeding being done. It is assumed the monitoring results are really for the Ground broadcast seeding. | 40:11
Model 28 | Central Basin and Range | Post-burn ground seeding |  | 51000 | 20552 | Implemented | See Comments | 2 | 2017-01-11 | 2017-01-12 | Acres | 100 | Seeding | Ground Seeding | Ground Seeding | -1 | Confirmed seed list |  | Seeds | Confirmed on Paper | Unknown | Not Available |  | Primary objective is to accomplish an average establishment rate of no less than 1, seeded, desirable perennial plants per square meter by the end of the fifth year from fire containment | The treatment will broadcast Sandberg bluegrass (Poa secunda), bluebunch wheatgrass (Pseudoroegneria spicata ssp. spicata), Wyoming sagebrush (Artemisia tridentata ssp. wyomingensis), Nevada ephedra ( Ephedra nevadensis) in a banded pattern across areas of higher soil burn severity. | Seedings took place between 1/11/2017 and 1/12/2017. | Monitoring Results Summaries: Rangeland Ecological Site: R024XY058NV Sandy-loam. 8-10 P.Z..: The vegetation community for the sandy-loam. 8-10 P.Z., in reference condition, is typically dominated by Wyoming sagebrush and needleandthread (Hesperostipa comata). Reference vegetative composition is about 60% grasses, 5% forbs and 30% shrubs. T78-D1-SandPass-SAN-17: 2017: This plot met the perennial ESR objective. This plot did not meet the ESR density objective. This area is a sandy area primarily dominated lemon scurf pea (Psoralidium lanceolatum) with spaced populations of needle and thread Thurber's needlegrass and some California evening primrose (Oenothera californica). A very small population of young shrubs, primarily yellow rabbitbrush (Chrysothamnus viscidiflorus), were found in the area. Cheatgrass and tall tumblemustard were very common on site and almost dominate. Bare ground was greatly decreased and litter amount was much more than expected when compared to the reference state. For a photograph of line 1, see Figure 1. Conclusions: The Sand Pass fire monitoring plot met the ESR perennial and failed to meet density objective for recovery post burn after the first year of monitoring. The site is dominated by a perennial forb with a sub dominate population of perennial grasses. Cheatgrass is common in thick groups. No seeded species were found on plot, but the plot was dominated by perennials that were established before the fire. The plot was seeded in the fall of 2016. | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2019-09-05 | 353.15 | 351.29 |  | Unknown | Loss of perennials, Erosion, Forage for wildlife, Habitat for wildlife, Loss of native vegetation, Rangeland health, Special status species | The fire burned a cumulative total of 1,130 acres, with 441 acres of BLM-administered lands and 689 acres of private land. The fire area burned 68 acres previously in the Jungo Road fire that occurred in 1985. The fire burned 616 acres of mapped Greater Sage-Grouse Other Habitat Management Area (OHMA). The entire fire burned area is year-round pronghorn antelope habitat and 95% of the burned area is mule deer year-round habitat as defined by the Nevada Department of Wildlife. The loss of shrub cover will negatively affect these species which utilized shrubs for cover, foraging, and nesting. Rice2019s blue (Euphilotes pallescens ricei), a BLM sensitive species butterfly, is known to occur in the area of the fire. Rice2019s blue is dependent on buckwheat (Eriogonum spp.) as a larval host plant. Lahontan indigobush (Psorothamnus kingii), as special status species, has been observed growing within one mile of the fire and its habitat could be threatened due to the increasing population of non-native annuals caused by the Sand Pass fire. The Sand Pass allotment composes 698 acres of the burned area and the Bloody Runs allotment composes 432 acres of the burned area. The fire area has known populations of invasive annuals including cheatgrass (Bromus tectorum) and tall tumble mustard (Sysimbrium altissimum). Lack of treatment in the area could result in monocultures of cheatgrass directly after a fire. |  |  |  | The fire burned within two United State Department of Agriculture (USDA) Natural Resource Conservation Service (NRCS) soil map units, containing two to three soil components each. The different soil components are associated with different USDA, NRCS rangeland ecological site descriptions. The fire burned within Major Land Resource Area (MLRA) 24- Humboldt Area. The possible MLRA 24 rangeland ecological sites are R024XY005NV, which is a loamy site receiving 8-10201d precipitation annually, R024XY017NV, which is a sandy site receiving 8-10201d precipitation annually, R024XY058NV, which is a sandy loam receiving 8-10201d precipitation annually, and a dune land site receiving 8-11201d precipitation annually however, is not defined as an ecological site by NRCS. The soils in the fire area are identified as moderately erosive to water and wind events. The sandy nature of these soils will contribute to accelerated soil loss and deposition due to the loss of shrub and grass cover. |  | 20:20
Model 28 | Central Basin and Range | Post-burn ground seeding |  | 51043 | 20562 | Implemented |  | 2 | 2018-12-19 | 2018-12-19 | Acres | 5757 | Seeding | Ground Seeding | Ground Seeding: Broadcast | -1 | Confirmed seed list | Stream Shrub Mix | Seeds | Confirmed on Paper | Unknown | Not Available |  | Establish desirable species at 4 per square meter or more within 5 years. |  | Aerial seeding was completed on 12/19/18 by Hammond Helicopter at a cost of $4.45/ac. | The three sites that were aerial seeded only had no seedlings present of seeded species, but good return of perennials, primarily species that were seeded in previous ESR treatments. Field bindweed was observed at the north monitoring site on Cedar Hills, but no other noxious weeds were observed at study sites or in the surrounding area. Detailed vegetation monitoring results are documented below. The ESR treatments on the Stream Complex Fire still shows good recovery overall the second year following the fire. Density of perennial species for four sites is on track to meet the four-year seeding objective. Only a couple seeded forage kochia plants were found in the aerial seeded sites, but re-established perennials from previous seedings came back well. The chaining site seeded with a native/introduced mix had very few seeded species observed, with results similar to 2018. The chained site that received the native mix had good success in 2018 with establishing seeded species, with a total species composition of 77%. That went down in 2019 to 18% in 2019. Density of perennial plants also went from 12 plants per square meter to 5. The site has almost been completely taken over by tall tumblemustard where there had previously been bare ground. Foliar cover went from 13% to 98%, with tumble mustard accounting for 80% of that. In 2020, the density of seeded or re-established perennial species averaged an impressive 20.77 plants per square meter. Perennials have stabilized soils and appear to be competing well with cheatgrass. Relative frequency of perennial species average across the five sites was 53.32%. No noxious weeds were observed within the ESR site, nor were any found by the SLFO Weeds crew when they monitored in June, 2020. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 5761.14 | 5761.14 |  | Contractor | Loss of desirable species | Establish desirable species. | [5 empty] | 37:35
Model 28 | Central Basin and Range | Post-burn ground seeding |  | 53065 | 20986 | Implemented | Unknown | 1 | 2018-02-01 | 2018-03-31 | Acres | 546 | Seeding | Ground Seeding | Ground Seeding: Broadcast | -1 | Unknown seed list |  | Seeds | Unknown Seed List Origin | Unknown | Not Available |  | To establish native perennial vegetation within the burn perimeter to maintain sage-grouse habitat and limit the amount of non-native invasive species cover post burn. | Unknown | In addition, 546 acres were broadcast seeded with Wyoming/Lahontan sagebrush. | Unknown | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | None | 445.02 | 420.45 |  | BLM | Cover for wildlife, Habitat for wildlife, Habitat for sage grouse, Invasion by cheatgrass, Invasion by non-native annuals, Invasive species, Loss of desirable species, Nesting bird species, Noxious weeds, Vegetal cover, Wildlife in treated area | To maintain sage-grouse habitat and limit the amount of non-native invasive species cover. | Mechanical problems during seed application, Seed application took a longer than expected, Tires blowing out | Several mishaps and altering events occurred. This site is approximately a 1-hour drive from any services. We experienced several flat tires on the drill seeders and UTVs which slowed seeding efforts significantly. | Snowing | Finally, we were forced to cease due to heavy snowfall. | Total cost for ground seeding - $186,000 (It was not reported how much drill vs broadcast costed individually). Eagle Lake CA | 49:41
Model 28 | Central Basin and Range | Post-burn ground seeding |  | 57585 | 22014 | Implemented | See Comments | 2 | 2017-10-01 | 2018-09-30 | Acres | 55 | Seeding | Ground Seeding | Ground Seeding: Hand Broadcast | -1 | Confirmed seed list | Ground Seeding and Aerial Drainage Mix | Seeds | Confirmed on Paper | Unknown | Species Specific |  | Objective: The objectives for cover will be to obtain 70% of all perennial plant cover found in the associated reference site, or, when not possible, achieve 50% of the lowest value for perennial cover associated with the appropriate ecological or range site by the end of the third year. Density objectives for aerially seeded areas will be based on having three seeded species firmly rooted per square meter by first or second growing season following seeding. | The BLM proposes to broadcast seed by hand a total of 40 acres of land within Sacramento Canyon. Seeding would occur in the December 2017 or January 2018 | Ground seed 55 acres with competitive perennial grasses and forbs along riverbanks and stream edges where overhead power lines prevent aerial seeding. This activity will be coordinated with chemical control of invasive annual plant species. A portion of this work was performed with NDF to hand-seed. | 2020 was a difficult year due to the coronavirus and most notably the season started later than usual. This could show itself as an incorrect perennial species count due to many drying out before June when monitoring began. After the third year of treatments, monitoring results show that all five of the plots have met their plant density objectives, and all but one plot failed the ESR perennial objective. Natural recovery has excelled compared to the seeding aspect. Unfortunately, the perennial count was influenced by the dead and burnt sagebrush and Utah juniper found during LPI. As a common trend, the plots that were lower and close to roads had a higher amount of annual invasive grass. T108 was a slight exception with a strong perennial population and a diverse annual presence. This fire will continue to develop with reestablishing shrubs and grasses contending with cheatgrass being present. | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2021-04-07 | 111.69 | 109.66 |  | BLM | Erosion, Establishment of seeded species, Invasion by cheatgrass, Invasive species | Infestations of at least four noxious weed species occur within and outside the burned area. Saltcedar (Tamarix sp.), Russian knapweed (Acroptilon repens), whitetop (Cardaria draba), and Scotch thistle (Onopordum acanthium) all occur within and outside the fire boundary. Other exotic invasive species such as cheatgrass, Russian olive (Elaeagnus angustifolia), and bull thistle (Cirsium vulgare) are also at risk of increasing within the burned area without additional treatment. Seeding of perennial grasses and forbs along riverbanks and stream edges where overhead power lines prevent aerial seeding. | [5 empty] | 43:38
Model 28 | Central Basin and Range | Post-burn ground seeding |  | 70407 | 24967 | Implemented | Unknown | 2 | 2020-01-15 | 2020-02-12 | Acres | 1458 | Seeding | Ground Seeding | Ground Seeding | -1 | No seed list |  | Unknown | No Seed List | Unknown | Unknown |  | To inhibit invasive plant species | Drill seeding per treatment map. | Unspecified planting/seeding as part of the BPSS invasive annual control. Implementation verified using GIS attribute table. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | None | 1458.07 | 1458.07 |  | Unknown | Invasive species | Invasive plant species control | [5 empty] | 46:30
Model 28 | Central Basin and Range | Post-burn ground seeding |  | 73230 | 6070 | Implemented | Successful | 1 | 2011-10-01 | 2012-12-31 | Acres | 600 | Seeding | Ground Seeding | Ground Seeding: Dribble | -1 | Confirmed seed list |  | Seeds | Confirmed on Paper | Unknown | Unknown |  | Apply and Cover the seed to the burned area prior to winter and spring precipitation to establish seeded species, reduce invasive weeds, increase forage base, and reduce erosion. | The DWR has agreed to supply fourwing saltbush and bitterbrush seed as a dribbler mix to be applied through dribblers on the dozers while we are chaining. | The UDWR provided small burnet and cliffrose that was applied on dribblers. | S3 Aerial Seeding/ Single Chaining - Successful - See statement below. | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | 2024-06-04 | 417.5 | 416.8 |  | BLM and Cooperators | Establishment of seeded species | Establish seeded species, reduce invasive weeds, increase forage base, and reduce erosion. | [5 empty] | 22:23