## model30-treatment-info
Model | Ecoregion | Treatment | LO_notes | Trt_ID | Prj_ID | Plan_Imp | Success | Dates_Confirmed | Init_Date | Comp_Date | Units | Num_Units | Trt_Type_Major | Trt_Type_Sub | Treatment_Type | Treatment_Seeded | Seed_List | Seed_Mix_Name | Seeds_or_Seedlings | Seed_List_Confirmed | Control_Areas | Seed_Application_Rate | Seed_Notes | Objectives | Planned_Implementation | Actual_Implementation | Treatment_Effect_and_Results | Trt_Feature_Type | Feature_Status | How_Feature_Created | Feature_Creation_Date | Total_Acres | BLM_Acres | GIS_Notes | Initiated_By | Trt_Concerns | Trt_Concerns_Desc | Problems_Apply_Trt | Problems_Apply_Trt_Desc | Conditions_At_Trt | Conditions_At_Trt_Desc | Trt_Notes | User_Updated
Model 30 | Wyoming Basin | Prescribed burn | Reduce sagebrush, increase forage | 64 | 22 | Implemented | None | 2 | 1997-09-09 | 1997-09-09 | Acres |  | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | 1. Accomplish the burn with a fire that does not exceed the prescription parameters of line holding capabilities. 2. Create a mosaic of habitat and a more diverse vegetative community. Increase the availability/ accessibility of herbaceous forage for wildlife/livestock. 3. Kill sagebrush within the treatment area as shown on Exhibit A. | All firing will be by drip torch and terra torch. Strip head firing will be the principal firing technique but the Burn Boss may determine other techniques based upon observed and predicted fire behavior. Escape potential will be minimized by using various firing techniques in order to control burn patterns and fire intensities. B. |  |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 736.2543 | 254.0052 |  | BLM | Habitat for mule deer, Habitat for antelope, Forage for wildlife, Forage for livestock, Loss of perennials, Loss of vegetation | The proposed action is to conduct a prescribed burn in the Adam Weiss grazing allotment NO. 00637 located about 5 miles northeast of Grass Creek, Wyoming. The burn is necessary to implement the Adam Weiss Allotment Management Plan in compliance with the Grass Creek Management Framework Plan and the Absaroka Front HMP. | None |  | None |  |  | 36:58
Model 30 | Wyoming Basin | Prescribed burn | Reduce sagebrush and juniper | 1933 | 718 | Implemented | None | 2 | 1999-04-15 | 1999-04-15 | Acres | 254 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | The proposed action also includes a prescribed burn to reduce undesirable plant species, big sagebrush and juniper in the Individual Allotment. | Of the desired treatment area 500 acres are public lands, 90 acres are Forest Service lands and 24 acres are deeded lands owned by the Bullingers. There is approximately 160 acres of big sagebrush/bunch grass type on Forest Service lands within this proposal. To maintain consistency with the Big Horn Forest Plan, no more than 25~~ ( 40 acres) will be burned in any five year period on Forest Service lands. The prescribed burning would be planned for during both spring and/or fall, 1993 or later. A spring burn, which is first priority if possible, would occur early enough (February thru March 31st) prior to perennial grass plant green up to reduce plant mortality/damage by fire. If fall burns are conducted they will be after September 1st, allowing perennial grass plants to be dormant. The actual percent of the total project area that will burn depends upon the density of cover, amount of understory (fine fuels) and climatic conditions at the time of the actual burn. The job would be accomplished through manpower, hand held drip and or pneumatic torches will be used as the primary fire source. The job will . be accomplished by fire qualified personnel from the Worland District office .Fire lines will be necessary at intermittent locations, all lines will be burned out, no mechanical lines are necessary. No riparian areas will be burned |  |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 254.3598 | 254.36 |  |  | Loss of perennials, Loss of vegetation | The proposed action also includes a prescribed burn to reduce undesirable plant species, big sagebrush and juniper in the Individual Allotment. | None |  | None |  |  | 48:24
Model 30 | Wyoming Basin | Prescribed burn | Reduce sagebrush and juniper | 4405 | 1571 | Implemented | None | 2 | 2000-03-13 | 2000-03-13 | Acres | 683 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Reduce sagebrush and juniper within the blocks by 60 to 80% in a mosaic pattern. Kill 80% of the juniper in block# 1 Anticipated actual burn acres between 463- 616 acres which is 60-80% of treatment area. | The proposed action is a prescribed burn within the Allotment #02552 (see attached map). The proposed treatment are approximately 1,000 total acres, 600 acres of which are public land. Due to shallower soils, rocky drainages, and the percent canopy of sagebrush, the percentage of the burn area that burns is not a concern. The prescribed burn block on the west side will take place in the fall of 1998, depending upon climatic conditions. The burn on the east side will take place in the fall in one to two years, contingent upon the construction of an additional pasture fence. The burn will be accomplished with the permittee, Jim Wilson, the NRCS, and the Thermopolis Volunteer Fire Department. The permittee will rest the pasture for two growing seasons following the burn. | Area was burned |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1084.306 | 641.9296 | The reported fire report acerage was only 683 for this treatment not the 1084 digitized by BLM personnel. | BLM | Rangeland health | The purpose of the prescribed burn is to improve the quantity and quality of herbaceous vegetation by replacing big sagebrush dominated sites with herbaceous plant communities. | None |  | None |  |  | 10:54
Model 30 | Wyoming Basin | Prescribed burn | Reduce sagebrush | 9124 | 3263 | Implemented | None | 2 | 1995-03-20 | 1995-03-20 | Acres | 1024.9 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | First is to improve the ecological condition of these sites by reducing the density of the sagebrush (range site guides indicate that big sagebrush should not constitute more than 15% of production). Second, improve forage conditions for livestock. Third, improve conditions for wildlife, particularly antelope. Fourth, improve riparian conditions where heavy stands of sagebrush have moved in. Fifth, produce perennial or increased intermittent flows of water in Dry Creek, South Fork Dry Creek and Cottonwood Creek located in the Little Dry Creek Allotment. | The burns in the Little Dry Creek Unit would be conducted in the spring/fall and would be primarily done by the operator, with the BLM providing support, labor and material to prevent escape of the fire. In the Sage Creek units, the low density of the fuel dictates that fall burning should be conducted in order to be successful. However, if opportunities for spring burning arise, then such burning would be done. These burns would be conducted by the BLM. Spring burns, if attempted, would occur early enough and fall burns late enough to avoid fire damage to perennial grasses. Burns would be primarily small acreage, small percentage burns scattered over the entire study area to maximize diversity. The majority of the treated acres would be within these burn/treatment areas. The expected percent of the burn/treatment areas to be treated would range from 20 - 50%. Actual percentages of treatment areas would vary depending upon density of cover, overall production and climatic conditions at the time of the burn. It is possible that some burn blocks would result in percentages less than 20 or greater than 50%, but overall the burns should remain within the stated range (See Table l for summary of burn acres. Maps of key burn/treatment areas are found in Appendix l while estimated acreages and expected treatment percentages of burn units by burn block are reported in Appendix 2.). 1 |  |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1025.018 | 625.5194 |  | BLM and Cooperators | Forage for livestock, Loss of perennials, Loss of vegetation | A need for control burning was identified for the Sage Creek Units in Deseret Ranches of Wyoming Allotment Management Agreement of December 3, 1993. Further, a need to reduce sage brush competition through burning was identified by the operator for Little Dry Creek Allotment, especially in the higher elevations. Reduction of such stands of heavy sagebrush is often desirable since they will adversely compete with the development of grasses and forbs. If the stand becomes heavy enough, other species can be entirely crowded out. Several objectives are intended for this burn. First is to improve the ecological condition of these sites by reducing the density of the sagebrush (range site guides indicate that big sagebrush should not constitute more than 15% of production). Second, improve forage conditions for livestock. Third, improve conditions for wildlife, particularly antelope. Fourth, improve riparian conditions where heavy stands of sagebrush have moved in. Fifth, produce perennial or increased intermittent flows of water in Dry Creek, South Fork Dry Creek and Cottonwood Creek located in the Little Dry Creek Allotment. | None |  | None |  |  | 2:22
Model 30 | Wyoming Basin | Prescribed burn | Reduce sagebrush | 9778 | 3487 | Implemented | See Comments | 2 | 1998-09-25 | 1998-09-25 | Acres | 236 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | 1 . Accomplish the burn with a fire that does not exceed the prescription parameters of line holding capabilities . 2. Create a mosaic of habitat and a more diverse vegetative community . Increase the availability/accessibility of herbaceous forage for wildlife/livestock and remove conifer encroachment . 3 . Reduce sagebrush within the blocks by 80% . Remove 40% of the stems less than one inch in diameter, in a fall burn . | Firing will be by drip torch, propane torch and/or terra torch . Strip head firing will be the principal firing technique . The Burn Boss may determine other techniques based upon observed and predicted fire behavior. Escape potential will be minimized by using various firing techniques . |  | Willow Ck Double-H: Estimate 60% sage removal; Estimate 20-30% Stem[sp?] removal. [Burn Date 4/29/98] Willow Ck Block 1: Close to meeting objective of removing 80% of sage. Excellent in meeting objective of removing 40% of stem less than 1" | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 249.0597 | 201.2893 |  | BLM | Forage for wildlife, Forage for livestock, Habitat for wildlife | This project is in accordance with the Washakie RMP and grazing agreements. Long range goals are to improve livestock and wildlife forage, create more diverse habitat and to improve ecological condition. Site specific goals are as follows: 1. Accomplish the burn with a fire that does not exceed the prescription parameters of line holding capabilities. 2. Create a mosaic of habitat and a more diverse vegetative community. Increase the availability/accessibility of herbaceous forage for wildlife/livestock. 3. Kill 70-90 percent of the sage and juniper within the actual burn areas. Reduce sagebrush canopy cover by 50% and juniper canopy cover by 80%. 4. Enhance declining stands of aspen and cottonwood in riparian areas. | None |  | None |  |  | 23:56
Model 30 | Wyoming Basin | Prescribed burn | Reduce sagebrush, increase forage | 9960 | 3544 | Implemented | None | 1 | 00/00/1987 | 00/00/1987 | Acres | 1200 | Prescribed Burn | Prescribed Burn | Prescribed Burn | 0 | [7 empty] | Increase forage production of native perennial grasses and forbs. The burn should be in a mosaic pattern with 50%-75% of the sagebrush actually burned. | This burn will be accomplished by the use of hand drip torches or terra torch. Firing techniques will be strip head fire, head fire, and backing fire. Large patches of brush will be burned by using strip head fires; fingers of heavy brush will be burned by head fire and strip head fire. |  |  | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2014-07-29 | 2129.4328 | 1142.0136 |  |  | Brush control, Forage quality, Forage for livestock, Habitat for wildlife | Increase forage production of native perennial grasses and forbs. | None |  | None |  | Limited Information. | 50:43
Model 30 | Wyoming Basin | Prescribed burn | Reduce sagebrush, increase forage | 15228 | 5503 | Implemented |  | 2 | 1995-08-29 | 1995-10-11 | Acres | 462.75 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | 1. Accomplish the burn with a fire that does not exceed the prescription parameters of line holding capabilities . 2. Create a mosaic of habitat and a more diverse vegetative community. Increase the availability/accessibility of herbaceous forage for wildlife/livestock. 3. Partially alleviate big game damage in the spring to private irrigated lands by offering early succulent growth on public lands. | see prescribed burn plan. |  |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 462.7543 | 456.2185 |  |  | Forage for livestock, Rangeland health | This project is in accordance with the Cody RMP, within the Horse Creek Study Area which encompasses seven grazing agreements. Long range goals are to improve livestock and wildlife forage, create more diverse habitat and to improve ecological condition. Site specific goals are as follows: 1. Accomplish the burn with a fire that does not exceed the prescription parameters of line holding capabilities . 2. Create a mosaic of habitat and a more diverse vegetative community. Increase the availability/accessibility of herbaceous forage for wildlife/livestock. 3. Partially alleviate big game damage in the spring to private irrigated lands by offering early succulent growth on public lands. The Burn Bose, in consultation with the Resource Advisor, may adjust burn acres by treatment area and block to meet resource objectives. | None |  | None |  |  | 8:22
Model 30 | Wyoming Basin | Prescribed burn |  | 21225 | 7762 | Implemented | None | 2 | 1997-04-27 | 1997-09-29 | Acres | 4321.9 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | The proposed action is to conduct prescribed burns on approximately 8158 acres within the Devil's Canyon/Little Mountain area. Of these burn acres approximately 5028 acres are public, 2330 acres are private and 800 acres are state lands . | The proposed burning if approved would begin in the fall/spring of 1994/95 and continue for five to seven years or until completed . The majority of the burns will be conducted in the spring to take advantage of natural controls and r educe manpower costs. Spring burns will create a better mosaic of treated and untreated areas and will provide forage and ground cover shortly after treatment. Areas that cannot be spring burned will be burned in the fall if necessary . Spring burns will occur early enough and fall burns late enough to avoid fire damage to perennial grasses . North facing slopes off Dugans Bench, where effective soil moisture is greater, may have aspen seedlings planted following burning. This will generally take place following spring burning and where aspen is presently none existent. Treatment areas were jointly chosen by the Bureau of Land Management and Wyoming Game & Fish Department during visits to the area. Personnel from both agencies acting as resource advisors will be present to design the burns as they develop and address site specific concerns. The burns are proposed as primarily small acreage, small percentage burns scattered over the entire study area to maximize diversity while allowing important sagebrush stands to remain for winter forage and/or parturition cover for wildlife. Because of a concern for cover and aesthetics, older and heavier stands of limber pine and Douglas fir at the head of drainages and ridge line stands on the south side of Devil's Canyon will be excluded from burning as much as possible. Lighting techniques and timing of the burns will be carefully chosen so as to keep these areas from burning. Acreages and expected treatment percentages of allotments are represented in table 1 and maps of key burn treatment areas are found in Appendix 1. The majority of the treated acres will be within these burn/treatment areas. Generally, the desired percent of the burn areas to be treated is 40-60%, see table 2 for pasture specific burn acres/percent&$s in the Moss Ranch Allotment. These percentages will vary depending upon density of cover, overall production and climatic condition at the time of the burns. All burns will receive two growing seasons of rest from livestock grazing, and have long term management in place prior to burning. The prescribed burns will be accomplished hand labor, and hand held drip and/or pneumatic torches will be the primary fire source. Fire qualified personnel from the Worland District Office, Cody Resource Area, and Wyoming Game and Fish will conduct the burn. Fire lines will be necessary, especially during fall burns, however no mechanical lines will be constructed. No riparian areas will be burned. |  | see prescribed fire report | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 4322.143 | 1252.5394 |  | BLM | Rangeland health, Habitat for sage grouse | The primary goal for the area is to develop management strategies that maintain and restore the ecological integrity, productivity, and biological diversity on a mini-ecosystem basis . The proposed action is one step towards achieving this goal. | None |  | None |  |  | 58:07
Model 30 | Wyoming Basin | Prescribed burn | Reduce sagebrush | 25313 | 9314 | Implemented | None | 2 | 3/00/2007 | 2007-03-23 | Acres | 100.2 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Reduce/remove stands of large decadent basin big sagebrush along the riparian area in a mosaic pattern. | The burn will be completed using drip torches and possibly the terra torch. For all ignitions, the general tactic will be to anchor on the downwind side of the unit and progressing into the wind along the flanks creating black-line. |  |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 113.8677 | 108.6941 |  |  | Habitat for sage grouse, Migratory Birds, Provide forage for wildlife | The Rattlesnake Creek prescribed burn was proposed to further allow the riparian area and associated floodplain tiers to move towards a functional condition and upward trend by removing the decadent basin big sagebrush and encouraging more desirable riparian and upland vegetation species to establish and eventually dominate the site. It is also expected that by replacing the tall, heavy sagebrush plants with healthier, younger plants and more grasses and forbs, habitat quality for sage grouse brood-rearing will be improved by providing highly palatable and desirable vegetation and increasing insect food sources for broods. | None |  | None |  |  | 31:24
Model 30 | Wyoming Basin | Prescribed burn |  | 27111 | 9967 | Implemented | None | 1 | 00/00/1984 | 00/00/1984 | Acres | 1842.52 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [11 empty] | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1843.9816 | 1547.6108 |  |  | Unknown |  | None |  | None |  | There is very little information for this project. | 11:40
Model 30 | Wyoming Basin | Prescribed burn | Reduce sagebrush and juniper | 27343 | 10062 | Implemented | Unknown | 2 | 2006-10-03 | 2006-10-14 | Acres | 1698.8 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Much of the project area vegetation is composed largely of the sagebrush/grass type, with significant areas of the mountain shrub type (serviceberry, antelope bitterbrush, mountain mahogany, etc.) and aspen. These vegetation types in the area are rated in fuels condition classes I, II and III. Fuels in classes II and III are no longer within ecological limits and are susceptible to large wild fires. The use of prescribed fire can convert class II and III fuel types to class I types, which are within ecological limits and are not susceptible to large or damaging wildfires. The current composition of fuels condition classes is estimated to be Class I 15%, Class II 65% and Class III at 20%. The project area lies within the area of highest wildfire occurrence in the entire Southwestern Zone. Watershed conditions and rangeland health although satisfactory are less than ecological potential. Plant community diversity has been reduced with the succession of sagebrush and juniper communities. Unique vegetation types such as mountain shrub and aspen are in danger of being replaced by sagebrush due to interspecific competition. Prescribed fire can and has been used to improve water quality (long-term) by reducing overland flow of water, increasing ground cover and increasing infiltration levels, all of which reduce the amount of sediment that will reach streams. Sediment transported to streams by accelerated rates of erosion is a primary source of elevated levels of dissolved salts. Excess sedimentation and salinity are both issues in the Flaming Gorge Reservoir downstream of the project area. Flaming Gorge provides locally, regionally and nationally significant recreational activity particularly in the use of the fisheries it provides. As water infiltration is improved, spring flows will increase. Any water supplied to Sage Creek from spring flows would be cooler, and more constant in flow rates producing larger base flows in the late summer when the critical period for aquatic wildlife generally occurs. Springs can also be an important source of water for terrestrial wildlife. Most mountain shrubs (mountain mahogany, serviceberry, etc.) sprout after a fire. Prescribed fire can be used to remove competition from sagebrush and juniper allowing for re-sprouting of the mountain shrubs and increasing production and age class diversity. | The BLM proposes to treat with prescribed fire, approximately 9,000 acres within the Salt Wells Basin (Map 1). The entire burn block (Maximum Management Area, MMA) encompasses approximately 35 ,000 acres and includes approximately 700 acres of private land (Janets' Inc.) and 3,560 acres of State of Wyoming Trust land. Janet Scarpelli, president of Janets&$ Inc. has agreed to allow deeded lands under their ownership, within the project area, to be included in the burn. Mrs. Scarpelli is the only State of Wyoming grazing lessee, and has signed a consent form, for approval by the Wyoming State Land Board. The Salt Wells Basin Prescribed Burn is planned for the fall (October) of 2006. Vegetative communities targeted for treatment include sagebrush/grass, mountain shrub, and aspen, small areas of juniper encroachment (where young junipers are expanding into sagebrush/grass types) may also be included. To accomplish vegetation and habitat management objectives, the actual burned area will not exceed approximately 10,500 acres of the 35 ,000-acre block (30%). |  |  | Polygon | Confirmed | Digitized by LTDL data entry personnel using a confirmed map | 2014-08-11 | 1699.0643 | 1112.4954 |  | BLM | Aspen regeneration, Brush control, Encroaching vegetation, Erosion, Fire hazard, Habitat quality, Hazardous fuels reduction, Invasion by pinyon-juniper, Rangeland health, Sagebrush, Water quality, Sedimentation, Watershed health | This action will also meet the objectives developed for the Little Mountain Habitat Improvement Project and the Greater Red Creek ACEC for those portions of these special designations within the project area, including: 1) Improve watershed condition and enhance watershed values, including, but not limited to, improving channel stability, vegetative diversity and abundance, and water quality&* 2) Improve riparian areas that are at less than proper functioning to proper functioning condition as a minimum&* 3) Repair, improve, or maintain CRCT habitat in Sage Creek and its tributaries&* 4) Provide opportunities for dispersed recreation uses in the area that are consistent with the primary watershed, riparian, and fisheries management objectives&* and 5) Enhance and maintain important wildlife habitat. | None |  | None |  | Final units pulled from GIS. Dates pulled from EA addendum. | 57:16
Model 30 | Wyoming Basin | Prescribed burn | Reduce sagebrush, increase forage | 27457 | 10114 | Implemented | Unknown | 2 | 1995-09-26 | 1995-09-26 | Acres | 181 | Prescribed Burn | Prescribed Burn | Prescribed Burn | 0 | [7 empty] | 1. Accomplish the burn with a fire that does not exceed the prescription parameters of line holding capabilities. 2. Improve range condition by decreasing big sagebrush and increasing grasses and forbs. 3. Kill 70-90 percent of the sage within the actual burn areas. Reduce sagebrush canopy cover by 60% . 4. Improve Kirby Creek watershed condition by decreasing run-off with increased herbaceous vegetation. | Firing will be by drip torch. Strip head firing will be the principal firing technique. The Burn Boss may determine other techniques based upon observed and predicted fire behavior. Individual block ignition pattern will be determined by the Burn Boss and Firing Boss, the day of operation, based upon fuels and weather. | Area was burned | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 288.7282 | 288.7284 |  | BLM | Forage for livestock, Forage for wildlife, Rangeland health | The purpose of the proposed action is a prescribed burn to improve the quantity and quality of herbaceous vegetation by replacing big sagebrush dominated sites with plant communities consisting of mixed grasses, forbs, and shrubs. This project will improve. livestock and wildlife forage habitat, improve the ecological range condition, and create a more diversified and healthy habitat. It will improve the livestock distribution and take grazing pressure off of Sand Draw. | None |  | None |  |  | 51:08
Model 30 | Wyoming Basin | Prescribed burn | Reduce sagebrush, increase forage | 34147 | 12668 | Implemented | None | 2 | 2012-04-10 | 2012-05-09 | Acres | 1025 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | This burn is designed to increase seral stage diversity within the treatable vegetation by reducing confer encroachment and decadent stands of sagebrush and curlyleaf mountain mahogany stands. The results would lower the FRCC rating to a more normal condition (FRCC 1). Younger shrub and herbaceous response would increase the quality and quantity of forage, cover, nesting habitat and habitat diversity for wildlife into the future until this project area needs additional fire regime maintenance. | The plan is to primarily use a "ping-pong ball dispenser&& from a helicopter, which is a Premo MK ill Aerial Ignition Device; an aerial ignition device which injects ethylene glycol into a plastic sphere containing potassium permanganate. The primed spheres are ejected from the aircraft and would evenly distribute prescribed fire within the treatable vegetation. Our objective is to produce a mosaic burn ranging between 20 and 40 percent of the treatable vegetation. Black areas would generally be as long and narrow as possible to create maximum seral stage interspersion. Some treatment areas may vary in size as the control of a prescribed burn is variable depending on weather conditions. |  |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1024.75 | 866.5 |  |  | Habitat for mule deer, Habitat for desert bighorn sheep, Habitat for elk, Habitat for sage grouse, Habitat for wildlife | This burn is designed to increase seral stage diversity within the treatable vegetation by reducing confer encroachment and decadent stands of sagebrush and curlyleaf mountain mahogany stands. The results would lower the FRCC rating to a more normal condition (FRCC 1). Younger shrub and herbaceous response would increase the quality and quantity of forage, cover, nesting habitat and habitat diversity for wildlife into the future until this project area needs additional fire regime maintenance. Prescribed burning will also reduce fuel loading, fuel continuity, safety risks to the public, potential damage to private property, and loss or decline in conditions of wildlife habitat and watershed conditions in the event that a large scale wildland fire occurs. When applicable the Wyoming Guidelines for Managing Sagebrush Communities would be used and the project tailored to wildlife habitat requirements especially for bighorn sheep populations recently augmented and local populations of mule deer, elk, and sage grouse ( Centrocercus urophasianus). | None |  | None |  |  | 22:15
Model 30 | Wyoming Basin | Prescribed burn | Reduce sagebrush | 34316 | 12745 | Implemented | None | 2 | 1999-07-22 | 1999-09-23 | Acres | 2000 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | [7 empty] | Kill 30% of sage by remove 50% of stem material <1" | DRIP TORCH WILL BE USED TO IGNITE STRIP HEAD FIRES. SNOW BANKS, NATURAL FUEL BREAKS, AND TRAILS WILL USED FOR HOLDING. |  |  | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown |  | 1638.6676 | 1638.6691 |  |  | Habitat for wildlife, Forage for wildlife, Forage for livestock, Rangeland health | The purpose of this environmental assessment is to analyze proposed wildlife habitat enhancements along an approximately twenty five mile section of the Dry Creek riparian corridor and an upland area prescribed burn designed to reduce sagebrush density and improve vegetative diversity. Habitat enhancement projects would include prescribed burning , planting of food plots shrubs and cottonwood tree seedlings, and construction of dugout pit ponds . These actions are proposed to improve habitat for upland game birds, Neotropical migratory birds, waterfowl, and mammals that currently inhabit the Dry Cr eek riparian zone. The Whistle creek road prescribed burn would also be designed to r educe sagebrush density, improve vegetative diversity for wildlife and improve forage for wildlife, livestock and wild horses. Benefits of all the proposed actions would include: improved plant community diversity, increases in available forage for grazing animals including wildlife, wild horses and livestock&* improvements in riparian condition through better vegetative diversity and ground cover&* improvements in water quality obtained by decreasing erosion and sediment losses&* re-establishment of woody plant species by increasing subsurface water levels and planting native trees and shrubs. The proposed actions would achieve wildlife and watershed objectives of the Cody RMP and would help meet RMP livestock grazing management objectives . Some objectives of the Cody Wetlands HMP could also be achieved in an efficient and cost effective manner . | None |  | None |  |  | 42:51
Model 30 | Wyoming Basin | Prescribed burn | Reduce conifers | 72517 | 25539 | Implemented | Unknown | 2 | 2021-04-29 | 2021-05-14 | Acres | 592 | Prescribed Burn | Prescribed Burn | Prescribed Burn: Broadcast Burn | 0 | No seed list | [6 empty] | Reduce fuel loading and modify future fire behavior. Reduce fire suppression costs and aid in fire control should a future wildfire event occur within the proposed project area. Reduce the threat to public and firefighter safety. Minimize the loss of important ecosystem components from wildfire events. | The project area would be scheduled to be broadcast burned in the spring months or late fall when existing snow load drifting on leeward slopes can be utilized for fire spread control lines. Implementation would occur over a 3-10 year period, starting as early as the fall of 2019. Ignitions would be accomplished by use of a vehicle-mounted terra-torch where possible (along roads), by hand carried drip torches (areas of limited access such as steep draws, bowls, ridges, and where control may be difficult), and by helicopter with a Heli-torch or plastic sphere dispenser (PSD, areas difficult to access and deemed unsafe for hand ignitions). The majority of the treatment units within the project area would be hand ignited with drip torches. Constructed control lines would be created with hand tools, black lines (burning), water/foam (wet lines), or the use of a skid steer with mowing attachment. A cultural clearance has been completed for the project area, and any soil disturbing control lines constructed not been previously identified would require site-specific clearances. | Broadcast burn was completed, confirmed by GIS attribute table. | Unknown | Polygon | Confirmed | Digitized by BLM field office personnel, method unknown | 2024-03-19 | 591.03 | 591.03 |  | Unknown | Hazardous fuels accumulation, Forest health, Public safety | Boundary expansion of the Hadsell Watershed Prescribed Burn. Decrease conifer canopy and reduce fuel loading in a mosaic pattern in order to achieve land management objectives. Removal of younger age class conifers and reduction in fuel loading within this area will enable firefighters with a greater opportunity to prevent the spread of wildfire into dense lodgepole pine stands on the top of Green Mountain and to safely use existing 2-track roads as anchor points to stop the spread of wildfire to the north and east. | [5 empty] | 42:43